## INFORMAL & FORMAL PROJECTS
Project Priority List | [8 empty] | 2021-02-09 | [7 empty] | Informal and Formal Projects
Unit | Campus Priority | Control Code | Project Status Block | Project Type | Department Code | Sub Department Name | Bldg Code | Building Name | Project Request Name | Project Description | Date Created | Project Account Manager | Project Customer | Financial Account Manager | Scope & Budget Manager | Project Number | Project Coordinator | Scope & Budget | Approved Project Total | Amount Billed | Estimated Design Complete | Notes
IF | 6 | SA-0444 | Project On Hold Design Services | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE NORTH ROOF REPLACEMENT | Cone North Roof Replacement - Fully remove existing system to replace the Cone North Building Roofing System. | 2019-12-09 13:04 | MERCK, DONNA (dlmerck) |  | HARRIS, MELODY (mhharris) | BOAL, JOHN (jboal1) | 20-0112 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 2/9/2021: Project on hold.
AA | 0 | AA-1660 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY 310 HYDROLOGY & BIOCHEMISTRY LAB | Renovation of space on the on the 3rd floor as a hydrology and biochemistry lab and renovation of a classroom space on the 2nd floor. | 2019-11-06 12:30 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0084 | BOAL, JOHN (jboal1) | 35439 | 37439 | 27811.03 | 2020-05-29 | 2/9/2021: Four contractors were asked to price the project. Bids are due 2/23.
AA | 0 | AA-1661 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY 316 LANDSCAPE ECOLOGY LAB | Renovation of McEniry 316 and 313 for use as landscape ecology lab. | 2019-11-06 12:31 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0085 | BOAL, JOHN (jboal1) | 35000 | 38000 | 28111.28 | 2020-05-30 | 2/9/2021: Four contractors were asked to price the project. Bids are due 2/23.
AA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0020 | McEniry | MCENIRY HVAC UPGRADE | Replace HVAC in McEniry | 2019-11-19 15:06 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | BOAL, JOHN (jboal1) | 7336875 | 6635671.05 | 0 |  | Consultants: Architect: Jenkins Peer Mechanical Engineer: CMTA, Inc. (formally McCracken and Lopez) CM@Risk: New Atlantic Contracting Bid date for subcontractors was August 19. Project bid well under budget. Floors 2, 3 and 4 are under construction now. Completion of these floors is scheduled for May 15. Construction of the first floor and basement are scheduled to begin May 15 and be completed August 15. Installation of a full building exhaust system has been recently added to the scope of work. Completion of that exhaust system is scheduled for November. Return of occupants to the building is still scheduled for mid August.
AA | 0 | AA-1722 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY RESERACH LABS - DEMO & HVAC | Demolition and HVAC work to be completed in conjunction with McEniry HVAC & IT Infrastructure Replacement Capital Project | 2020-07-09 08:27 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 21-0007-I | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 2/9/2021: Scope of work of this project has been partially absorbed into the capital project. The rest of the work will be included in the individual lab projects. This project should stay open until it is determined how the completion of the lab projects will be funded.
AA | 0 | AA-1729 | Scope & Budget Requested | Informal Projects | 23900 | Graduate School | 0048 | Cato Hall | CATO 2ND FL LOBBY GRADUATE SCHOOL DROP BOX | The Graduate School would like to mount a document drop box in the second floor lobby of Cato Hall. The document box is 15 x 11.25 x 13.5 inches | 2020-09-30 07:57 | PENOUILH, STEVE (spenouil) | PENOUILH, STEVE (spenouil) | PENOUILH, STEVE (spenouil) | BOAL, JOHN (jboal1) | 21-0033-I | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 2/9/2021: Met with customer and Michael Rogers of the Renovation team before Thanksgiving. Customer is looking for a table to put the drop box on. This work can be accomplished with a work order.
AA | 0 | AA-1738 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY AV | AV work needed to update McEniry classrooms and teaching lab. | 2021-01-26 12:28 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 21-0068-I | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 2/9/2021: Initial meeting with customer was held last week. AISLE group is doing a building survey today. Price proposal will be submitted by Friday.
AA | 1 | AA-1696 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY 233 CAGIS COMPUTER CLUSTER RELOCATION | McEniry-CAGIS Computer Cluster Relocation | 2020-03-12 10:36 | SCHAUBLE, DONIA (dcooke) | JONES, PATRICK (pajones) | MCMANNEN, TONYA (tmcmanne) | SPATARO, EVAMARIE (espataro) | 20-0194 | BOAL, JOHN (jboal1) | 55000 | 55000 | 5700 | 2020-08-31 | 2/9/2021: Part of the scope of work has been incorporated into the capital project. Purchase orders were issued last week for Armstrong Mechanical and Republic Electric to complete the work. Also issued purchase order to CSI for cabling.
AA | 6 | AA-1670 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0017 | Belk Gymnasium | BELK GYM 024 KINESIOLOGY LAB | Belk Gym - 024 - Move human physiology research lab from Cameron 2nd floor to Belk Gym Ground floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:28 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0122 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 2/9/2021: Customer has been asked to provide additional scope information but not yet supplied it. Project is not yet funded.
BA | 6 | BA-1631 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0068 | Bioinformatics | FPFM, BIOINFORMATICS 124 CODE ROOM USE SEPARATIONS | FPFM - BIOINFORMATICS 124 CODE REQUIRED ROOM USE SEPARATIONS: Mechanical, storage and wood shop uses need separation by 2-hour fire walls. Construction costs unknown. Outside design is required at $30,000. | 2017-11-02 06:48 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | BOAL, JOHN (jboal1) | 18-0089 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 2/9/2021: Project not funded.
AA | 0 | AA-1720 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | LIBRARY LEASE SPACE | Work related to kick off library off campus space lease. | 2020-07-08 07:58 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 21-0002-I | CAUDLE, AMANDA (afelock) | 40000 | 240943.75 | 0 | 2020-08-03 | (2-8-21) Outstanding items: Canopy (working with Richard on lease amendment) and blind quote for office and conference room.
AA | 0 | AA-1726 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | CLASSROOM COVID FURNITURE MOVE FOR SOCIAL DIST | This project is to move and store all excess furniture that will not be used in classrooms this fall due to furniture being spaced for social distancing. This project applies to all academic buildings on campus. | 2020-08-06 08:31 | MCMANNEN, TONYA (tmcmanne) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 21-0018-I | CAUDLE, AMANDA (afelock) | 225317 | 339559 | 172115.94 | 2020-08-31 | (2-8-21) Working with Commercial Works to finalize billing amount in May when all furniture comes back to campus and project closes out.
AA | 1 | AA-1446 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL FIRST FLOOR LOBBY RENOVATION | Plans for renovation of Fretwell first floor (open public space).Contact Shawn Long for details 7-0075 | 2017-09-07 15:06 | SCHAUBLE, DONIA (dcooke) | LONG, SHAWN (sdlong) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 18-0060D&C | CAUDLE, AMANDA (afelock) | 34000 | 33900 | 33475 | 2018-08-13 | (2-8-21) Meeting to review rendering with CLAS and Donia - week of February 8. Work to be coordinated with Fretwell Cafe project.
SA | 6 | SA-0408 | Project On Hold Design Services | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE SOUTH 3 MODERNIZATION | Cone Center - South 3: Upgrade and modernize South 3 level of Cone Center. Collaborate with Director and Associate Director to establish design options and features. | 2019-01-31 13:53 | MERCK, DONNA (dlmerck) |  | MERCK, DONNA (dlmerck) | CAUDLE, AMANDA (afelock) | 19-0147 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) Placed on hold 7-2-20.
SA | 6 | SA-0450 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION M101 ESPORTS LOUNGE | There is a space identified in the Student Union as a potential opportunity for an Esports Lounge. Need to determine if it is feasible in the space given the needs of the group. Need feasibility information by 1/28 and then will proceed further if ne | 2020-01-16 10:59 | MEEHAN, MORGAN (mmeeha11) |  | DALE, JEREMY (jdale8) | CAUDLE, AMANDA (afelock) | 20-0137 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) Informal budget provided to Morgan Meehan 1-27-20. Pending approval to proceed. Placed on Hold April 27.
BA | 6 | BA-1696 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1007 | Union Deck | UNION DECK STORAGE ROOM | UNION DECK Storage Room, provide large storage room on level 1 underneath of the up ramp where area is fenced off. This modification was rejected in the Expansion project due to schedule but we would like to review requirements and price out impleme | 2018-05-07 09:37 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | CAUDLE, AMANDA (afelock) | 18-0232 | CAUDLE, AMANDA (afelock) | 225000 | 0 | 0 |  | (2-8-21) Placed on hold 1-23-20.
BA | 6 | UA-0039 | Project On Hold Design Services | Informal Projects | 30300 | Alumni Affairs | 0088 | Hauser Alumni Pavilion | HAUSER ALUMNI PAVILION SECURITY DOORS | Project to add garage door type security between the brick columns . Cleo - use 138062. Contact Scott Plunkett at 7-7792 | 2017-11-14 09:27 | PLUNKETT, SCOTT (ssplunke) |  | WIDMAIER, CLEO (cswidmai) | CAUDLE, AMANDA (afelock) | 18-0101 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) Placed on hold 2-17-20.
AA | 1 | AA-1680 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1043A-1057D DIST. ED MOVE FROM 1017 STE. | Colvard - 1031A, 1032A, 1033B, 1033C,1044A, 1045A, 1046A, 1047A, 1048A, 1048B, 1049A, 1050A, 1057, 1057A, 1057B, 1057C, 1057D - Move Distance Educatioin from Colvard Suite 1017 to new location on Colvard 1000 level. Project will require painting and | 2020-01-14 11:00 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0131 | CAUDLE, AMANDA (afelock) | 37000 | 50000 | 12573.8 | 2020-06-15 | (2-8-21) Carpet install 2-15-20. Anticipate move date week of February 22.
AA | 0 | AA-1719 | Approved-Design & Estimate FAM | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | STORRS, ROBINSON & ROWE ARTS QUAD | Quad between Storrs, Robinson, and Rowe - The arts quad project is intended to provide canopied space for outdoor art and architecture teaching. Tented structures will cover areas of the quad and the recessed yard in front of Storrs. Amenities will | 2020-07-01 13:46 | SCHAUBLE, DONIA (dcooke) | MULLER, BROOK (bmuller7) | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 21-0001-I | FRERE, ELIZABETH (efrere) | 50000 | 49720 | 0 | 2020-12-31 | Project scope revised, requested Watson Tate Savory to revise their proposal accordingly and resend. Added renderings and cost estimates to scope. SD/DD phase design to be completed, CD phase will not commence until funding can be identified.
AA | 0 |  | Created | Capital Projects | 15100 | Academic Affairs VC | 0068 | Bioinformatics | BIOINFORMATICS 4TH FLOOR BUILD-OUT | Build-out 4th floor to provide interdisciplinary research space to support UNC Charlotte's need for labs and faculty offices. | 2018-06-04 10:33 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | FRERE, ELIZABETH (efrere) | 10500000 | 9408278.83 | 0 |  | "Consultants Designer - LS3P Lab Planner - RFD CM@R - Balfour Beatty Milestone dates and activities Balfour Beatty selected as CMR, precon contract approved by SCO and sent to Balfour for signature April 30, 2020 Alternates discussed March 16, 2020 CMR submitted SD/DD phase cost estimate on April 8, 2020 SD/DD reconciled cost estimate reviewed on April 16, 2020, within budget and approved to move forward without any revisions Design contract routed for University signatures on April 13, 2020 Project taken off hold, restarted design process after Design contract was executed on 6/11/20. CD Kickoff Meeting completed on July 20, 2020 SCO approved SD/DD phase submittal on May 21, 2020 Issues to be addressed Next CD workshop meeting will be late August 2020 BSL3 valve funding issue still on-going - design and construction to be an informal project, trying to locate funding for total project total +/-$400,000 "
AA | 6 | AA-1414 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD BIOLOGY CAMERA REPLACEMENT | Woodward Biology Camera Replacement | 2017-05-16 13:26 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 18-0010 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) Placed on hold 11-21-17.
AA | 6 | AA-1638 | Project On Hold Design Services | Informal Projects | 15175 | Center City Campus | 0073 | The Dubois Center | CCB 1106 EXPANSION | Explore the possibility of remodeling and expanding 1106 at Center City. Remove wooden side walls and wall between 1106 and the storage areas behind it to make the room larger. | 2019-08-19 13:41 | DUPLESSIS, ANN (aduples1) |  | DUPLESSIS, ANN (aduples1) | CAUDLE, AMANDA (afelock) | 20-0051 | CAUDLE, AMANDA (afelock) | 13000 | 0 | 0 |  | (2-8-21) Routed scope and budget for design 12/4/19. Pending customer approval to proceed. Placed on hold 6-26-20.
AA | 6 | AA-1673 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0004 | Atkins | ATKINS 146, 149 CNT. FOR GRAD.LIFE MOVE FROM CONE | Atkins - 146, 148A, 148B, Suite 149 - Move Center for ¦Graduate Life from Cone 2nd floor to Atkins 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:57 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0125 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 6 | AA-1698 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0080 | PORTAL | PORTAL 129 UPGRADES | Portal - 129 - Upgrades to Active Learning Classroom | 2020-03-16 08:25 | SCHAUBLE, DONIA (dcooke) | TANKERSLEY, RICHARD (rtankers) | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0199-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | SCIENCE BUILDING | The Science Building will provide important undergraduate class laboratory and interdisciplinary research space for UNC Charlotte. Many of UNC Charlottes buildings were constructed before doctoral instruction and, in some cases, before master leveli | 2011-06-02 09:30 | RAJA, JAYARAMAN (jraja) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 90000000 | 96962683.86 | 0 |  | Clark Nexsen - Designer Balfour Beatty - CM @ Risk Jenkins Peer - Feature Wall Design Consultant Milestone Dates and Activities: 11/09/2020: RUP 5 BO received 10/29/2020. 11/10/2020: Data Center BO received 11/10/2020. 02/08/2021: Science Building finish site work ongoing. Millwork continuing install on all levels. Ceiling grid and lighting being installed on all levels. AHU connections ongoing. Hard tile installation ongoing. MEP trimout ongoing at casework. Site stairs, lighting, and hardscaping installation ongoing. 01/12/2021: Signage package bid opening held. 02/12/2021: Feature wall mock-up ready for viewing. Feature wall fabrication begins 02/17; install 04/24. BO requirements draft received from CN 02/05. Issues to be resolved: Project schedule updated 01/26/2021. (-60 days behind schedule) Contract completion date: April 9, 2021. (Schedule update shows 05/03/2021 BO and not acceptable to the University). 01/21/2021 Equipment list and move logistics Customer meeting held. Ongoing assessment with Academic Affairs.
AA | 0 | AA-1540 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0037 | McMillan Greenhouse | GREENHOUSE FOR BIOLOGY FACULTY | Greenhouse for Biology Faculty | 2018-06-29 09:17 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 19-0023 | PATEL, NAVINKUMAR (npatel24) | 228650 | 228650 | 23467.27 | 2020-08-21 | (02.08.21) DD drawings complete. Designer working on changes per additional scope, to provide budget and drawings. CD will not begin until this has been reviewed and approved. Received a construction estimate from Cost Plus. Reviewing drawings and cost estimate and sent revised schedule for Jay Raja to review. Meeting with Customer 02.08.2021 to review alternates. Project informal bid opening 03.02.2021.
AA | 0 | AA-1713 | Approved Scope & Budget FAM | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 4077-4085 FACULTY START UP | Reconfigure former spaces 4077, 4078, 4080, 4081, 4084, and 4085 into 3 spaces needed for Psychology research. This is part of a new faculty start up. | 2020-06-13 13:11 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0249-I | PATEL, NAVINKUMAR (npatel24) | 150000 | 0 | 0 |  | (02.08.21) Layout, finishes and furniture have been approved by the end user. Received pricing from Heartland and sent to Donia. Was requested to get another construction estimate. SCOPE and BUDGET sent for review and approval to AA. Estimated completion date 04.15.2021.
AA | 0 | AA-1730 | Req Scope & Budget Review | Informal Projects | 15100 | Academic Affairs VC | 0004 | Atkins | ATKINS 2ND FLOOR FACULTY EZ VIDEO STUDIOS | Atkins - 2nd Floor - Addition of 2 EZ video studios on the 2nd floor. | 2020-10-14 08:11 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 21-0045-I | PATEL, NAVINKUMAR (npatel24) | 160181 | 0 | 0 |  | (02.08.21) Project has been submitted for SCO review. Has to be complete by end of March. Funding ends at the end of April. DD set reviewed and will be sending to SCO 02.05.2021.
AA | 1 | AA-1705 | In Design | Informal Projects | 15100 | Academic Affairs VC | 0075 | Motorsports Research | MOTORSPORTS VIBRATION PAD | Motorsports research needs to have their existing vibration pad permanently floor mounted. Adam Stall has a specific location in mind and needs to find out if the pad can be mounted in that location. Costs for the work must be identified and approv | 2020-03-30 17:31 | SCHAUBLE, DONIA (dcooke) | STALL, ADAM (astall) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0214-I | PATEL, NAVINKUMAR (npatel24) | 4000 | 0 | 0 |  | (02.08.21) Electrical costs sent to AA for review and approval. Will update schedule of completion when FO provided one.
AA | 0 | AA-1737 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD BREEZEWAY | Update Colvard Breezeway with power and WIFI to support outdoor student tutoring and gathering. While first priority is power and WIFI updated furniture and improvements through adding banners, paint, artwork on various levels of the breezeway are d | 2021-01-26 00:41 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SMITH, RYAN (rsmit341) | 21-0067-I | SMITH, RYAN (rsmit341) | 0 | 0 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultants: TBD * Contractor: TBD * Project Delivery Method: TBD * Tentative Construction Timeline: 02/15/21 - 04/01/21 MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Stakeholder Review to define project scope. --- Project Funding Secured --- Work Orders and PO's Issued --- Project Approvals Received --- Construction Work Started * 60 Day Outlook: Completed by 04/01/21 --- Construction Complete * 90 Day Outlook: Completed by 05/01/21 --- Project Closed Out NOTES / ISSUES / CONCERNS: * Customer has $20,000.00 budget for Electrical, IT, and Site Furniture upgrades. * Customer has tight completion timeline of Mid March.
AA | 0 | AA-1731 | Scope & Budget Requested | Informal Projects | 27100 | Enrollment Management | 0095 | Gage Undergraduate Admissions Center | GAGE ADMISSIONS GEM CART SHELTER | Gage Admissions - Provide scope and budget only for installation of a Gem cart shelter at Gauge Admissions. Shelter should match structure and appearance of shelters across the street at Housing & Residence Life. | 2020-10-14 13:12 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | ROSS, KRISTIE (kaross) | SMITH, RYAN (rsmit341) | 21-0047-I | SMITH, RYAN (rsmit341) | 0 | 0 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultant: TBD * Contractors: TBD * Project Delivery Method: Informal Project Bid * Tentative Project Delivery Timeline: TBD MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Present design and construction costs and achieve customer decision to move forward on Pre-Fab Structure Option. * 60 Day Outlook: Completed by 04/01/21 --- Secure Project Funding --- Issue PO's to Purchase Prefab Structure & Construct * 90 Day Outlook: 05/01/21 --- Receive Pre-Fab Structure 30 - 90 Day Production Time --- Onsite Estimated Construction Duration: 2 Weeks NOTES / ISSUES / CONCERNS: * Currently determining if customer has adequate funding to move forward with this project. * Project budget determined to be less then $30,000.00.
AA | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | INFORMATION TECHNOLOGY INFRASTRUCTURE UPGRADES | IT Infrastructure Upgrades in Rowe, Storrs and Reese | 2018-10-18 11:02 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 3800050.24 | 3020570.04 | 0 |  | Consultants / Contractors: Consultants: Optima Engineering Contractors: Shiel Sexton CM@R Milestones: * Project construction is behind scheduled 198 day delivery schedule. * Final SCO Inspection anticipated for last week of Feb. Notes / Issues / Concerns: * COVID cases hindering manpower needed for cabling installation.
AA | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0020 | McEniry | MCENIRY HVAC (R&R) | This project will address needed HVAC repairs and upgrades in McEniry. | 2018-09-28 08:28 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 500518.85 | 1236313.66 | 0 |  | Consultants / Contractors: * Consultant: McCracken & Lopez & Jenkins Peer * Contractor: Armstrong Mechanical Milestones: * Work is no complete. Designer Punch List: Dan Van Dike - Jenkins Peer has been completed by contractor.
AA | 1 | BA-1923 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0097 | Science Building | SCIENCE FF&E | SCIENCE FF&E: Furniture for the new Science building & Data Center. Capital funded project. Project Dollar Maximum; $1,500,000. Assign to Alicia Wells. | 2020-02-19 15:35 | FAKE, WILLIAM (wmfake) |  | CEALLAIGH, SHERRYL (sceallai) | WELLS, ALICIA (awells43) | 20-0176 | WELLS, ALICIA (awells43) | 1500000 | 1500000 | 23358.5 | 2021-08-31 | (2/8/21) RUP/Data additional furniture to install mid February. Science furniture revisions sent to Donia last week. Additional changes were requested and customer meetings to be set up.
AA | 0 | AA-1736 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0004 | Atkins | ATKINS 2ND & 3RD FL CARPET & PAINT | Provide carpet and paint on portions of the 2nd floor and the 3rd floor to update areas where new furniture will be provided to create socially distanced student study space. | 2021-01-21 12:23 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 21-0066-I | WELLS, ALICIA (awells43) | 408616 | 408616 | 0 | 2021-04-30 | (2/8/21) Painting started 2/8 and carpet is on order.
AA | 0 | AA-1734 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0004 | Atkins | ATKINS LIBRARY FURNITURE (SOC. DIST.) | Furniture for socially distanced student study space to be installed on floors 2,3,5,6,and 7. | 2020-11-10 14:09 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 21-0054-I | WELLS, ALICIA (awells43) | 942000 | 942000 | 0 | 2021-04-30 | (2/8/21) Final furniture quotes came in above project cost and are being revised. Power circuits are being confirmed by FO on 2/11 for additional floor power requested. The engineering group is working with me as well on this request.
AA | 1 | AA-1686 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY FF&E | McEniry - Furniture Project - Full scope still needs to be determined.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 11:23 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0135 | WELLS, ALICIA (awells43) | 13000 | 13000 | 12419.99 | 2021-12-31 | (2/8/21) Wtg on final customer feedback to revise layouts. Furniture meetings with faculty to be set up in regards to specific lab needs. Furniture to be ordered end of March.
IF | 6 | BA-1929 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | MEMORIAL STRUCTURAL SCULPTURE DESIGN | MEMORIAL STRUCTURAL SCULPTURE DESIGN: Structural design for steel memorial sculpture with foundation in University Gardens to contain large stones with student etched memorials. Pro Bono (no cost) design by SKA Consulting Engineers. Fund: 336487. | 2020-03-02 09:05 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0182 | FAKE, WILLIAM (wmfake) | 1 | 1 | 0 | 2020-10-30 | (11-11-2020) No new updates - Project awaiting Customer approval actions and funding source. (10-27-2020) - Two Construction Cost Estimates: (#1) $21,600 steel frame only (SteelFab). Installation $29,800 (MV Momentum). Contingency $2,600. Net total $55,000. (#2) $21,600 steel frame only (SteelFab). Installation $18,700 (Heartland Contracting). Contingency $2,000. Net total $42,300. Well over $17,000 anticipated by Customer Marek Ranis - Marek acknowledged receipt of estimates on Monday,10-26-2020. (09-29-2020) - Design by SKA (Garrett Overcash) Pro Bono: Design completed and approved by Customer late Tuesday 09-15-2020. Final documents submitted to SCO week of 09-21-2020 using SCO - ID# 20-21851-01. SCO Approved documents on 09-29-2020. (03-03-2020) Original construction start anticipated mid-October with completion anticipated late November - Needs a project request entry by Student Affairs for Construction phase.
BA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0045 | Fretwell | FRETWELL CAFE' RENOVATION | Renovate Fretwell Cafe' | 2019-11-20 05:38 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | CAUDLE, AMANDA (afelock) | 722500 | 756599.5 | 0 |  | (2-8-21) Consultants: Watson Tate Savory - designer Milestone dates and activities: Kickoff meeting held June 16. SD/DD submitted to SCO September 30. CD kickoff meeting October 27. Submit CD's to SCO 2/2/21. Anticipate approval to bid by 2/19/21.
BA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0069 | Popp Martin Student Union | POPP MARTIN STUDENT UNION | renovate Einsteins, New Venue & Crown Commons | 2019-11-20 05:53 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | CAUDLE, AMANDA (afelock) | 9638114.5 | 9111644 | 0 |  | (2-8-21) Crown Commons is on hold Consultants: Moseley Architects - designer Shiel Sexton - CM@R McCracken & Lopez - commissioning agent Shake Smart concept CD's complete and submitted to SCO February 8, 2021. Anticipate bid day March 19, 2021.
BA | 0 | BA-1968 | Construction | Informal Projects | 10400 | Business Services AVC | 0082 | South Village Crossing | SVC SUN SAILS | SVC Sun Sails, provide sun sails over portions of the terrace area. | 2020-07-08 07:58 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0003-I | CAUDLE, AMANDA (afelock) | 60000 | 60000 | 28643.28 | 2020-08-11 | (2-8-21) Structural engineering reviewing shop drawings 12-15-20. Anticipate frame installation by end of January. We will hold on the fabric installation until spring.
BA | 0 | BA-1971 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0069 | Popp Martin Student Union | STUDENT UNION 137-138 STORAGE ROOM MODIFICATIONS | SU Storage Room Modifications, modify 137 and 138 to remove demizing wall. Relocate some metal shelving. Need large item storage and pallet drop area. Provide rolling plastic shelving typical of our dry storage areas to provide more storage within | 2020-07-13 13:57 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0012-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) Layouts and budget pricing provided to Drew Averitt on 9-21-20. Pending his approval to proceed.
BA | 0 | BA-1972 | Construction | Informal Projects | 13902 | Engineering Services | 0092 | Facilities Ops and Parking (FOPS) | FOPS OFFICE MODIFICATIONS | Coordination of moves to relocate Engineering to FOPs Building. | 2020-07-14 09:12 | FAKE, WILLIAM (wmfake) | JANUS III, DONALD (drjanus) | WITHERSPOON, MELANIE (mewither) | CAUDLE, AMANDA (afelock) | 21-0013-I | CAUDLE, AMANDA (afelock) | 15000 | 15000 | 9500 | 2020-11-11 | (2-8-21) CD's sent to SCO for review 12-17-20. Pricing options sent to business office for funding approval to proceed 1-12-21.
BA | 6 | BA-1930 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0001 | Kennedy | KENNEDY CONTEMPLATIVE SPACE RENOVATION | KENNEDY CONTEMPLATIVE SPACE RENOVATION, DESIGN: Chancellor 2020 Central Funds: $50,000. Design Only. Project Dollar Maximum: $30,800.00. | 2020-03-04 07:20 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0184 | FRERE, ELIZABETH (efrere) | 30800 | 30800 | 30800 | 2020-04-15 | (05-08-2020) Watson Tate Savory total design contract reduced to $29,920. Partial invoice for $23,222.10 dated 04-23-2020 was approved for payment on 04-27-2020.
BA | 0 | BA-1975 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0072 | EPIC Building | FPFM, EPIC CORRIDORS VINYL TILE REPLACE | FPFM, EPIC CORRIDORS VINYL TILE REPLACEMENT: BES Project Request: EPIC Building corridors on multiple floors have significantly damaged vinyl composition tile (VCT) Very thin style tile - Old and no longer available. Need review and estimate. | 2020-08-17 14:47 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | CAUDLE, AMANDA (afelock) | 21-0022-I | CAUDLE, AMANDA (afelock) | 10500 | 10500 | 0 | 2020-09-08 | (2-8-21) Work scheduled for January 27-29.
BA | 0 | BA-1992 | Scope & Budget Requested | Informal Projects | 14500 | Grounds | 3016 | Facilities Annex Ten (Grounds) | FACILITIES ANNEX TEN GROUNDS DEPT ADD OFFICE | Building 3016, annex 10 - create a new office space by swapping the exterior window and door, adding an interior wall, door, and sliding window (like in BES office) at the back, side entrance of the grounds triple wide.We are also relocating the colo | 2020-10-14 08:11 | CANAPINO, JON (jcanapin) | CANAPINO, JON (jcanapin) | WITHERSPOON, MELANIE (mewither) | CAUDLE, AMANDA (afelock) | 21-0046-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) Provided scope & budget to Joey on 11-20-20. Pending funding approval to proceed.
BA | 0 | BA-1994 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0039 | Auxiliary Services Building | ASB HALLWAY & RESTROOM IMPROVEMENTS | ASB restroom improvements, mens room to be reviewed and cleaned up, new paint, flooring, partitions, fixtures?, new touchless controls. Womens room new touchless controls. ADA Restoom new touchless controls. Carpet deep clean & remove carpet bubbl | 2020-10-22 14:59 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0049-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) Working with Renovation Shop to price work. Anticipate scope & budget by February 12.
SA | 6 | SA-0462 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC SALONS AND PREFUNCTION CARPET | Project is to gather estimates and designs on replacing the carpet inside and outside of the SAC Salons. | 2020-03-16 08:40 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | HILL, CAROLINE (cmhill2) | 20-0202-I | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 10/26/2020 - Reached out to Customer and project funding is under evaluation. Project will still need to be on hold for now.
AA | 6 | AA-1531 | Project On Hold Design Services | Informal Projects | 24400 | Research & Economic Dev. VC | 0080 | PORTAL | PORTAL 232 AND 242 ENHANCEMENTS | PORTAL 322: 1) add color, texture, or paneling to the walls 2) move the UNCC sign in the space to different location 3) upgrade the photos and picture frames in the roomPORTAL 242: 1) add wall covering to wall outside of 242 and hang pictures like th | 2018-05-22 10:42 | MATEEN, ALI (amateen) | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) | HILL, CAROLINE (cmhill2) | 19-0001 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 2/9/2021 - Compiling updated pricing for Customers.
AA | 6 | AA-1610 | Project On Hold Design Services | Informal Projects | 19400 | College of Business | 0035 | Friday | FRIDAY 391 RENOVATION | We are looking at splitting the room in two similar to 388/393.It may not be an exact half split though.We want one side to be a small PhD classroom and the other side to be a student bullpen area similar to 388/393.Classroom half needs to seat 20 if | 2019-04-10 13:24 | CARMICHAEL, TIMOTHY (twcarmic) | CARMICHAEL, TIMOTHY (twcarmic) | TWEED, DANA (dtweed1) | HILL, CAROLINE (cmhill2) | 19-0204 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 10/26/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1616 | Project On Hold Design Services | Informal Projects | 19400 | College of Business | 0035 | Friday | FRIDAY 242 CONFERENCE ROOM | I need a cost estimate to convert Friday 242 into a conference room. Move 1 display to the end wall. Remove the remaining 5 displays (Belk College Technology Team will take the 5 that get removed). Patch and paint walls. Core drill to connect lapto | 2019-04-22 13:35 | CARMICHAEL, TIMOTHY (twcarmic) | CARMICHAEL, TIMOTHY (twcarmic) | SANCHEZ, STEPHANIE (ssanch12) | HILL, CAROLINE (cmhill2) | 19-0211 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 10/26/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1690 | Project On Hold Design Services | Informal Projects | 24200 | OneIT-CIO | 0001 | Kennedy | KENNEDY 320 RECONFIGURATION | We would like to discuss options for how Kennedy 320 can adjust for growth, specifically using 2 - 4 areas of existing space. Sandra Soriano (78987) is the contact for this request. | 2020-02-07 14:44 | VITALLO, JUDY (jvitallo) |  | VITALLO, JUDY (jvitallo) | HILL, CAROLINE (cmhill2) | 20-0170 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 10/26/2020 - Project on hold per customer request.
BA | 2 | BA-1919 | Scope & Budget Requested | Informal Projects | 10500 | Auxiliary Operations | 0082 | South Village Crossing | SVC TERRACE FURNITURE | SVC Terrace Furniture, propose, review and provide exterior furniture and accessories on the upper floor terrace area. Replace and or relocate existing furniture as supports the overall plan fo rthe terrace. | 2020-02-10 11:20 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 20-0167 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) Working with vendors to get sample pieces in for trial period.
BA | 2 | BA-1927 | Construction | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR DOOR REPLACEMENT | PROSPECTOR Door Replacement, replace the (5) full glass door locations with standard doors. There are (3) exterior pairs of doors (tied into Open Options), (1) interior vestibule pair of doors and (1) interior pair of doors (needs to lock). Pending | 2020-02-27 11:42 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 20-0190 | CAUDLE, AMANDA (afelock) | 12000 | 12000 | 0 | 2020-11-23 | (2-8-21) In design with C Design. Anticipate SCO review early March with bidding around mid-March.
BA | 6 | BA-1586 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT: Congestion Task Force assignment for design only: Central Funds - Project Dollar Maximum: $13,000. | 2017-05-17 07:56 | FAKE, WILLIAM (wmfake) |  | PAQUETTE, NOELLA (njpaquet) | KELLY, SHAWN (skelly64) | 17-0225 | KELLY, SHAWN (skelly64) | 13000 | 13000 | 11731.7 | 2017-05-29 | PROJECT NOTES UPDATED: * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultant: Dewberry * Contractors: TBD * Project Delivery Method: TBD * Tentative Construction Timeline: TBD MILESTONES: * 30 Day Outlook: --- On Hold till construction funding can be secured and further direction provided. NOTES / ISSUES / CONCERNS: * CD's 100% Complete & Ready for Construction * Project was initially undertaken as a Chancellor Dubois Funded Campus Circulation Improvement.
BA | 6 | BA-1762 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1056 | Lot 7 | LOT 7 & 7A RECONFIGURATION | LOT 7 & 7A Reconfiguration, redesign Lots 7 and 7A to optimize usage and traffic flow (Design only at this point in time). | 2019-01-07 10:46 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 19-0106 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | PROJECT NOTES UPDATED: * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultant: TBD * Contractors: TBD * Project Delivery Method: TBD * Tentative Construction Timeline: TBD MILESTONES: * 30 Day Outlook: --- On Hold till Parking Services provides funding and direction for project. NOTES / ISSUES / CONCERNS: * Project scope will be determined by long term Cone Deck decisions.
BA | 2 | C-0041 | Construction | Informal Projects | 10250 | Legal Affairs | 0048 | Cato Hall | CATO 1ST FL TITLE IX & INTERNAL AUDIT | Title IX & Internal Audit Cato Hall first floor renovations. | 2020-03-30 17:31 | JOHNSON, MELANIE (mmjohns1) |  | SHUE, BRENDA (bshue3) | CAUDLE, AMANDA (afelock) | 20-0215-I | CAUDLE, AMANDA (afelock) | 210000 | 210000 | 178668.06 | 2020-05-18 | (2-8-21) Title IX move from Cone to Cato 10-28-20. Internal Audit move date anticipated around March 10 (Jennifer requested to wait for her furniture to arrive before she moves her team).
BA | 2 | BA-1945 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | DINING SEAT CUSHIONS | SEAT CUSHIONS, various locations, need to provide seat cushions for all hard wood seats. Includes Prospector, Student Union, SVC. Project will have to be bid given the number of seats. | 2020-04-10 12:56 | AVERITT, DREW (daveritt) | HOLMES, ROBERT (rholme16) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 20-0222-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) Working on request for pricing for material management bidding. Drew and I captured all chair information necessary for bidders. Chair samples delivered 6-29-20 for customer feedback on foam selection and construction.
BA | 0 | BA-1979 | Approved Scope & Budget FAM | Informal Projects | 13900 | Facilities Management AVC | 0055 | Facilities Management & Police & Public Safety | FM 228 BUSINESS OPS RENOVATION | Facilities Management Bldg - Suite 228 Add a glass storefront to the office 228A. Also move Admin Group from FOPs to suit 228. (it is also possible we will request one of the cubes be removed/relocated.)Warehouse - Need conceptual drawing for addin | 2020-09-16 09:17 | CEALLAIGH, SHERRYL (sceallai) |  | WITHERSPOON, MELANIE (mewither) | CAUDLE, AMANDA (afelock) | 21-0029-I | HILL, CAROLINE (cmhill2) | 87000 | 0 | 0 |  | 2/9/2021 Updated from Amanda on this project. I have connected with Sherry and will continue moving project forward.
BA | 0 | BA-2001 | Approved Scope & Budget PAM | Informal Projects | 13950 | FM Maintenance Operations | 0001 | Kennedy | KENNEDY FIRST FLOOR CARPET REPLACEMENT | Kennedy First Floor - Room 101Temporarily jack/lift all work stationsRemove damaged carpet tiles and wet gluePrep concrete floor and install new carpet squares | 2021-01-07 15:01 | SNODGRASS, NATHANIEL (nsnodgra) | TAYLOR, PAUL (ptaylo18) | WITHERSPOON, MELANIE (mewither) | HILL, CAROLINE (cmhill2) | 21-0060-I | HILL, CAROLINE (cmhill2) | 70500 | 0 | 0 |  | 2/9/2021 - Scope & Budget entered into Archibus. Waiting for the PAM and FAM to approve.
BA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0097 | Science Building | SCIENCE CAFE' | Auntie Ann's Cafe in the new science bldg | 2019-11-20 07:45 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 1377225 | 1179204 | 0 |  | Consultants: BUILT - Chartwells Consultants for SD Clark Nexsen - Designer for DD, CD, CA Milestone Dates and Activities: 02/08/2021 CD's complete 02/05. Routing for University review and comment. Advertise bids 03/04; Bid opening 04/06. Construction to begin May 2021 after completion of Science Building construction. 10/20/2020: Final equipment specs reviewed and approved by Aux. Services and Chartwells. 01/26/2021 Additional revised equipment specs received, pushing CD completion from 01/28 to 02/05.
BA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 1007 | Union Deck | UNION DECK ELEVATOR | Replace elevator | 2020-06-15 14:38 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | NEILSON, JOHN (jneilson) | 0 | 706124 | 0 |  | Meeting with PaTS occurred on 06/18/20 to discuss budget and scope. Design RFP posted to university website and GA on 6/18/20 Proposals were received on 7/10/20, and shortlisting occurred on 7/20/20. Designer interviews occurred on 8/5/20, and WHN Architects, PA was selected. Design fee proposal received 9-1-20, contract issued on 9-9-20, and received back from designer on 9-10-20. Contract was routed to Beth Hardin on 9-14-20. On site meeting with design team on 9-24-20 to begin investigation. SD/DD production is on hold pending decision on path forward. PaTs and others visited a modular elevator installation and manufacturing facility on 12/17/20. A meeting is scheduled for 1/6/21 to discuss. Design production is appox. 3 weeks behind schedule. 1-28-21 - PaTs was impressed with the modular elevator concept, and wants to pursue it along with modernizing the existing hydraulic machine. They have been provided add'l information regarding both options and I am awaiting add'l cost information to determine if both can be provided under the current budget, which appears to be unlikely.
IF | 0 | BA-1966 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0536 | Hickory | HICKORY INVERTER - EGRESS LIGHTING - 2 | HICKORY INVERTER - EGRESS LIGHTING - 2: Phase 2 of the Hickory Invertor for Egress Lighting. Scheduled to complete early FY-2021. Project Dollar Maximum: $7,000. Funding Source: 336487 (Design Fees). Assign to Amanda Caudle. | 2020-06-15 12:02 | FAKE, WILLIAM (wmfake) |  | PAQUETTE, NOELLA (njpaquet) | FAKE, WILLIAM (wmfake) | 20-0250-I | CAUDLE, AMANDA (afelock) | 7000 | 7000 | 0 | 2020-06-15 | (2-8-21) Additional funding requested to compete the project 2-5-21.
IF | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | REGIONAL STORM WATER IMPROVEMENTS MASTER PLAN | Authorization is $850,000 - Capital budget is $750,000. Storm Water Volume Control r-58. #2 priority project in Storm Water Master plan. Required to bring us into compliance with Clean Water Act.The restoration of Toby Creek is proposed as a partners | 2013-12-16 16:34 | FESSLER, JOHN (jafessle) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | FRANZ, PETER (pfranz) | 750000 | 402139.45 | 0 |  | University is currently reviewing in Bluebeam, University. Resubmitting existing SCMs that are currently receiving partial or no stormwater credits to the City, Surface is analyzing existing SCMs on campus that were never submitted to the City (UREC, FOPS) or receiving partial credit (EPIC, Lot 27, Phase XII, Phase XIII, South Village Deck). Additional cost proposal from Surface (consultant is Wildlands) to be submitted as soon as they collect all the needed documentation for the above SCMs - anticipated cost +/- $60,000. After our review of the draft report it was decided that taking more time to work with Surface to help us find consensus as to what we want from the final report and provide clarifications that were moving targets when the scope of the designer's work was originally determined. Clarification of FM team roles and responsibilities - Peter will be finalizing the master plan by compiling comments and getting final draft.
IF | 0 | AA-1733 | Scope & Budget Requested | Informal Projects | 27700 | Disability Services | 8001 | Main Campus East Grounds | STAIR CONTRAST STRIPING | Request scope and budget of identified locations that need high contrast stripes on stairs, as part of ADA and campus compliance.Request Caroline Hill as project manager--already discussed with Lisa Lanier, AD. | 2020-10-22 14:59 | MONTIE, KATHRYN (ksmontie) | LANIER, LISA (llanier) | MONTIE, KATHRYN (ksmontie) | HILL, CAROLINE (cmhill2) | 21-0051-I | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 2/9/2021 - Scope & Budget sent to Customer in December. Dropped samples off with Katie yesterday. Waiting to hear if funding is available for this project.
IF | 0 | BA-1950 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | PPS & ITS DUCK BANK AT EVI | FPFM, PPS & ITS DUCK BANK AT EVI: Create duct bank connection on campus for AT&T, CenturyLink on John Kirk. Determine route on Martin Village Connector to terminate at existing MH 94 on Martin Village Road. Coordinate with EVI and Lot 5A Projects. | 2020-04-20 16:30 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | WITHERSPOON, MELANIE (mewither) | KELLY, SHAWN (skelly64) | 20-0228-I | KELLY, SHAWN (skelly64) | 300000 | 5000 | 0 | 2020-10-16 | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultants: CMTA / McCraken & Lopez * Contractor: TBD * Project Delivery Method: TBD * Tentative Construction Timeline: TBD MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Present final design to project stakeholders. --- Discuss project next steps recommend project cancellation or hold due to EVI decision to be put on hold indefinitely. NOTES / ISSUES / CONCERNS: * Funding authorization is needed to move the project past initial design. * Duct-bank Project will be dependent of whether EVI Road Improvement moves forward.
IF | 0 | BA-1965 | Construction | Informal Projects | 10400 | Business Services AVC | 0029 | Housing and Residence Life | HRL CATERING SCREEN WALL | HRL, Catering Screen Wall, provide fence or green wall in and around the Catering cart/van parking area as students are cutting through area with near misses and some students jumping off the loading dock presenting lots of safety issues. Please ass | 2020-06-10 07:56 | HOLMES, ROBERT (rholme16) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 20-0247-I | KELLY, SHAWN (skelly64) | 10000 | 10000 | 0 | 2021-02-26 | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultants: None * Contractor: UNCC Grounds Dept. * Project Delivery Method: PDC In-House Project Delivery * Tentative Construction Timeline: 2/15/21 - 4/15/21 MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Grounds Fabricate Metal Trellis Structures --- Grounds Installs Trellis Structures * 60 Day Outlook: Completed by 04/01/21 --- Grounds Installs Landscape Plantings * 90 Day Outlook: Completed by 05/01/21 --- Project Closeout Completed NOTES / ISSUES / CONCERNS: * Currently awaiting purchase of material for trellis fabrication.
IF | 6 | SA-0397 | Project On Hold Design Services | Informal Projects | 29700 | Housing and Residence Life | 0503 | Scott Hall | SCOTT HALL TO SOVI BRIDGE | request for FM Projects to evaluate and design a new (replacement) path from Scott Hall Bridge to SOVI (Dining Hall) lower level. | 2018-10-30 15:00 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | KELLY, SHAWN (skelly64) | 19-0072 | KELLY, SHAWN (skelly64) | 10000 | 10000 | 3067.2 | 2019-09-20 | PROJECT NOTES UPDATED: * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultant: McAdams * Contractors: TBD * Project Delivery Method: TBD * Tentative Construction Timeline: TBD MILESTONES: * 30 Day Outlook: --- Project on hold till receive further direction and funding from HRL & FM AVC. NOTES / ISSUES / CONCERNS: * Project original proposed to be split funded between FM & HRL prior to Pandemic. * Survey and SD Design currently completed.
IF | 6 | BA-1854 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0046 | Barnhardt Student Activity Center | FPFM, SAC FIRE & SMOKE PURGE SYSTEMS INVESTIGATION | FPFM, SAC FIRE & SMOKE PURGE SYSTEMS INVESTIGATION: Investigate smoke management of SAC during fire alarm activation. AHU devices do not shut down; smoke purge system serving the food court does not function. Assign to Don Janus. | 2019-07-23 08:33 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | KELLY, SHAWN (skelly64) | 20-0034 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | PROJECT NOTES UPDATED: * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultant: TBD * Contractors: TBD * Project Delivery Method: TBD * Tentative Construction Timeline: TBD MILESTONES: * 30 Day Outlook: --- On Hold Pending Review and direction from FM Engineering Dept NOTES / ISSUES / CONCERNS: * None
IF | 0 | BA-1982 | Req Design Estimate Review | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, LIBRARY LANE VEHICULAR GATE | FPFM, LIBRARY LANE VEHICULAR GATE: Install security gate and infrastructure to control vehicle traffic on to core of campus from Library Lane. Project Dollar Maximum: $150,000.00. Assigned to: Shawn Kelly. | 2020-10-07 11:13 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0034-I | KELLY, SHAWN (skelly64) | 150000 | 220000 | 0 | 2021-05-28 | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultants: None * Contractor: Draw Enterprises & UNCC Grounds Dept. * Project Delivery Method: PDC In-House Project Delivery * Tentative Construction Timeline: 04/01/21 - 06/01/21 MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Secure Project Funding from FBO. --- Issue All PO for Design & Gate Equipment. --- Review and Complete Design * 60 Day Outlook: Completed by 04/01/21 --- Complete Design --- Select Contractors --- Begin Work * 90 Day Outlook: Completed by 05/01/21 --- Work Underway NOTES / ISSUES / CONCERNS: * Currently awaiting funding approval from FBO.
IF | 0 | BA-1983 | Approved Scope & Budget FAM | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, STORRS SERVICE LANE VEHICULAR GATE | FPFM, STORRS SERVICE LANE VEHICULAR GATE: Install security gate and infrastructure to control vehicle traffic on to the core of campus from Storrs Lane. Project Dollar Maximum: $150,000.00. Assign to: Shawn Kelly. | 2020-10-07 13:36 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0035-I | KELLY, SHAWN (skelly64) | 150000 | 0 | 0 |  | PROJECT NOTES UPDATED: * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultants: None * Contractor: Draw Enterprises & UNCC Grounds Dept. * Project Delivery Method: PDC In-House Project Delivery * Tentative Construction Timeline: 04/01/21 - 06/01/21 MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Secure Project Funding from FBO. --- Issue All PO for Design & Gate Equipment. --- Review and Complete Design * 60 Day Outlook: Completed by 04/01/21 --- Complete Design --- Select Contractors --- Begin Work * 90 Day Outlook: Completed by 05/01/21 --- Work Underway NOTES / ISSUES / CONCERNS: * Currently awaiting funding approval from FBO.
IF | 0 | BA-1984 | Approved Scope & Budget FAM | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, MARTIN HALL VILLAGE SITE CLEAN UP | FPFM, MARTIN HALL VILLAGE SITE CLEAN UP: Remove construction debris, fencing, grade, and re-landscape for visual improvement. Project Dollar Maximum: $50,000.00. A completed estimate is yet to be developed. Assign to: Shawn Kelly. | 2020-10-07 14:43 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0036-I | KELLY, SHAWN (skelly64) | 50000 | 0 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultants: None * Contractor: Draw Enterprises & UNCC Grounds Dept. * Project Delivery Method: PDC In-House Project Delivery * Tentative Construction Timeline: 03/01/21 - 05/01/21 MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Receive and review all funding needs for material and labor for Grounds Department. --- Secure Project Funding from FBO. --- Issue All PO's and Work Requests. --- Begin construction of landscape improvement. * 60 Day Outlook: Completed by 04/01/21 --- Work underway * 90 Day Outlook: Completed by 05/01/21 --- Complete Work NOTES / ISSUES / CONCERNS: * Current scope of work consists of grading and haul-off, erosion control measure installation, site seeding, sodding, chain-link fence removal, & site reforestation to natural state.
IF | 0 | BA-1985 | In Design | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, HOTEL FILL SITE IMPROVE LANDSCAPE | FPFM, HOTEL FILL SITE IMPROVE LANDSCAPE: Provide a 3 Phased approach to cleaning up perimeter of fill site and landscape. Project Dollar Maximum: $295,000.00. A completed estimate is yet to be developed. Assign to: Shawn Kelly. | 2020-10-07 15:16 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0037-I | KELLY, SHAWN (skelly64) | 295000 | 0 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultants: None * Contractor: Draw Enterprises & UNCC Grounds Dept. * Project Delivery Method: PDC In-House Project Delivery * Tentative Construction Timeline: 03/01/21 - 05/01/21 MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Receive and review all funding needs for material and labor for Grounds Department. --- Secure Project Funding from FBO. --- Issue All PO's and Work Requests. --- Begin construction of landscape improvement. * 60 Day Outlook: Completed by 04/01/21 --- Work underway * 90 Day Outlook: Completed by 05/01/21 --- Complete Work NOTES / ISSUES / CONCERNS: * Current scope of work consists of concrete walk improvement, split rail fence & gate install, grading, sod, landscape planting, and site signage.
IF | 0 | BA-1995 | Scope & Budget Requested | Informal Projects | 13800 | Environmental Health & Safety | 0022 | Solvent Storage | SOLVENT STORAGE BLDG VENTILATION | EHS would like get a quote to have an intrinsically -safe/explosion proof exhaust fan and hood installed at ventilation slats within the solvent storage building. The hood height should be about 5 feet to allow a 55-gallon drum to be stored beneath. | 2020-10-22 14:59 | FISENNE, STEPHEN (sfisenn1) | FISENNE, STEPHEN (sfisenn1) | SANTOSCOY, IRENE (isantosc) | KELLY, SHAWN (skelly64) | 21-0050-I | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultants: TBD * Contractor: TBD * Project Delivery Method: TBD * Tentative Construction Timeline: TBD MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Review project scope with EHS Stakeholders to find alternate location for process. --- Discuss next steps with FM PDC, Engineering, & Operations --- Develop Project Delivery Timeline & Expectations NOTES / ISSUES / CONCERNS: * Customer would like to install ventilation system in hazardous waste building located between McEniry and Greenhouse. * Ventilation would put toxic fumes in the air a low level. Further investigation suggests we would need to put 40 to 50 foot tall stacks on the building in order to appropriately vent these fumes. * Stacks of this nature will not fit on this building due to its location.
IF | 1 | BA-1938 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | CRI BUS PULL OFF DESIGN | CRI BUS PULL OFF DESIGN: Assign to Shawn Kelly. Project Dollar Maximum: $25,000. | 2020-03-16 15:35 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0210-I | KELLY, SHAWN (skelly64) | 25000 | 21305.55 | 20872.95 | 2020-06-12 | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultants: Dewberry * Contractor: TBD * Project Delivery Method: Informal Project Bid * Tentative Construction Timeline: 4/01/20 - 6/01/20 MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- DD Design Reviewed with Project Stakeholders --- CD's and specifications for bid completed and construction funding secured. * 60 Day Outlook: Completed by 04/01/21 --- SCO Approval Received --- Informal Bid Process Started --- Contractor Awarded Assuming Informal Bid Process --- Construction Started * 90 Day Outlook: Completed by 05/01/21 --- Work Underway NOTES / ISSUES / CONCERNS: * Constructing bus pull off as desired without addressing costly reallocation of existing shallow utilities and keeping project within the budget allocated.
IF | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | RECLAIMED WATER | The University has developed a proposed partnership with Charlotte Water (City of Charlotte) to bring reclaimed water to campus from the Mallard Creek waste water plant. This water will replace potable water currently used in chillers and boilers on | 2016-12-15 07:53 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 2100000 | 1965355.27 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultant: AECOM * Contractors: TBD * Project Delivery Method: Single Prime * Tentative Construction Duration: 06/29/21 - 10/30/22 MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- 60% Construction Documentation Completion --- 90% Construction Documentation submitted to SCO 02/08/21 --- 90% Construction Documentation Completion (Out for Internal Review 02/08/21) * 60 Day Outlook: Completed by 04/01/21 --- Tentative Obtain SCO & Internal CD Approval * 90 Day Outlook: SCO Approval by 05/01/21 --- Advertise for Bid for Construction --- Select Contractor for Construction NOTES / ISSUES / CONCERNS: * Charlotte Water Scheduled to Complete on Campus Portion of Reclaimed Waterline by 05/2022.
IF | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0055 | Facilities Management & Police & Public Safety | MODIFICATIONS TO JW CLAY & ROBERT D SNYDER RD | improvement to the JW Clay and Robert Snyder Roads | 2020-08-10 11:41 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | KUGLER, BRIAN (bhkugler) | 0 | 956659 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultant: EMH&T * Contractors: TBD * Project Delivery Method: (Single Prime) * Tentative Construction Duration: 04/05/20 - 07/31/21 MILESTONES: *30 Day Outlook: To Be Complete By 03/01/21 --- Redesign --- Submit to SCO --- Internal Review --- Independent Cost Estimate --- Advertise for Bids (Posted February 8th.) --- Review Bids --- Select & Award Contractor * 60 Day Outlook: To Be Complete By 04/01/21 --- Execute Contracts * 90 Day Outlook: To Be Complete 05/01/21 --- Tentative Start Day for Construction 04/5/21 --- Construction Underway NOTES / ISSUES / CONCERNS: * Upon receiving bids project was identified as 50% over budget and is currently in the redesign process to bring the project within budget for construction.
IF | 0 | BA-1989 | Approved Scope & Budget FAM | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, HOTEL - NO COST UPDATES | FPFM, HOTEL - NO COST UPDATES: Project Request: Provide updates on Hotel Construction. Brian Kugler serves as FM Liaison for Hotel Construction Project. Assign to Brian Kugler. | 2020-10-08 15:28 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0042-I | KUGLER, BRIAN (bhkugler) | 0.01 | 0 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultants: Cooper Carry * Contractors: Choate * Project Delivery Method: CM@Risk * Tentative Construction Duration: 03/05/19 - 02/26/21 MILESTONES: * 30 Day Outlook: To Be Completed 03/01/21 --- Final Exterior & Interior Finishes --- Awning connecting to light rail pedestrian bridge * 60 Day Outlook: To Be Completed by 04/01/21 --- Grand Opening scheduled for 03/31/21 NOTES / ISSUES / CONCERNS: * Agreement between foundation and CDOT to connect awning to the light rail stair tower. Architect sending drawings to CDOT who will send contracts to UNCC. Brian will forward to Niles for review and contract approval. * Waiting to here if Choate Construction Crew needs lightrail safety training from CATS or if training can be waived.
IF | 0 | BA-1990 | Approved Scope & Budget FAM | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, MECKLENBURG: TOBY CREEK RESTORE | FPFM, MECKLENBURG COUNTY: TOBY CREEK RESTORATION: NO COST Project Request: Provide updates on Mecklenburg County Toby Creek Restoration. Brian Kugler serves as FM Liaison for the project. Assign to Brian Kugler. | 2020-10-08 15:52 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0043-I | KUGLER, BRIAN (bhkugler) | 0.01 | 0 | 0 |  | PROJECT NOTES UPDATED * 02/08/21 CONSULTANTS / CONTRACTORS * Consultants: Kimley Horn * Contractors: Blythe Development * Project Delivery Method: (CM@Risk) * Tentative Construction Duration: 10/5/20 - 03/29/22 MILESTONES * 30 Day Outlook: 03/01/21 --- Bank Clearing & Construction of Streambank Structures NOTES / ISSUES / CONCERNS: * Recently flooding submerged two excavators. Repairs to previous work underway.
IF | 0 | BA-1991 | Approved Scope & Budget FAM | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, CHARLOTTE: SEWER & RECLAIMED WATER | FPFM, CHARLOTTE WATER: SEWER & RECLAIMED WATER LINE: NO COST Project Request: Provide updates on Charlotte Water Sewer & Reclaimed Water Line construction. Brian Kugler serves as FM Liaison for the project. Assign to Brian Kugler. | 2020-10-08 16:13 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0044-I | KUGLER, BRIAN (bhkugler) | 0.01 | 0 | 0 |  | PROJECT NOTES UPDATED * 02/08/21 CONSULTANTS / CONTRACTORS * Consultants: Stantec * Contractors: R.H. Price * Project Delivery Method: Design Build * Tentative Construction Duration: 01/03/20 - 05/05/22 MILESTONES * 30 Day Outlook: To Be Complete By 03/01/21 --- Aerial crossing of Mallard Creek to be complete. --- Greenways to be closed from 02/02/21 - 03/15/21 NOTES / ISSUES / CONCERNS: * 11/16/20: Recently flooding caused damaged to erosion control measures and small diesel spill. Repairs to erosion control measures and diesel spill mitigation currently underway. * Vertical separation at roadway being reviewed to see if fault is with R.H. Price during Phillips Rd. boring.
SA | 6 | SA-0407 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0077 | Halton-Wagner Tennis Complex | HALTON TENNIS COMPLEX LOWER HALL FLOODING | The lower hallways of the Halton Tennis Complex flood when there is heavy rain. Zone 1 has performed some modifications to the weep holes in the brick which has helped but we are still getting some flooding. The water drains towards the building inst | 2019-01-24 16:57 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | LANIER, LISA (llanier) | 19-0134 | LANIER, LISA (llanier) | 34000 | 0 | 0 |  | 02/08/2020 Water infiltration continues. Further evaluation required; Engaged designers for proposal and Scope & Budget.
IF | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | WEST SUBSTATION | Project adds a second electrical substation to feed electricity from Duke Energy 100 KVA supply on the west side of campus (across W.T. Harris). This is needed to provide redundancy to our electrical source to insure fail safe operation for research | 2013-10-08 10:19 | GILBERT, CHRISTOPHER (cgilbert) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | LANIER, LISA (llanier) | 6500000 | 2539400.2 | 0 |  | "Schedule to complete testing of 45 remaining cable lengths would be three weeks. Remaining contingency is enough to cover the cost of replacing longest length of cable on campus Engineering has met with FO to discuss this project. Majority of testing can be done without interruption of power to buildings (looped system). Circuit K, Seg 1: Outages would occur in Martin, Hawthorne, SHC, Counseling Center, FM/PPS and Annexes Circuit D, Seg 11: Levine Hall and HRL Circuit D, Seg 7: East Decks, Lots 4, 4A, Lot 6, Cato, Storrs, Band Center Circuit K, Seg 2: Martin Hall McKim & Creed Design Amendment #2 reduction of scope and fees routed for University signature to send to SCO."
IF | 0 | AA-1735 | Construction | Informal Projects | 24202 | OneIT-Enterprise Infrastructure | 0004 | Atkins | ATKINS G65 HVAC FOR UPS | Atkins G65 New HVAC for the UPS Room.Please proceed with a project for the quote of $28,000.00 from McKim & Creed. This quote is to identify what would be needed for the replacement of the HVAC units and the electrical issues for the UPS Room. We | 2020-12-14 09:32 | FRANCUS, KATHLEEN (krfrancu) | FRANCUS, KATHLEEN (krfrancu) | VITALLO, JUDY (jvitallo) | SMITH, RYAN (rsmit341) | 21-0059-I | SMITH, RYAN (rsmit341) | 30149 | 30133.55 | 0 | 2021-05-31 | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultant: McKim Creed * Contractors: TBD * Project Delivery Method: Informal Project Bid * Tentative Project Delivery Timeline: TBD MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Issue designer PO and begin design work. * 60 Day Outlook: Completed by 04/01/21 --- 90% Drawings Ready for Review * 90 Day Outlook: Completed by 05/01/21 --- 100% Drawings & Bid Docs Approved for Bid Posting NOTES / ISSUES / CONCERNS: * HVAC work will begin after completion of the Atkins UPS installation.
IF | 0 | BA-1987 | Approved Scope & Budget FAM | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, COMPLETE ROADWAY STATUS ASSESSMENT | FPFM, COMPLETE ROADWAY CONDITION ASSESSMENT: Perform internal roadway condition assessment per NCDOT guidelines. Establish campus roadway repair priorities. Develop a long-term maintenance plan. Project Dollar Maximum: $25,000. Assign to Ryan Smith. | 2020-10-08 13:29 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0039-I | SMITH, RYAN (rsmit341) | 25000 | 0 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultant: Internal UNCC Staff * Contractors: TBD * Project Delivery Method: None - Study * Tentative Project Delivery Timeline: TBD MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Provide outline to PDC Director for completing pavement condition assessment. * 60 Day Outlook: Start by 04/01/21 --- Start Assessment * 90 Day Outlook: 05/01/21 --- Continue on Going assessment as time permits. NOTES / ISSUES / CONCERNS: * None at this time.
SA | 6 | SA-0441 | Project On Hold Design Services | Informal Projects | 28900 | University Recreation | 0017 | Belk Gymnasium | BELK GYM 127 RECONFIGURE | Adding a door and wall to create a designated space to be used after UREC moves from Belk Gym to UREC building. Separating COR10 from 127 | 2019-10-16 13:31 | BELL, ROBERT (rbell16) |  | BARRETT, LACRISSA (lbarre11) | LINGER, JOSHUA (jlinger2) | 20-0074 | LINGER, JOSHUA (jlinger2) | 9987.5 | 0 | 0 |  | 07/07/2020 -Project on Hold per email from Robbie Bell 02/24/20. Overall price ($9,988) was more then they expected. They will use the space as is for now to determine necessity of project.
SA | 6 | SA-0439 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC 062 FITNESS ROOM RENOVATION | Fitness room renovation two include two spaces; one space is to remain a multipurpose room for events and the other space is to be converted into offices and storage space. Would like to keep as much of original hardwood floor as possible. | 2019-10-09 09:37 | STONE, CYNTHIA (cstone26) |  | STONE, CYNTHIA (cstone26) | LINGER, JOSHUA (jlinger2) | 20-0070 | LINGER, JOSHUA (jlinger2) | 0 | 0 | 0 |  | 07/07/2020 -Project on hold while Customer determines if they have other options.
SA | 6 | SA-0454 | Project On Hold Design Services | Informal Projects | 29700 | Housing and Residence Life | 0544 | Witherspoon | WITHERSPOON CABINET & COUNTERTOP REPLACEMENT | Witherspoon Hall.. We want to replace the countertops and cabinets in the kitchens in similar configuration to what's currently in the apartments. ..per Alan Hinton 757-692-9020 | 2020-02-11 15:47 | FOUST, KATHY (kfoust3) |  | BUNKER, DEBRA (dbunker) | LINGER, JOSHUA (jlinger2) | 20-0173 | LINGER, JOSHUA (jlinger2) | 353194.69 | 0 | 0 |  | 07/07/2020 - project on hold due to cost considerations
IF | 0 | SA-0471 | Construction | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION ROOF LEAKS | PMSU has two active leaks in Stairwell 001 and 377. We have worked with renovations shop in the past with no real resolution about fix. We are requesting a Project Manager assist to investigate and provide a permanent repair. | 2020-09-25 12:26 | BROWN, JOSHUA (jbrow450) | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | SMITH, RYAN (rsmit341) | 21-0031-I | SMITH, RYAN (rsmit341) | 3600 | 3600 | 0 | 2021-07-01 | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultant: REI Engineers * Contractors: TBD * Project Delivery Method: Informal Project Bid MILESTONES: * 30 Day Outlook: Completed by 04/01/21 --- Deliver Site Assessment Report to customer and discuss next steps. --- If approved to move forward request quotes for repair work and gain funding approval from customer to perform repair work. NOTES / ISSUES / CONCERNS: * Customer funding is minimal at this time and project will move slowly due to long approval process for funding.
IF | 0 | SA-0469 | Construction | Informal Projects | 30000 | Health Services | 0065 | Student Health Center | STUDENT HEALTH CENTER AIR HANDLER | Repair an Air Handler Unit at the Student Health Center | 2020-07-21 14:14 | BARRETT, LACRISSA (lbarre11) | FLORES, CLAUDIA (cflores3) | BARRETT, LACRISSA (lbarre11) | SMITH, RYAN (rsmit341) | 21-0016-I | SMITH, RYAN (rsmit341) | 13490 | 296347 | 10100 | 2021-05-01 | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultant: AME * Contractors: Trane * Project Delivery Method: Omnia Agreement * Tentative Construction Timeline: 05/01/21 - 07/01/21 MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Reviewing Pricing from Trane through Omnia Agreement --- Contractor Selected & PO Issued --- Drawing Complete --- SCO Approval Received * 60 Day Outlook: Completed by 04/01/21 --- Contractor Selected & PO Issued --- Equipment Ordered * 90 Day Outlook: 05/01/21 --- Awaiting Equipment Delivery NOTES / ISSUES / CONCERNS: * Funding secured with instruction to move forward as soon as possible to replace the AHU.
IF | 6 | BA-1796 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1008 | North Deck | NORTH DECK FFA LIGHTING REPLACEMENT | NORTH DECK FFA LIGHTING REPLACEMENT, replace top level light fixtures with LED type units in place of the metal halite. | 2019-02-14 09:30 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | LOVE, DAVID (dflove) | 19-0161 | LOVE, DAVID (dflove) | 7900 | 0 | 0 |  | Consultants / Contractors: * Consultants: None * Contractors: None Milestones: * Project placed On Hold till further funding is secured by customer. * Project will move forward pending approval of new campus Standard LED light fixture. Issues: * Existing campus lighting standard is no longer being manufactured.
IF | 6 | BA-1797 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1009 | CRI Deck 1 | CRI DECK FFA LIGHTING REPLACEMENT | CRI DECK FFA LIGHTING REPLACEMENT, replace top level light fixtures with LED type units in place of the metal halite. | 2019-02-14 09:31 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | LOVE, DAVID (dflove) | 19-0162 | LOVE, DAVID (dflove) | 6800 | 0 | 0 |  | Consultants / Contractors: * Consultants: None * Contractors: None Milestones: * Project placed On Hold till further funding is secured by customer. * Project will move forward pending approval of new campus Standard LED light fixture. Issues: * Existing campus lighting standard is no longer being manufactured.
IF | 6 | BA-1913 | Project On Hold FAM | Informal Projects | 13115 | Safety and Security | 0000 | Campus | CAMPUS SIREN UPGRADE "ALERTUS" | Safety & Security - Campus Siren upgrade - "Alertus" | 2020-01-31 11:09 | HILL, MICHELLE (mphilipp) |  | BARNETT, DENISE (dbarne33) | LOVE, DAVID (dflove) | 20-0162 | LOVE, DAVID (dflove) | 0 | 0 | 0 |  | Consultants / Contractors: * Consultants: Alertus * Contractors: None Selected Milestones: * Project on hold until Police & Public Safety can secure new project funding. Issues: * None
IF | 0 | AA-1709 | Construction | Informal Projects | 24202 | OneIT-Enterprise Infrastructure | 0004 | Atkins | ATKINS L36 G20 UPS | Atkins UPS for Atkins L-36 and G20ITS would like to start a project to replace the existing UPS at Atkins for our IT rooms. We have been in conversation with Tom MacNab who has worked with a vendor to provide a quote for what he feels is needed bas | 2020-04-27 07:30 | FRANCUS, KATHLEEN (krfrancu) | FRANCUS, KATHLEEN (krfrancu) | VITALLO, JUDY (jvitallo) | SMITH, RYAN (rsmit341) | 20-0229-I | SMITH, RYAN (rsmit341) | 10000 | 324800 | 15575 | 2020-09-30 | PROJECT NOTES UPDATED: * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultants: McKim & Creed * Contractor: TBD * Project Delivery Method: Informal Project Bid * Tentative Construction Timeline: 04/01/21 - 06/30/21 MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Final Drawings Approved --- SCO Approval Received --- Solicit Bids --- Award Contract * 60 Day Outlook: Completed by 04/01/21 --- Execute Contract * 90 Day Outlook: Completed by 05/01/21 --- Delivery time for UPS units --- Start Construction NOTES / ISSUES / CONCERNS: * Engineering study has been removed from the project scope as requested by the customer. We are moving forward with the design of the UPS units, only, per the suggested specifications of the customer. Details regarding bidding in discussion. * HVAC work to be performed as a separate informal project after installation of the UPS.
IF | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0020 | McEniry | McEniry Roof Repl | repl roof on McEniry | 2020-09-08 |  | HORNE, KATHRYN (khorne16) | CEALLAIGH, SHERRYL (sceallai) |  | 21-0026-F | WALTERS, DOUGLAS (dwalte22) | 0 | 0 | 0 |  | Consultants / Contractors: * Consultant: SKA * Contractors: TBD Milestones: * SKA hired to review spec's and wall flash details provided by Tremco. Site visit scheduled with consultant for Feb.9th. Notes / Issues / Concerns: * None at this time.
SA | 0 | SA-0474 | Scope & Budget Requested | Informal Projects | 29700 | Housing and Residence Life | 0564 | Martin Hall | MARTIN HALL SHOWER REPLACEMENT FY21 | We need to replace the remaining showers in Martin Hall with the same shower units we have used the last two years. | 2021-02-02 08:36 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | CAUDLE, AMANDA (afelock) | 21-0070-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (2-8-21) Met with customer on site 2-1-21. Anticipate scope and budget to customer by 2-12-21.
SA | 2 | SA-0456 | Construction | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION COMMAND CENTER SPEAKER SYSTEM | Student Union wants to use a command center speaker utilized through current Fire Control Panel for Building Announcements. | 2020-02-18 16:55 | BROWN, JOSHUA (jbrow450) |  | DALE, JEREMY (jdale8) | CAUDLE, AMANDA (afelock) | 20-0187 | CAUDLE, AMANDA (afelock) | 7000 | 7000 | 5928.72 | 2020-08-20 | (2-8-21) Approval from DOI and Safety. Working on SCO exemption request for necessary approvals.
SA | 2 | SA-0409 | Scope & Budget Requested | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 200 UPGRADES | Student Union - 200 - Aesthetic and other upgrades to room 200 to reflect new naming of space as James M. Hoppa Room. | 2019-02-12 13:12 | MEEHAN, MORGAN (mmeeha11) | BROWN, JOSHUA (jbrow450) | MARTIN, KAREN (kmart126) | HILL, CAROLINE (cmhill2) | 19-0156 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 2/9/2021 - Compiling materials board per Customer request.
AA | 6 | AA-1702 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0063 | College of Health and Human Services | CHHS VIRTUAL CADAVER LAB | CHHS - Virtual Cadaver Lab | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0205-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (09.14.2020) Waiting on information from Donia regarding location, and equipment. ON HOLD
AA | 6 | AA-1668 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0058 | Grigg Hall | GRIGG 386 CLEAN ROOM MOVE FROM CAMERON | Grigg - 386A - Move portions of existing Cameron clean room to Grigg 386A . This will locate all campus clean room functions into Grigg.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:19 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0120 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (09.14.2020) Working with Wei Gao on scope for equipment moves Will engage designer once scope is detailed. Will follow up with Donia regarding design fee.
AA | 6 | AA-1676 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0012 | Smith | SMITH 217/218/220 SYST. ENGIN. MOVE FROM CAMERON | Smith - 205, 206, 211, 212, 213, 214, 216, 308,311,314,317,318,319,320, 320A,325,348,349,351,352 - relocate Systems Engineering from Cameron 2nd floor to Smith and create graduate bull pins for Engineering Technology graduate students who currently o | 2020-01-14 10:44 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0128 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (09.01.2020) Waiting on design fee from McVeign & Mangum. Will follow up with them this week.
AA | 6 | AA-1677 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0012 | Smith | SMITH 2 & 3 FLOOR CORRIDOR REFRESH | Smith - 245D and 2nd/3rd floor corridors - Provide AV upgrade for conference room 245D for use by Engineering Technology. Replace existing VCT possibly Asbestos containing in 2nd and 3rd floor corridors with LVT to match recently renovated hallways o | 2020-01-14 10:50 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0129 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | NNP - part of Cameron moves
AA | 6 | AA-1685 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0063 | College of Health and Human Services | CHHS 330 NURSING SIMULATION LAB | CHHS - 330, 330A - Convert existing Classroom in School of Nursing Simulation Lab.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 11:12 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0134 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (09.01.2020) Waiting on Donia for equipment and project scope. ON HOLD
AA | 6 | AA-1684 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 114 116 118 120 122, 124 ACT. LEARN. CLRM | Fretwell - 114, 116, 118, 120, 122, 124 - Create new Active Learning Classroom and relocate Math Computer labs from other floors in Fretwell.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 2020-01-14 11:10 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0133 | SISCO, ASHLEY (asisco1) | 28634 | 0 | 0 |  | (12/01/20) Per email from Donia 6/24 this project is on hold due to funding. Will revisit in early fall.
AA | 6 | AA-1693 | Project On Hold Design Services | Informal Projects | 18000 | English | 0045 | Fretwell | FRETWELL 275 AND 248C REFRESH | I would like to talk to Ashley Sisco about possible options (seating and mobile wall) for refurbishing the English Department Reception area and lounge.Fretwell 275 and 248C | 2020-02-20 10:55 | WILLIAMS, ANGELA (anwillia) |  | WILLIAMS, ANGELA (anwillia) | SISCO, ASHLEY (asisco1) | 20-0177 | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 |  | (12/01/20) Per email from customer this project will be on hold.
AA | 6 | AA-1701 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 314 RENOVATIONS | Fretwell - Suite 314 - Office of Interdisciplinary Studies | 2020-03-16 08:40 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0204-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 |  | (12/01/20) Per email from Donia on 5/27/20 this project will be placed on hold. Will revisit in 6 months.
SA | 2 | SA-0461 | Construction | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC SALONS A/V | Project is to replace and upgrade Salon A/V. Project would include replacement of projectors and screens, additional projectors and screens, increased capability of streaming and conferencing, integration of cable TV, and necessary upgrades to audio | 2020-03-16 08:39 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | SPATARO, EVAMARIE (espataro) | 20-0201-I | LANIER, LISA (llanier) | 25000 | 30000 | 22838.19 | 2020-08-31 | 02/08/2021: Meeting page-turn held with customer on 02/03; review with design team held 02/05 for bid document accuracy and scope gap clarifications. Inaccuracies being addressed with designers.
SA | 2 | SA-0459 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0544 | Witherspoon | WITHERSPOON FALLING KEYSTONES | Please put in an Archibus request for Design Services. We have some failing keystones underneath a few balconies at Witherspoon Hall and need some help determining the proper fix.Thanks,Donny | 2020-02-26 15:19 | FOUST, KATHY (kfoust3) |  | BUNKER, DEBRA (dbunker) | LINGER, JOSHUA (jlinger2) | 20-0189 | LANIER, LISA (llanier) | 15537.5 | 38537.5 | 36898.73 | 2020-08-28 | 02/08/2021 - Preparing bid docs for remaining lintels repair/replacement.
IF | 6 | BA-1944 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | STARBUCKS TRUCK PAD AND ELECTRICAL | STARBUCKS TRUCK Pad and Electrical, provide design to provide a prototypical pad off off the sidewalk for Starbucks Truck to pull over and sell during the day. Initial location is intended to be Smith but pad could be used anywhere - need pull off, | 2020-04-10 12:56 | AVERITT, DREW (daveritt) | THOMPSON, JODY (jthom373) | MEDINA, CHARISSE (cturne66) | SMITH, RYAN (rsmit341) | 20-0221-I | SMITH, RYAN (rsmit341) | 26000 | 0 | 0 |  | PROJECT NOTES UPDATED: * 01/25/21 CONSULTANTS / CONTRACTORS: * Consultant: TBD * Contractor: TBD * Project Delivery Method: TBD MILESTONES: * Project on Hold per Drew Averitt per 6/16/2020 Email NOTES / ISSUES / CONCERNS: * None at this time.
SA | 0 | SA-0473 | Scope & Budget Requested | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0078 | Judy W. Rose Football Center | JUDY ROSE ADDITIONAL CAMERAS LOCKER ROOM | This is a project request to create a quote to add 2 additional cameras in the Judy Rose Football Center. These cameras would oversee the 2 entrances/exits to the football home locker room (008). I have already spoke with Lisa Lanier and David Love a | 2021-01-15 16:04 | RICE, JARRETT (jrice39) | RICE, JARRETT (jrice39) | STONE, CYNTHIA (cstone26) | LANIER, LISA (llanier) | 21-0064-I | LANIER, LISA (llanier) | 0 | 0 | 0 |  | 02/08/2021: Routed camera request form for signature to initiate the project meeting. Meeting to be scheduled on site with ITS and Lockshop for estimate. Will route Scope and Budget for approval and place in Construction.
SA | 0 | SA-0472 | Scope & Budget Requested | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC A/V ELECTRIC & HVAC | Split for the A/V project for Electrical and HVACProject should be forwarded to Eva Spataro who is working on the existing A/V project. | 2020-11-18 15:11 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | LANIER, LISA (llanier) | 21-0056-I | LANIER, LISA (llanier) | 0 | 0 | 0 |  | 02/08/2021: Meeting page-turn held with customer on 02/03; review with design team held 02/05 for bid document accuracy and scope gap clarifications. Inaccuracies being addressed with designers.
SA | 0 | SA-0467 | Scope & Budget Requested | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION PLUMBING DRAIN LINES STUDY | A project to fully investigate these apparent systemic issues and provide recommendations to bring the system into reliable operating conditions. Can original construction team involvement for repair/remediation/cost recovery? We would like the fee | 2020-07-08 08:04 | BROWN, JOSHUA (jbrow450) | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | LANIER, LISA (llanier) | 21-0005-I | LANIER, LISA (llanier) | 0 | 0 | 0 |  | 02/08/2021 Met with Don Janus and Don Gariepy to discuss scope and MO investigation and next steps for phasing. Don G. held customer meeting for phasing on 02/01. MO to request funding for equipment necessary to self-perform outside of this project.
SA | 0 | SA-0465 | Construction | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC OFFICE LEAK ROOM 303 | BSAC - Room 303. There is a substantial leak in office 303 but upon prior inspections the leak does not seem to come from the roof but perhaps issues with the gutter system or the window panes. We need a contractor to evaluate the source of the probl | 2020-06-29 14:42 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | LANIER, LISA (llanier) | 20-0261-I | LANIER, LISA (llanier) | 5000 | 5000 | 3800 | 2021-04-30 | 02/08/2021 - Final report received and reviewed with customer. Multiple repairs required. Routing Scope and Budget to customer for approval to move project into design.
AA | 6 | AA-1692 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | BAND TOWER FOOTING DESIGN | Band Tower Footing Design - The marching band will be installing a pre-fabricated 24' tall steel tower at the practice field. The tower will need to have a footing designed by an NC licensed engineer. Getting a budget for this project is very urgent | 2020-02-12 10:38 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SMITH, RYAN (rsmit341) | 20-0174 | SMITH, RYAN (rsmit341) | 550 | 550 | 520 | 2021-08-31 | PROJECT NOTES UPDATED: * 01/25/21 CONSULTANTS / CONTRACTORS: * Consultant: Education Steel Products & WTS * Contractor: TBD * Project Delivery Method: TBD MILESTONES: * Project placed on hold 12/14/20 pending funding * Reviewed next actions and proposed design with customer. * Completed conceptual image of tower to present to Administration for approval. . NOTES / ISSUES / CONCERNS: * Tower requested by Marching Band will cost approx. $85,000.00. * Total Project Cost Estimated at $125,000.00 - $150,000.00. * 09/21/20: Held meeting with customer. Due to department budget reductions customer does not see having funding for construction till 2021 or 2022. * Project recommended to be put on hold pending completion of conceptual presentation image. * Presentation image completed and reviewed by Kathryn Horne. Project placed on hold 12/14/20.
SA | 6 | SA-0440 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC 334A-E SALONS LIGHTING UPDATE | Replace light fixtures, and update control system to accommodate new lighting. | 2019-10-09 09:42 | STONE, CYNTHIA (cstone26) |  | STONE, CYNTHIA (cstone26) | SPATARO, EVAMARIE (espataro) | 20-0071 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | 9/22/2020: Project can be FF&E. Will work with customer to schedule. Customer holding for funding.
IF | 6 | BA-1889 | Project On Hold Design Services | Informal Projects | 13115 | Safety and Security | 0046 | Barnhardt Student Activity Center | FIRST PRIORITY CAMERA PROJECT PHASE 2 | Please assign to David Love - Phase 2 includes SAC, West Deck, Belk Gym, Cone, Colvard, Levine Hall, Cato, Prospector, McEniry, Auxiliary Services, Cameron, Bioinformatics, PORTAL, EPIC, Grigg, Duke, Motorsports, South Village Deck. (Approximately 2 | 2020-01-07 10:31 | HILL, MICHELLE (mphilipp) |  | BARNETT, DENISE (dbarne33) | SPATARO, EVAMARIE (espataro) | 20-0115 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | 9/22/2020: Defining Scope & Timeline with Customer. On hold until priority 1 is complete.
IF | 6 | AA-1655 | Project On Hold Design Services | Informal Projects | 15175 | Center City Campus | 0073 | The Dubois Center | CCB OUTDOOR LIGHTING | Additional lighting needs to be added to the back garden area. Please assess the current lighting, make recommendations for additional and adequate lighting and provide an estimate of cost. | 2019-10-10 12:30 | DUPLESSIS, ANN (aduples1) |  | DUPLESSIS, ANN (aduples1) | SPATARO, EVAMARIE (espataro) | 20-0079 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | 9/22/2020: Customer has received estimates. Waiting on decision.
SA | 6 | SA-0424 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION LED LIGHTING RETROFIT | Student Union - Entire BuildingStudent Union wants to increase sustainability by reducing energy consumption and decrease annual maintenance cost for replacement fluorescent lights by retrofitting lighting to LED. This project aligns with UNC policy | 2019-06-24 09:37 | BROWN, JOSHUA (jbrow450) | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | SPATARO, EVAMARIE (espataro) | 20-0022 | SPATARO, EVAMARIE (espataro) | 43000 | 0 | 0 |  | 9/22/2020: On hold.
AA | 6 | AA-1632 | Project On Hold Design Services | Informal Projects | 17200 | Biological Sciences | 0056 | Woodward Hall | WOODWARD 461 EMERGENCY CIRCUIT | Woodward Hall - 461 - Add emergency circuit to lab (461). Almost a mirror project to the recently completed 361 | 2019-08-08 14:59 | GRAY, DAVID (dlgray) |  | GRAY, DAVID (dlgray) | SPATARO, EVAMARIE (espataro) | 20-0044 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | 9/22/2020: Scope and budget provided to customer. Waiting on customer decision. Likely to be cancelled.
SA | 6 | SA-0455 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 340 POWER UPGRADE | Student Union would like to add additional power to the multi purpose room 340. We are looking at 100A, 3 phase, 5 wire, 120/208V. Requesting Eva Spataro on this project | 2020-02-18 16:03 | BROWN, JOSHUA (jbrow450) |  | MEEHAN, MORGAN (mmeeha11) | SPATARO, EVAMARIE (espataro) | 20-0186 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | 9/22/2020: Sent scope and budget to customer. Customer taking S&B to lobby for funding.
SA | 6 | SA-0388 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC ARENA BB & CURTAIN - LOW VOLTAGE | Change existing retractable basketball goals and mechanical partition curtain systems in Halton arena from 120v to low voltage. | 2018-07-26 14:21 | MOON, STUART (sgmoon) |  | BARNES, TRENT (tbarne21) | SPATARO, EVAMARIE (espataro) | 19-0038 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 |  | 10/13/2020: On hold. Originally project created by Grant Moon. Equipment was purchased by SAC staff that was insufficient. Design needed and additional equipment. Funding does not exist for this project, Cynthia requested it remain on hold.
AA | 6 | AA-1629 | Project On Hold Design Services | Informal Projects | 24400 | Research & Economic Dev. VC | 0080 | PORTAL | PORTAL INTERIOR GRAPHIC SIGNAGE | We want signage to raise the profile of the Office of Tech Transfer, SBTDC, Ventureprise, 49er Foundry, and the PORTAL Solutions Desk. Signage needs to large enough to be seen from across the lobby, attractive, and professional. All of these offices | 2019-07-15 14:23 | MATEEN, ALI (amateen) |  | KEENE, PATRICIA (pgkeene) | TERRY, STEPHEN (slterry) | 20-0032 | TERRY, STEPHEN (slterry) | 10800 | 0 | 0 |  | 09-30-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1663 | Project On Hold Design Services | Informal Projects | 18050 | DPT Writing, Rhet, Digital Studies | 0042 | Cameron Hall | CAMERON WRITING PROGRAM 1ST FLOOR SIGNS | CAMERON WRITING PROGRAM 1ST & 2ND FLOOR SIGNS: Name changes needed to Department of Writing, Rhetoric and Digital Studies. Several signs throughout first and second floors need to reflect our new name. Please contact Denise Sabo 7-1902 | 2019-11-15 13:46 | SABO, DENISE (dsabo1) |  | MULLIN, JOAN (jmulli40) | TERRY, STEPHEN (slterry) | 20-0089 | TERRY, STEPHEN (slterry) | 2900 | 0 | 0 |  | 09-30-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1706 | Project On Hold Design Services | Informal Projects | 15300 | College of Liberal Arts & Sciences | 0045 | Fretwell | FRETWELL 3RD FLOOR ATRIUM NAMING | Fretwell 3rd Floor Atrium Naming. Dr. Robert & Mrs. Tiwana Anderson Atrium Signage and Portrait development and installation | 2020-03-31 17:42 | FRIZZELL, MARY ELLEN (mfrizzel) | LEKOSKI-EURICH, JUDY (jlekoski) | STAFFORD, ELEANOR (eastaffo) | TERRY, STEPHEN (slterry) | 20-0217-I | TERRY, STEPHEN (slterry) | 5400 | 0 | 0 |  | 09-30-20. No change. Budget review. Customer said to hold.
BA | 6 | BA-1544 | Project On Hold Design Services | Informal Projects | 13800 | Environmental Health & Safety | 0000 | Campus | CAMPUS WIDE BUILDING EVACUATION MAPS | Building evacuation interior floor plan maps need to be installed in all buildings. The Office of Environmental Health and Safety would like to request an official scope and budget to install these maps. | 2017-03-07 16:43 | GRIFFIN, DARIUS (dgriffin) |  | GRIFFIN, DARIUS (dgriffin) | TERRY, STEPHEN (slterry) | 17-0195 | TERRY, STEPHEN (slterry) | 0 | 0 | 0 |  | 09-30-20 - Still on hold for funding. Scope was provided to EHS for funding review. This may need to be an internally BA funded projecgt.
BA | 6 | BA-1680 | Project On Hold Design Services | Informal Projects | 13800 | Environmental Health & Safety | 0000 | Campus | CAMPUS SERVICE VEHICLE SIGNAGE | Please provide a proposed scope and budget for the project detailed below. Once the scope and budget is received, our office will be able to determine if the project can be completed this fiscal year or in the next.Approximately 15 marker post signs | 2018-04-02 16:44 | GRIFFIN, DARIUS (dgriffin) | ALSTON, TAMEKA (talsto16) | BARNETT, DENISE (dbarne33) | TERRY, STEPHEN (slterry) | 18-0198 | TERRY, STEPHEN (slterry) | 18500 | 0 | 0 |  | 09-30-20 - Still on hold for funding. Scope and preliminary designs were provided to EHS for review.
BA | 6 | BA-1871 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING: Need Scope & Budget to allow further review by Jon Varnell to allow assessment of funding options. Please assign to Steve Terry. | 2019-11-18 10:44 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | TERRY, STEPHEN (slterry) | 20-0088 | TERRY, STEPHEN (slterry) | 30000 | 30000 | 0 | 2020-06-12 | 09-30-20. No change. Budget review. Customer said to hold.
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0020 | McEniry | MCENIRY CHILLER | replace chiller | 2021-01-07 14:12 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | KELLY, SHAWN (skelly64) | 0 | 1032155.3 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultant: TBD * Contractor: TBD * Project Delivery Method: Single Prime Bid * Tentative Construction Duration: 11/01/21 - 06/01/22 MILESTONES: *30 Day Outlook: To Be Complete By 03/01/21 --- Designer Interviews Held --- Designer Selection Made --- Designer PO Requested * 60 Day Outlook: To Be Complete By 04/01/21 --- Designer PO Issued --- Schematic Design Started * 90 Day Outlook: To Be Complete 05/01/21 --- Review Schematic Design NOTES / ISSUES / CONCERNS: * Will need designer to make recommendations on the electrical scope that can be accomplished within the current project budget prior to start of design.
AA | 6 | AA-1669 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD 264, 275 KINESIOLOGY MOVE FROM CAMERON | Woodward - 264, 275, 276, 276AMove Kinesiology Research labs from Cameron 2nd floor to Woodward 2nd Floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:25 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0121 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (2/8/21) Project on hold
AA | 6 | AA-1671 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1028 FADO MOVE FROM CAMERON | Colvard - 1028, 1028A, 1028B, 1028C, 1028D, 1028E, 1028F, 1028G, 1028H, 1028I - Relocate FADO from Cameron 2nd Floor to Colvard 1000 level.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 2020-01-14 09:46 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0123 | WELLS, ALICIA (awells43) | 10000 | 10000 | 0 | 2020-06-30 | (2/8/21) Project on hold
AA | 6 | AA-1672 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0042 | Cameron Hall | CAMERON 174 MOSAIC MOVE FROM CAMERON | Cameron- Suite 174 - Relocate Mosaic from Cameron 2nd floor to Cameron 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 2020-01-14 09:51 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0124 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (2/8/21) Project on hold
SA | 6 | SA-0442 | Project On Hold Design Services | Informal Projects | 29000 | Cone Univ Center | 0017 | Belk Gymnasium | BELK GYM 120 VENTURE MOVE | Venture has been approved to move from Cone to Belk gym. Within this project includes: coordinating a move of the staff, office furnishing needs, space renovations in Belk for storage space. As this project is related to project SA-0441 it could be | 2019-10-24 14:09 | MEEHAN, MORGAN (mmeeha11) | MEEHAN, MORGAN (mmeeha11) | DALE, JEREMY (jdale8) | WELLS, ALICIA (awells43) | 20-0080 | WELLS, ALICIA (awells43) | 160000 | 160000 | 0 | 2020-07-31 | (2/8/21)Project on hold until Spring 2021
AA | 6 | AA-1674 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0072 | EPIC Building | EPIC 1231 FURNITURE | EPIC - 1231 - Furniture Project - Exact scope still needs to be determined.Do not contact end users directly. Set up first meeting with Donia Schauble and Alicia Wells only. | 2020-01-14 10:01 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0126 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (2/8/21) Project on Hold
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 2131 | Field 6 - Football | MCCOLL FOOTBALL FIELD TURFF REPL | Replace the turf at the McColl Richard Football Field | 2021-01-19 09:39 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | KUGLER, BRIAN (bhkugler) | 0 | 480000 | 0 |  | PROJECT NOTES UPDATED: * 02/08/21 CONSULTANTS / CONTRACTORS: * Consultant: Fit Fields * Contractor: TBD * Project Delivery Method: (Single Prime) * Tentative Construction Duration: 04/15/20 - 06/15/21 MILESTONES: *30 Day Outlook: To Be Complete By 03/01/21 --- Fit Fields Condition Assessment --- Write & Review Performance Specifications --- Hold Vendor Showcase for Turf Providers (February 8th. 2-5 pm.) --- Select & Issue PO To Turf Vendor * 60 Day Outlook: To Be Complete By 04/01/21 --- Order Material --- Schedule Contractor --- Select & Award Contractor --- Execute Contracts * 90 Day Outlook: To Be Complete 05/01/21 --- Project in Construction NOTES / ISSUES / CONCERNS: * Athletics would like to look at field collar options for increased strength and durability. * Athletics currently designing graphics package for football field to be completed for Fit Fields review by first week of February.

## PROJECTS in CLOSEOUT
Projects in Closeout
Unit | Campus Priority | Control Code | Project Status Block | Project Type |  | Sub Department Name |  | Building Name | Project Request Name | Project Description | Date Created |  |  | Project Account Manager | Financial Account Manager | Project Number | Project Coordinator | Scope & Budget | Approved Project Total | Amount Billed |  | Notes
AA | 1 | AA-1556 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0537 | Sycamore | SYCAMORE FF&E | Sycamore FFEThe units that are moving are:Urban Institute_Contact: Jeff MichaelMetropolitan studies_ Contact: Curt WaltonInstitutional research_Contct: Steve Coppola | 2018-10-05 15:11 | HUNTER, KATHY (kdwhaley) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 19-0067F | WELLS, ALICIA (awells43) | 315000 | 419880 | 401514.27 | 2019-02-19 | (6/23/20) Move complete. Finalize punch list items
AA | 0 | AA-1718 | Scope & Budget Requested | Informal Projects |  | Research & Economic Dev. VC |  | Grigg Hall | GRIGG 330 SAFETY SHOWER | Grigg Hall - 330 - We would like a quote to purchase and install a lab safety shower. Is the current plumbing sufficient and can it be tied into the tempered water line? Need an idea of the timeline. | 2020-06-29 14:26 | 20-0258-I | PATEL, NAVINKUMAR (npatel24) | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) |  |  | 0 | 0 | 0 | 2020-04-24 | (7/14/20) Project complete. Working on final invoicing
AA | 1 | AA-1634 | Construction | Informal Projects |  | Academic Affairs VC |  | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | 20-0048 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) |  |  | 27589 | 80000 | 62292.54 | 2020-03-06 | (06-03-20) - Current work Complete. Nancy to provide other sign needs to use remaining balance. Project to remain open.
AA | 0 | AA-1714 | Construction | Informal Projects |  | AISLE |  | Burson | BURSON, CAMERON, COED, CHHS SIMULCAST CLASSROOMS | Burson 115, Cameron 101, COED 065, CHHS 281 we will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | 20-0252-I | PATEL, NAVINKUMAR (npatel24) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) |  |  | 9000 | 9000 | 0 | 2020-02-28 | 06/01/20: Construction Completed 06/26/20: Projected Project Closeout
AA | 0 | AA-1715 | Construction | Informal Projects |  | AISLE |  | Fretwell | FRET, FRIDAY, MCENIRY, DENNY SIMULCAST CLASSROOMS | Fretwll 128, Friday 137, McEniry 117 Denny220. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | 20-0253-I | PATEL, NAVINKUMAR (npatel24) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) |  |  | 9000 | 9000 | 0 | 2019-08-16 | 07/31/20: Construction Complete 08/07/20: Projected Project Closeout Note: Awaiting Special Order Brick to complete Year 1 Masonry Repairs.
AA | 0 | AA-1716 | Construction | Informal Projects |  | AISLE |  | Belk Gymnasium | BELK GYM, DUKE, EPIC SIMULCAST CLASSROOMS | Belk Gym 201, Duke 345, Epic 2222. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | 20-0254-I | PATEL, NAVINKUMAR (npatel24) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) |  |  | 9000 | 9000 | 0 | 2020-02-28 | 07/31/20: Projected Construction Completion 08/14/20: Projected Project Closeout Note: Project delayed due to equipment manufacture production delays caused by Covid-19
AA | 0 | AA-1717 | Construction | Informal Projects |  | AISLE |  | Rowe | ROWE, SMITH, STORRS, WOODWARD SIMULCAST CLASSROOMS | Rowe 161, Smith 202, Storrs 290, Woodward 155. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:13 | 20-0255-I | PATEL, NAVINKUMAR (npatel24) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) |  |  | 9000 | 9000 | 0 | 2020-04-03 | 100% complete Close out Project
AA | 0 | AA-1724 | Construction | Informal Projects |  | Academic Affairs VC |  | Cameron Hall | CAMERON 217 COVID19 TESTING LAB | Prepare exiting lab area in Cameron Lab Suite 271 to be ready for use as COVID 19 Testing Lab per description provide by Angelica Martins | 2020-07-16 11:39 | 21-0015-I | PATEL, NAVINKUMAR (npatel24) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) |  |  | 5100 | 5100 | 0 | 2020-08-30 | 100% complete project closeout phaset
AA | 1 | AA-1704 | Construction | Informal Projects |  | Academic Affairs VC |  | Cafeteria Activities Building | CAB KITCHEN EQUIPMENT DEMO | CAB-Kitchen Equipment Demolition | 2020-03-16 08:41 | 20-0207-I | BOAL, JOHN (jboal1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 53382 | 60882
AA | 0 | AA-1636 | Construction | Informal Projects |  | Academic Affairs VC |  | Fretwell | FRETWELL 407 SOCIOLOGY LAB | Convert existing small classroom in Fretwell 407 into a Sociology lab. | 2019-08-15 12:57 | 20-0050 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 17171 | 17171 |  | This project is closed out.
AA | 1 | AA-1634 | Construction | Informal Projects |  | Academic Affairs VC |  | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | 20-0048 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) |  | 27589 | 80000
AA | 1 | AA-1707 | Construction | Informal Projects |  | Academic Affairs VC |  | College of Education | COED 002-009 ACTIVE LEARNING CLASSROOM | COED Building - Rooms 002, 003, 005, 007, 009 - This project is meant to combine rooms 002, 005, and 007 into a large active learning classroom for 128 students. Room 009 would be converted into a graduate bull pin and room 003 would become a semina | 2020-04-09 11:12 | 20-0219-I | CAUDLE, AMANDA (afelock) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) |  | 265000 | 265000 |  | (9.1.20) Work complete
AA | 1 | AA-1635 | Construction | Informal Projects |  | Academic Affairs VC |  | Woodward Hall | WOODWARD VIVARIUM AUTOCLAVE REPLACEMENT | Replace current vivarium autoclave with larger-capacity, internal-boiler autoclave. | 2019-08-15 11:48 | 20-0049 | CAUDLE, AMANDA (afelock) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 200000 | 209000 |  | (8/31/20) Project complete. Waiting on final billing.
AA | 1 | AA-1697 | Construction | Informal Projects |  | Academic Affairs VC |  | Robinson Hall | ROBINSON BELK THEATER ORCHESTRA PIT LIFT | Replacement of Orchestra Lift | 2020-03-16 08:25 | 20-0198-I | CAUDLE, AMANDA (afelock) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 268293.64 | 268293.64 |  | (9-1-20) Work complete - wrapping up punch list items.
AA | 1 | AA-1641 | Construction | Informal Projects |  | Performing Arts Services (PAS) |  | Robinson Hall | ROBINSON 220 FACULTY OFFICE | Need to create a new faculty office from the alcove part of Robinson 220 that is adjacent to 221 and create a separate entrance into the hallway. This project should be similar to the one recently done for Robinson 124. | 2019-08-27 17:32 | 20-0075 | HILL, CAROLINE (cmhill2) | LUEKE, BEVERLY (bblueke) |  | RUCKER, BETH (aefird) |  |  | 8200 | 17400 |  | (9/2/20) project complete
AA | 0 | AA-1636 | Construction | Informal Projects |  | Academic Affairs VC |  | Fretwell | FRETWELL 407 SOCIOLOGY LAB | Convert existing small classroom in Fretwell 407 into a Sociology lab. | 2019-08-15 12:57 | 20-0050 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 17171 | 17171 |  | (09.01.2020) Work Complete
AA | 1 | AA-1634 | Construction | Informal Projects |  | Academic Affairs VC |  | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | 20-0048 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 27589 | 80000 |  | (09.01.2020) Work Complete
AA | 1 | AA-1623 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1040 ACTIVE LEARNING CLASSROOM | Colvard Classroom Active Learning | 2019-06-07 13:22 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0008 | CAUDLE, AMANDA (afelock) | 298000 | 298000 | 120458.21 |  | (09.01.2020) Work Complete
AA | 1 | AA-1694 | Construction | Informal Projects | 23700 | Prec Metrology & Intellignt Mfg Ctr | 0057 | Duke Centennial Hall | DUKE 138 350FG MOORE MACHINE RELOC | Duke Centennial Hall - Rooms 132 & 151The following is requested :1. CSA Certified2. 208 3 Phase 30 AMP Breaker /40 AMP Fuses3. (3) 208 1 PHASE 10 AMP Each4. High Pressure Air from BoosterThis is needed to prepare the lab for Moore 350FG machine | 2020-02-25 15:30 | CHASTAIN, JENNIFER (jchasta4) | DUTTERER, BRIAN (bsdutter) | CHASTAIN, JENNIFER (jchasta4) | SPATARO, EVAMARIE (espataro) | 20-0181 | CAUDLE, AMANDA (afelock) | 11000 | 7000 | 5629.57 |  | (09.01.2020) Work Complete
AA | 1 | AA-1707 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0052 | College of Education | COED 002-009 ACTIVE LEARNING CLASSROOM | COED Building - Rooms 002, 003, 005, 007, 009 - This project is meant to combine rooms 002, 005, and 007 into a large active learning classroom for 128 students. Room 009 would be converted into a graduate bull pin and room 003 would become a semina | 2020-04-09 11:12 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0219-I | CAUDLE, AMANDA (afelock) | 265000 | 265000 | 93125.93 |  | (09.21.20) Waiting on walk off matts, all punch list items complete All interior work is complete and Lab is functional.
AA | 0 | AA-1725 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | CLASSROOM SOCIAL DISTANCING DIAGRAMS | Generate and provide social distancing diagrams for all campus classrooms showing student seating layout to be achieved for social distancing in light of COVID 19 spread prevention. | 2020-07-22 15:29 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 21-0017-I | FRERE, ELIZABETH (efrere) | 25000 | 24490.1 | 0 |  | (9-22-20) Consultants: Biloba Architecture Contractor: MV Momentum LLC Milestone dates and activities: Construction and punch list complete. Working through final change order paperwork and close out documents.
AA | 0 | AA-1714 | Construction | Informal Projects | 28350 | AISLE | 0038 | Burson | BURSON, CAMERON, COED, CHHS SIMULCAST CLASSROOMS | Burson 115, Cameron 101, COED 065, CHHS 281 we will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0252-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 0 | (9-28-20) Consultants: Biloba Architecture Contractor: MV Momentum LLC Milestone dates and activities: Construction complete. Working through close out documents.
AA | 0 | AA-1715 | Construction | Informal Projects | 28350 | AISLE | 0045 | Fretwell | FRET, FRIDAY, MCENIRY, DENNY SIMULCAST CLASSROOMS | Fretwll 128, Friday 137, McEniry 117 Denny220. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0253-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 7757.63 | 9/21/2020: This project is complete at this time. Awaiting final billing.
AA | 0 | AA-1716 | Construction | Informal Projects | 28350 | AISLE | 0017 | Belk Gymnasium | BELK GYM, DUKE, EPIC SIMULCAST CLASSROOMS | Belk Gym 201, Duke 345, Epic 2222. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0254-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 15554.3 | (9/29/20) Construction complete. Project to be closed out.
AA | 0 | AA-1717 | Construction | Informal Projects | 28350 | AISLE | 0019 | Rowe | ROWE, SMITH, STORRS, WOODWARD SIMULCAST CLASSROOMS | Rowe 161, Smith 202, Storrs 290, Woodward 155. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:13 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0255-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 35455.64 | Consultants/Contractors: *Contractors: MV Momentum Milestones: *09/28/2020 - Project complete. Final billing received.
AA | 1 | AA-1634 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0048 | SISCO, ASHLEY (asisco1) | 27589 | 80000 | 77068.84 | 106913.39 | Consultant/Contractors: *Contractor: Heartland Construction Milestones: *09/29/2020 - Project punch list walk held 08/28. Project complete. Final billing issued.
AA | 0 | AA-1636 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 407 SOCIOLOGY LAB | Convert existing small classroom in Fretwell 407 into a Sociology lab. | 2019-08-15 12:57 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0050 | SISCO, ASHLEY (asisco1) | 17171 | 17171 | 15554.3 | 77068.84 | (9/29/20) Project complete. Need to reorder two lamps that came in with missing parts.
AA | 6 | AA-1684 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 114 116 118 120 122, 124 ACT. LEARN. CLRM | Fretwell - 114, 116, 118, 120, 122, 124 - Create new Active Learning Classroom and relocate Math Computer labs from other floors in Fretwell.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 2020-01-14 11:10 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0133 | SISCO, ASHLEY (asisco1) | 28634 | 0 | 0 | 93125.93 | (9-28-20) Construction complete - wrapping up final billing.
AA | 6 | AA-1693 | Project On Hold Design Services | Informal Projects | 18000 | English | 0045 | Fretwell | FRETWELL 275 AND 248C REFRESH | I would like to talk to Ashley Sisco about possible options (seating and mobile wall) for refurbishing the English Department Reception area and lounge.Fretwell 275 and 248C | 2020-02-20 10:55 | WILLIAMS, ANGELA (anwillia) |  | WILLIAMS, ANGELA (anwillia) | SISCO, ASHLEY (asisco1) | 20-0177 | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 | 78988.3 | (10-5-20) Equipment start up complete. Continue monitoring BAS trends. With funds remaining, looking into floor refinish.
AA | 6 | AA-1701 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 314 RENOVATIONS | Fretwell - Suite 314 - Office of Interdisciplinary Studies | 2020-03-16 08:40 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0204-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 | 218096.9 | (10-5-20) Installation complete. Wrapping up final billing.
AA | 1 | AA-1703 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0041 | Storrs | STORRS 230, 222B, 274, 276 RENOVATIONS | Storrs - Rooms 230, 222B, and 274/276 - Additional work and furniture needed to accommodate space changes that will take place as part of the Capital ITS Infrastructure Replacement work in the Storrs building. | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | PAYNE, TODD (tapayne) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0206-I | SISCO, ASHLEY (asisco1) | 77000 | 77000 | 3869.8 | 0 | Project already complete. Mark Reynolds and Todd Payne confirmed. Please cancel.
AA | 0 | AA-1724 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0042 | Cameron Hall | CAMERON 217 COVID19 TESTING LAB | Prepare exiting lab area in Cameron Lab Suite 271 to be ready for use as COVID 19 Testing Lab per description provide by Angelica Martins | 2020-07-16 11:39 | SCHAUBLE, DONIA (dcooke) | KEENE, PATRICIA (pgkeene) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 21-0015-I | PATEL, NAVINKUMAR (npatel24) | 5100 | 5100 | 0 | 14201.98 | 9/30/2020 - Will finalize invoices and close out project per Customer requests.
AA | 0 | AA-1718 | Scope & Budget Requested | Informal Projects | 24400 | Research & Economic Dev. VC | 0058 | Grigg Hall | GRIGG 330 SAFETY SHOWER | Grigg Hall - 330 - We would like a quote to purchase and install a lab safety shower. Is the current plumbing sufficient and can it be tied into the tempered water line? Need an idea of the timeline. | 2020-06-29 14:26 | MATEEN, ALI (amateen) | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) | PATEL, NAVINKUMAR (npatel24) | 20-0258-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | 117877.71 | 9/30/2020 - Following up with Customers to see how they would like to use their contingency.
AA | 1 | AA-1635 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD VIVARIUM AUTOCLAVE REPLACEMENT | Replace current vivarium autoclave with larger-capacity, internal-boiler autoclave. | 2019-08-15 11:48 | SCHAUBLE, DONIA (dcooke) | WILLIAMS, CHANDRA (cwill297) | MCMANNEN, TONYA (tmcmanne) | SPATARO, EVAMARIE (espataro) | 20-0049 | CAUDLE, AMANDA (afelock) | 200000 | 209000 | 87436.12 | 0 | Dependent on two other Colvard projects, no action until those projects move forward and have a clear schedule and plan.
AA | 0 | AA-1636 | Punch List | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 407 SOCIOLOGY LAB | Convert existing small classroom in Fretwell 407 into a Sociology lab. | 2019-08-15 12:57 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0050 | SISCO, ASHLEY (asisco1) | 17171 | 17171 | 15554.3 | 35455.64 | Consultants/Contractors: *Contractors: MV Momentum Milestones: *10/06/2020 - Project complete. Final billing received.
AA | 1 | AA-1697 | Construction | Informal Projects |  | Academic Affairs VC |  | Robinson Hall | ROBINSON BELK THEATER ORCHESTRA PIT LIFT | Replacement of Orchestra Lift | 2020-03-16 08:25 | 20-0198-I | CAUDLE, AMANDA (afelock) |  | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | 268293.64 | 268293.64 | 218096.9 | 15554.3 | (10/05/20) Construction complete. Project to be closed out.
AA | 1 | AA-1641 | Construction | Informal Projects |  | Performing Arts Services (PAS) |  | Robinson Hall | ROBINSON 220 FACULTY OFFICE | Need to create a new faculty office from the alcove part of Robinson 220 that is adjacent to 221 and create a separate entrance into the hallway. This project should be similar to the one recently done for Robinson 124. | 2019-08-27 17:32 | 20-0075 | HILL, CAROLINE (cmhill2) |  | LUEKE, BEVERLY (bblueke) |  | RUCKER, BETH (aefird) | 8200 | 17400 | 14201.98 | 77068.84 | (10/05/20) Project complete. Waiting on two lamps to be delivered. Final billing.
AA | 1 | AA-1634 | Construction | Informal Projects |  | Academic Affairs VC |  | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | 20-0048 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  | 27589 | 80000 | 77139.32 | 2020-07-28 | (10-5-20) Final SCO inspection scheduled for 9/29/20.
AA | 0 | AA-1711 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0041 | Storrs | STORRS 1ST FL STUDIO KNEE WALL REMOVAL | SoA would like to remove the knee wall in the 1st year studio area on the 1st floor. Once the wall is removed VCT in the area will need to be patched. | 2020-04-27 07:32 | SCHAUBLE, DONIA (dcooke) | PAYNE, TODD (tapayne) | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 20-0234-I | FRERE, ELIZABETH (efrere) | 10000 | 9991.6 | 5858.6 | 2020-07-13 | (10-5-20) MET Labs re-inspection complete 9/24/20. Final SCO inspection 9/29/20.
AA | 1 | AA-1704 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0031 | Cafeteria Activities Building | CAB KITCHEN EQUIPMENT DEMO | CAB-Kitchen Equipment Demolition | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0207-I | BOAL, JOHN (jboal1) | 53382 | 71182 | 7757.63 | 2020-08-03 | (10-5-20) Construction complete - wrapping up final billing.
BA | 1 | BA-1920 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0092 | Facilities Ops and Parking (FOPS) | MOVE FIS TO FOPS FACILITIES OPERATIONS | FPFM, MOVE FIS TO FOPS, FACILITIES OPERATIONS & PARKING SERVICES BUILDING: Moves Management: | 2020-02-11 05:24 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | CLARK, VALERIE (vclark9) | 20-0168 | SISCO, ASHLEY (asisco1) | 5000 | 80040.46 | 79724.1 | 2020-09-30 | Designer completed their work. Currently invoicing - requested backup information and more detailed breakdown of invoicing charges.
BA | 2 | BA-1894 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | 2020 CAMPUS PARKING MISC. SIGNS #1 | 2020 CAMPUS PARKING MISC. SIGNS #1, various signs as needed as done in years past. First 2 items are: 1) Replace damaged HC sign in Lot 7 with flex post. 2) Install 2 new spaces in Lot 16 for Geography and Earth Sciences vehicles. | 2020-01-23 08:54 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | TERRY, STEPHEN (slterry) | 20-0139 | TERRY, STEPHEN (slterry) | 7000 | 7000 | 2250 | 2020-06-30 | (10.05.20) Work Complete
BA | 0 | BA-1969 | Construction | Informal Projects |  | Business Services AVC |  | Prospector | PROSPECTOR COVID DINING MODIFICATIONS | PROSPECTOR Covid Modifications, modify Prospector as follows:1. All wall in Servery 200, patch and paint wall in 200 common with 200C. Remove and store door (at CAB) between 200/202.2 Remove portion of 4th cashier stand (end wall where cash regist | 2020-07-13 13:57 | 21-0010-I | CAUDLE, AMANDA (afelock) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) |  |  | 7000 | 7000 | 6358 | 2020-06-30 | (10.05.20) Work Complete
BA | 0 | BA-1970 | Construction | Informal Projects |  | Business Services AVC |  | Popp Martin Student Union | STUDENT UNION COVID DINING MODIFICATIONS | SU Covid Modifications1. at Bojangles, remove low wall and counter across from Bojangles BOH door and cashiers. Remove counter only at low wally near Bojangles pick up area. Need to determine how to treat top of wall - looks like we can cut stone | 2020-07-13 13:57 | 21-0011-I | CAUDLE, AMANDA (afelock) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) |  |  | 6500 | 6500 | 5893.32 | 2020-06-30 | (10.05.20) Work Complete
BA | 0 | BA-1956 | Construction | Informal Projects |  | Facilities Informal Projects |  | Bissell House | CHANCELLOR LOT EXTERIOR UPGRADES | CHANCELLOR LOT EXTERIOR UPGRADES: Project Dollar Maximum: $100,000.00 using Chancellor's Central Funds. Includes excavation design & construction, waterproofing, plants & bushes replanting, and soil compaction. Assign to Alicia Wells. | 2020-05-11 12:19 | 20-0237-BA | WELLS, ALICIA (awells43) | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) |  |  | 100000 | 300000 | 292826.55 | 2020-06-30 | (10.05.20) Work Complete
BA | 0 |  | Created | Capital Projects |  | Facilities Management AVC |  | Popp Martin Student Union | STARBUCKS RENOVATION | Renovate the Starbucks at Student Union | 2020-01-06 07:18 |  | CAUDLE, AMANDA (afelock) |  | CEALLAIGH, SHERRYL (sceallai) |  |  | 428309.49 | 316213.68 | 0 | 2019-11-13 | (10/05/20) Project complete. Waiting on two lamps to be delivered. Final billing.
BA | 0 |  | Created | Capital Projects |  | Facilities Management AVC |  | Popp Martin Student Union | STARBUCKS RENOVATION | Renovate the Starbucks at Student Union | 2020-01-06 07:18 |  | CAUDLE, AMANDA (afelock) |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | 428309.49 | 316213.68 | 2020-08-31 | (10/05/20) Construction complete. Project to be closed out.
IF | 2 | BA-1865 | Construction | Informal Projects | 10400 | Business Services AVC | 0029 | Housing and Residence Life | HOUSING & RESIDENCE LIFE LOADING DOCK LADDER | HRL, Loading Dock Ladder, add metal ladder at the catering loading dock between the two truck bays with roll over grab bars. This is required as drivers are jumping off dock rather than using nearby stairs. | 2019-10-28 12:02 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 20-0091 | KELLY, SHAWN (skelly64) | 1500 | 1500 | 184.14 |  | (10/05/20) Per email from Donia 6/24 this project is on hold due to funding. Will revisit in early fall.
IF | 2 | BA-1853 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | CAMPUS WIDE PARKING DECK REPAIRS PHASE 1 | CAMPUS WIDE PARKING DECK REPAIRS, provide recommended repairs for year 1 work as outlined by THP Limited, Inc. in various decks as outlined in previous reports and meetings. Please assign to Shawn Kelly. Thanks. | 2019-07-15 15:25 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | KELLY, SHAWN (skelly64) | 20-0033 | KELLY, SHAWN (skelly64) | 275000 | 275000 | 225585.16 |  | (10/05/20) Per email from customer this project will be on hold.
IF | 2 | SA-0451 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0545 | Wallis Hall | WALLIS HALL AIR COOLED CHILLER | For Design Services:The Wallis Hall air cooled chiller is at its end of life. Last summer it actually failed and we had to bring in a temporary chiller to cool the building for a few weeks to the cost of about $40,000. So we'd like to go ahead and | 2020-01-31 07:51 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | KELLY, SHAWN (skelly64) | 20-0161 | KELLY, SHAWN (skelly64) | 200000 | 202500 | 0 |  | (10/05/20) Per email from Donia on 5/27/20 this project will be placed on hold. Will revisit in 6 months.
IF | 2 | BA-1903 | Construction | Informal Projects | 10400 | Business Services AVC | 1096 | Chancellor's Lot | CHANCELLOR'S LOT CRACK SEAL & SEAL COAT | CHANCELLOR'S LOT CRACK SEAL & SEAL COAT, utilize JSS's existing contract to provide crack seal and seal coat maintenance this summer | 2020-01-23 09:17 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0146 | SMITH, RYAN (rsmit341) | 8600 | 8600 | 8470 | 2020-09-07 | (10/05/20) Entering PO's. Product is coming in and being stored in Storrs. Todd Payne is handling all the install of the product once the capital project is complete.
IF | 0 | BA-1960 | Construction | Informal Projects | 10500 | Auxiliary Operations | 1005 | West Deck | WEST DECK ARROWS | West Deck - repaint arrows Call West deck arrows) | 2020-05-13 11:06 | HOLMES, ROBERT (rholme16) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0241-I | SMITH, RYAN (rsmit341) | 4020 | 4020 | 4020 | 2020-09-30 | (10.05.20) All punch list items complete All interior work is complete and Lab is functional.
IF | 2 | BA-1756 | Construction | Informal Projects |  | Business Services AVC |  | CRI Deck 1 | CRI DECK ELECTRICAL REPAIRS | CRI DECK, Electrical Repairs, the bulk of the raceways in the main electrical closet exit the panelboards on the top, with the exception of the genset battery charger / jacket heater circuit. This circuit is in the slab of the electrical room, and c | 2018-12-13 11:34 | 19-0097 | SPATARO, EVAMARIE (espataro) | HOLMES, ROBERT (rholme16) | MULLMANN, JANETTA (jmullman) |  |  | 35000 | 3000 | 2600 |  | (10.05.20) Work complete
IF | 2 | BA-1860 | Construction | Informal Projects |  | Business Services AVC |  | Prospector | PROSPECTOR DUMPSTER BOLLARDS | PROSPECTOR, provide dumpster bollards. The 2 dumpsters (trash and recycling - 10CY) have a tendency to migrate out into the drive lanes until we reset them. Trucks are forced to have to maneuver around them to access the loading dock. We need to d | 2019-09-23 10:28 | 20-0066 | KELLY, SHAWN (skelly64) | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) |  | 9500 | 9500 | 0 | 2020-04-30 | (10-13-20) Equipment start up complete. Continue monitoring BAS trends. With funds remaining, looking into floor refinish.
IF | 2 | BA-1865 | Construction | Informal Projects |  | Business Services AVC |  | Housing and Residence Life | HOUSING & RESIDENCE LIFE LOADING DOCK LADDER | HRL, Loading Dock Ladder, add metal ladder at the catering loading dock between the two truck bays with roll over grab bars. This is required as drivers are jumping off dock rather than using nearby stairs. | 2019-10-28 12:02 | 20-0091 | KELLY, SHAWN (skelly64) | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) |  | 1500 | 1500 | 184.14 | 2020-08-31 | (10/12/20) Project to be closed out.
IF | 2 | BA-1853 | Construction | Informal Projects |  | Business Services AVC |  | Campus | CAMPUS WIDE PARKING DECK REPAIRS PHASE 1 | CAMPUS WIDE PARKING DECK REPAIRS, provide recommended repairs for year 1 work as outlined by THP Limited, Inc. in various decks as outlined in previous reports and meetings. Please assign to Shawn Kelly. Thanks. | 2019-07-15 15:25 | 20-0033 | KELLY, SHAWN (skelly64) | AVERITT, DREW (daveritt) |  | MULLMANN, JANETTA (jmullman) |  | 275000 | 275000 | 225585.16 |  | (10-20-20) Installation complete. Wrapping up final billing.
IF | 0 | BA-1967 | Construction | Informal Projects |  | FM Architectural/Engineering |  | Campus | CRAVEN CROFT RENOVATION | Renovation of several Craven Croft Houses to prepare to be rented Estimate prepared by Renovations team | 2020-06-25 15:24 | 20-0256-I | KELLY, SHAWN (skelly64) | FAKE, WILLIAM (wmfake) |  | HARRIS, ELLEN (elharris) |  | 60000 | 60000 | 33017.12 |  | 10/8/2020 - Will finalize invoices and close out project per Customer requests.
IF | 2 | BA-1864 | Construction | Informal Projects | Business Services AVC |  |  | Prospector | PROSPECTOR REROOF UPPER LEVEL | PROSPECTOR Reroof Upper Prospector - remove and replace the Upper Prospector roof which is only area that is still rubber and rock ballast with EPDM roof to match newer areas. | 2019-10-28 11:59 | 20-0090 | SMITH, RYAN (rsmit341) | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) |  | 26502 | 251002 | 21840 |  | Consultants / Contractors: * Consultants: None * Contractors: Heartland General Contracting Milestones: * Construction Completed * 10/09/20: Project Closeout Completed Notes / Issues / Concerns: * None
IF | 2 | BA-1848 | Construction | Informal Projects | Business Services AVC |  |  | South Village Deck | SOUTH VILLAGE DECK WEST ELEVATOR TOWER VENTILATION | SOUTH VILLAGE DECK, provide heating and ventilation in the west elevator tower as per Heapy Engineering recommendations received during the deck reviews (under a Shawn Kelly project). Thanks. | 2019-06-28 11:15 | 20-0028 | SMITH, RYAN (rsmit341) | AVERITT, DREW (daveritt) |  | MULLMANN, JANETTA (jmullman) |  | 17105 | 188105 | 169190.13 |  | (10/19/20) Project complete. Working on final billing
IF | 0 | BA-1951 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | PARKING DECK REPAIR YEAR 2; FACADE | PARKING DECK REPAIR Year 2; Facade, Joint & Concrete RepairYear 2 regular maintenance as specified by 5 year parking deck maintenance plan for repair of concrete flooring, exterior masonry, expansion joints, crack sealant, and facade repair. | 2020-04-27 07:31 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0231-I | SMITH, RYAN (rsmit341) | 150000 | 150000 | 120759.42 |  | Consultants / Contractors: * Consultants: None * Contractors: Lockelane Construction Milestones: * Construction Completed * 10/9/20: Project Closeout Completed Notes / Issues / Concerns: * None
IF | 0 | BA-1951 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | PARKING DECK REPAIR YEAR 2; FACADE | PARKING DECK REPAIR Year 2; Facade, Joint & Concrete RepairYear 2 regular maintenance as specified by 5 year parking deck maintenance plan for repair of concrete flooring, exterior masonry, expansion joints, crack sealant, and facade repair. | 2020-04-27 07:31 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0231-I | SMITH, RYAN (rsmit341) | 150000 | 150000 | 120759.42 |  | Consultants / Contractors: * Consultants: THP * Contractors: Carolina Restoration & Waterproofing Milestones: * 8/10/20 - 09/25/20: Completing masonry and additional structural improvements with remaining project contingency as authorized by customer. *10/05/20 - 10/09/20: Estimated Projector Closeout Complete Notes / Issues / Concerns: * None
IF | 0 | BA-1955 | Construction | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR REPLACE AHU-3 | PROSPECTOR REPLACE AHU-3. Replace AHU-3 which recently had the motor go down. Unit is 32 years old and probably best to make a full replacement rather than just the motor. Don Janus has been involved in discussions. | 2020-05-06 07:35 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | SMITH, RYAN (rsmit341) | 20-0236-I | SMITH, RYAN (rsmit341) | 240500 | 240500 | 17914.56 |  | Consultants / Contractors: * Contractors: - FM Renovations-Paint & Repair - FM BES-Cleaning, FM Zone 6-HVAC - Stratos Solutions-Flooring Milestones: * 7/20/20 - 8/14/20: Cleaning, Painting, & HVAC Repairs * 8/17/20 - 8/21/20: Carpet Installation * 8/24/20 - 8/28/20: Final Punch List & Completion of Properties 601 & 605 * 8/31/20 - 9/28/20: Final Punch List & Completion of Properties 625, 9902, & 9903. * 10/09/20: Projected 100% Project Closeout Notes / Issues / Concerns: * Project Delayed due to complications with wall paper removal and drywall repair as well as completing additional work requests as requested by Richard in Real Estate. * Minimal budget to repair any major structural or mechanical issues that may be found during cosmetic improvements.
IF | 0 | BA-1955 | Construction | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR REPLACE AHU-3 | PROSPECTOR REPLACE AHU-3. Replace AHU-3 which recently had the motor go down. Unit is 32 years old and probably best to make a full replacement rather than just the motor. Don Janus has been involved in discussions. | 2020-05-06 07:35 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | SMITH, RYAN (rsmit341) | 20-0236-I | SMITH, RYAN (rsmit341) | 240500 | 240500 | 17914.56 |  | Consultants / Contractors: * Consultant: REI Engineers * Contractor: Rike Roofing Milestones: * 08/17/20: Begin Construction * 10/09/20: Projected Construction Completion * 10/30/20: Projected Project Closeout Notes / Issues / Concerns: * Roof repair will still be under construction during the first four weeks of school. However, customer is aware and impacts to operations at Prospector loading dock will be minimal.
SA | 0 |  | Created | Capital Projects |  | FM Architectural/Engineering |  | Wells Fargo Fieldhouse | WELLS FARGO SOFTBALL INDOOR TRAINING FACILITY | A new Softball Indoor Training facility will be constructed in order to improve and extend practice schedules to remain competitive with other collegiate women's softball programs, including Conference USA peers. Further, the project will result in c | 2017-05-25 08:46 |  |  | CEALLAIGH, SHERRYL (sceallai) |  | NEILSON, JOHN (jneilson) |  |  | 650000 | 1174971.62 |  | Consultants / Contractors: * Consultant: Heapy Engineering * Contractors: Heartland General Contracting Milestones: * 08/05/20: Pre-Construction Meeting Held * 09/14/20 - 10/02/20: Construction Scheduled * 10/05/20 - 10/09/20: Final Punch List & SCO Inspections * 10/12/20 - 10/30/20: Project Construction & Financial Closeout Notes / Issues / Concerns: * None
SA | 0 | 11494 | Created | Capital Projects |  | FM Architectural/Engineering |  | Campus | EAST VILLAGE UTILITIES |  |  | This project is closed out. |  |  |  |  | KUGLER, BRIAN (bhkugler) |  | 2100000 | 1279159.45 | 44074 | 100% Complete Project Closeout
SA | 2 | SA-0447 | Construction | Informal Projects |  | Housing and Residence Life |  | Resident Managers House | GREEK HOUSE 14 CAMERA | Can you please create a design service project for pulling wiring and adding in an electrical outlet at Greek House 14 (Resident Manager's House) for the camera project?Thanks,Donny | 2019-12-12 12:10 | 20-0109 | LANIER, LISA (llanier) | FOUST, KATHY (kfoust3) |  | BUNKER, DEBRA (dbunker) | LANIER, LISA (llanier) |  | 8000 | 38500 | 44104 | Knee wall removal complete, basic electrical work complete, working with customer and Tom MacNab to find a solution for replacement of floor outlets that stick up out of the slab.
SA | 1 | IA-0035 | Construction | Informal Projects |  | Athletics Admin/Support |  | Barnhardt Student Activity Center | SAC 066 ATHLETIC WEIGHT ROOM RENOVATION | Building Name - Barnhardt Student Activity CenterRoom Number - 066Will need to add three offices to weight room in the SAC when Recreation vacates the area in November. Cannot do project until UREC has vacated the area after 11/1. | 2019-06-05 16:33 | 20-0053 | LANIER, LISA (llanier) | FERGUSON, JAMES (jcfergus) |  | SPEASE, DARIN (dspease) | LANIER, LISA (llanier) |  | 28500 | 114500 | 44022 | 11/11/2020: All work has been completed. Walked the space with the customer 11/6/2020 and received final approval. Getting invoices submitted now.
SA | 2 | SA-0365 | Construction | Informal Projects |  | Student Union |  | Popp Martin Student Union | STUDENT UNION 2ND FLOOR CARPET REPLACEMENT | Replace the carpet in 2nd floor common areas of the student union. Well worn areas include by the stairwell and Crown Commons | 2018-02-14 12:47 | 18-0146 | HILL, CAROLINE (cmhill2) | MEEHAN, MORGAN (mmeeha11) |  | HARRIS, MELODY (mhharris) |  |  | 135100 | 135100 | 44074 | 100% Complete Project Closeout
SA | 2 | SA-0447 | Construction | Informal Projects |  | Housing and Residence Life |  | Resident Managers House | GREEK HOUSE 14 CAMERA | Can you please create a design service project for pulling wiring and adding in an electrical outlet at Greek House 14 (Resident Manager's House) for the camera project?Thanks,Donny | 2019-12-12 12:10 | 20-0109 | LANIER, LISA (llanier) | FOUST, KATHY (kfoust3) |  | BUNKER, DEBRA (dbunker) |  |  | 8000 | 38500 | 44105 | Consultants / Contractors: * Consultant: McVeigh & Mangum/McCracken & Lopez * Contractor: Trane Milestones: * 10/16/20: Install new unit * 10/25/20: Startup, Testing, & Commissioning * 11/15/20: Projected Project Closeout Notes / Issues / Concerns: * None at this time.
SA | 0 | IA-0036 | Construction | Informal Projects |  | Athletics Admin/Support |  | Judy W. Rose Football Center | FOOTBALL LOCKER REPLACEMENT | Judy Rose Fieldhouse - Home Football Locker RoomTo replace lockers in home football locker room. Athletics has secured the lockers they want to purchase but need project # so that SCO can approve any electrical needs. Have discussed with Lisa Lanier. | 2020-05-18 11:38 | 20-0246-I | LANIER, LISA (llanier) | FERGUSON, JAMES (jcfergus) | SPEASE, DARIN (dspease) |  |  | 38300 | 38300 | 32008.49 | 44105 | Consultants / Contractors: * Consultant: McVeigh & Mangum/McCracken & Lopez * Contractor: Trane Milestones: * 10/16/20: Install new unit * 10/25/20: Startup, Testing, & Commissioning * 11/15/20: Projected Project Closeout Notes / Issues / Concerns: * None at this time.
| 0 | 11494 | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | EAST VILLAGE UTILITIES | The project is for the construction of utility infrastructure to support improvements to the East Village sector of campus to include water, telecom, and high voltage electrical service. | 2015-03-12 09:37 |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) |  |  | 2100000 | 1279159.45 |  | Consultants/Contractors: *Consultants: Engineering Services *Contractors: FO Milestones: *01/11/2021 - New lockers installed. Perimeter lockers are final and passed electrical inspection. Center lockers awaiting final electrical inspection. Project to be closed out.
AA | 0 | AA-1728 | Construction | Informal Projects |  | Greenhouse |  | McMillan Greenhouse | POLLY'S GARDEN | This is phase II of Polly's Garden in the VanLandingham Glen. The new work is an extension of previously installed work installed by Ponders, Inc. This project involves a combination of highly detailed specialty stonework that must be identical toex | 2020-08-27 13:56 | HILL, CAROLINE (cmhill2) | 21-0023-I | RAMOS, AMPARO (agil2) | GILLMAN, JEFFREY (jgillman) | HILL, CAROLINE (cmhill2) | [5 empty] | 2/1/2021 - Project completed. Will process invoice and close out project this week.
| IF | 0 |  | Capital Projects |  | FM Architectural/Engineering |  | Campus | CID 2 - EAST VILLAGE UTILITIES | The project is for the construction of utility infrastructure to support improvements to the East Village sector of campus to include water, telecom, and high voltage electrical service. | 2015-03-12 09:37 | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  |  | KUGLER, BRIAN (bhkugler) | [5 empty] | PROJECT NOTES UPDATED * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultant: McGill * Contractors: Two Brothers Utilities MILESTONES: *30 Day Outlook: To Be Completed by 03/01/21 --- Modeling & Report Revisions To Be Received --- Modelling & Report Revisions Reviewed & Approved by Greg Cole --- Final Project Closeout to be Complete NOTES / ISSUES / CONCERNS: * Project continues to remain open until FM Engineering is satisfied with model calculations. Final project closeout completely contingent on FM Engineering final approvals. * 05/18/20: Project Construction Completed * McGill currently providing model updates to water use calculations per Greg Cole of FM Engineering's direction. * Projected completion of model updates and review and approval by FM Engineering estimated to take 6 Months to complete. * Project currently being managed by Greg Cole of FM Engineering to determine and approve final model revisions and project completion.

## PROJECTS - ON HOLD
| Projects on Hold | [11 empty] | 2021-02-09
Unit | Campus Priority | Control Code | Project Status Block | Project Type | Sub Department Name | Building Name | Project Request Name | Project Description | Date Created | Project Account Manager | Financial Account Manager | Project Number | Project Coordinator | Scope & Budget | Approved Project Total | Amount Billed | Notes
AA | 6 | AA-1440 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Duke Centennial Hall | DUKE 349 RENOVATIONS | Convert faculty lounge to office spaceContact Kevin Scott Smith for details 7-8350 | 2017-09-07 12:39 | HUNTER, KATHY (kdwhaley) | HUNTER, KATHY (kdwhaley) | 18-0049 | BOAL, JOHN (jboal1) | 0 | 0 | 0 | 7/28/2020 : On hold. Project not funded.
AA | 6 | AA-1660 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | McEniry | MCENIRY 310 HYDROLOGY & BIOCHEMISTRY LAB | Renovation of space on the on the 3rd floor as a hydrology and biochemistry lab and renovation of a classroom space on the 2nd floor. | 2019-11-06 12:30 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0084 | BOAL, JOHN (jboal1) | 35439 | 37439 | 24653.05 | 7/28/2020: Scope of work has been significantly reduced. Change order to increase design fee has been issued. FY 21 funding from AA.
AA | 6 | AA-1661 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | McEniry | MCENIRY 316 LANDSCAPE ECOLOGY LAB | Renovation of McEniry 316 and 313 for use as landscape ecology lab. | 2019-11-06 12:31 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0085 | BOAL, JOHN (jboal1) | 35000 | 38000 | 24346.63 | 7/28/2020: Scope of work has been significantly reduced. Redesign fee was submitted 5-11. Change order to design purchase order has been issued. FY 21 funding from AA.
AA | 6 | AA-1670 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Belk Gymnasium | BELK GYM 024 KINESIOLOGY LAB | Belk Gym - 024 - Move human physiology research lab from Cameron 2nd floor to Belk Gym Ground floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:28 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0122 | BOAL, JOHN (jboal1) | 0 | 0 | 0 | 7/28/2020: Customer has been asked to provide additional scope information but not yet supplied it. Project is not yet funded.
AA | 6 | AA-1414 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Woodward Hall | WOODWARD BIOLOGY CAMERA REPLACEMENT | Woodward Biology Camera Replacement | 2017-05-16 13:26 | HUNTER, KATHY (kdwhaley) | HUNTER, KATHY (kdwhaley) | 18-0010 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | (7-28-20) Project on hold per Academic Affairs.
AA | 6 | AA-1638 | Project On Hold Design Services | Informal Projects | Center City Campus | The Dubois Center | CCB 1106 EXPANSION | Explore the possibility of remodeling and expanding 1106 at Center City. Remove wooden side walls and wall between 1106 and the storage areas behind it to make the room larger. | 2019-08-19 13:41 | DUPLESSIS, ANN (aduples1) | DUPLESSIS, ANN (aduples1) | 20-0051 | CAUDLE, AMANDA (afelock) | 13000 | 0 | 0 | (7-28-20) Routed scope and budget for design 12/4/19. Pending customer approval to proceed. Placed on hold 6-26-20.
AA | 6 | AA-1673 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Atkins | ATKINS 146, 149 CNT. FOR GRAD.LIFE MOVE FROM CONE | Atkins - 146, 148A, 148B, Suite 149 - Move Center for ¦Graduate Life from Cone 2nd floor to Atkins 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:57 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0125 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | (7-28-20) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 6 | AA-1698 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | PORTAL | PORTAL 129 UPGRADES | Portal - 129 - Upgrades to Active Learning Classroom | 2020-03-16 08:25 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0199-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | (7-28-20) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 6 | AA-1531 | Project On Hold Design Services | Informal Projects | Research & Economic Dev. VC | PORTAL | PORTAL 232 AND 242 ENHANCEMENTS | PORTAL 322: 1) add color, texture, or paneling to the walls 2) move the UNCC sign in the space to different location 3) upgrade the photos and picture frames in the roomPORTAL 242: 1) add wall covering to wall outside of 242 and hang pictures like th | 2018-05-22 10:42 | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) | 19-0001 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 | 7/27/2020 - Customer has requested that this project should be place on hold until further notice.
AA | 6 | AA-1610 | Project On Hold Design Services | Informal Projects | College of Business | Friday | FRIDAY 391 RENOVATION | We are looking at splitting the room in two similar to 388/393.It may not be an exact half split though.We want one side to be a small PhD classroom and the other side to be a student bullpen area similar to 388/393.Classroom half needs to seat 20 if | 2019-04-10 13:24 | CARMICHAEL, TIMOTHY (twcarmic) | TWEED, DANA (dtweed1) | 19-0204 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 | 7/27/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1616 | Project On Hold Design Services | Informal Projects | College of Business | Friday | FRIDAY 242 CONFERENCE ROOM | I need a cost estimate to convert Friday 242 into a conference room. Move 1 display to the end wall. Remove the remaining 5 displays (Belk College Technology Team will take the 5 that get removed). Patch and paint walls. Core drill to connect lapto | 2019-04-22 13:35 | CARMICHAEL, TIMOTHY (twcarmic) | SANCHEZ, STEPHANIE (ssanch12) | 19-0211 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 | 7/27/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1690 | Project On Hold Design Services | Informal Projects | OneIT-CIO | Kennedy | KENNEDY 320 RECONFIGURATION | We would like to discuss options for how Kennedy 320 can adjust for growth, specifically using 2 - 4 areas of existing space. Sandra Soriano (78987) is the contact for this request. | 2020-02-07 14:44 | VITALLO, JUDY (jvitallo) | VITALLO, JUDY (jvitallo) | 20-0170 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 | 7/27/2020 - Project on hold per customer request.
AA | 6 | AA-1668 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Grigg Hall | GRIGG 386 CLEAN ROOM MOVE FROM CAMERON | Grigg - 386A - Move portions of existing Cameron clean room to Grigg 386A . This will locate all campus clean room functions into Grigg.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:19 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0120 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | (07.28.2020) Working with Wei Gao on scope for equipment moves Will engage designer once scope is detailed. Will follow up with Donia regarding design fee.
AA | 6 | AA-1676 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Smith | SMITH 217/218/220 SYST. ENGIN. MOVE FROM CAMERON | Smith - 205, 206, 211, 212, 213, 214, 216, 308,311,314,317,318,319,320, 320A,325,348,349,351,352 - relocate Systems Engineering from Cameron 2nd floor to Smith and create graduate bull pins for Engineering Technology graduate students who currently o | 2020-01-14 10:44 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0128 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | (07.28.2020) Waiting on design fee from McVeign & Mangum. Will follow up with them this week.
AA | 6 | AA-1677 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Smith | SMITH 2 & 3 FLOOR CORRIDOR REFRESH | Smith - 245D and 2nd/3rd floor corridors - Provide AV upgrade for conference room 245D for use by Engineering Technology. Replace existing VCT possibly Asbestos containing in 2nd and 3rd floor corridors with LVT to match recently renovated hallways o | 2020-01-14 10:50 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0129 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | NNP - part of Cameron moves
AA | 6 | AA-1685 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | College of Health and Human Services | CHHS 330 NURSING SIMULATION LAB | CHHS - 330, 330A - Convert existing Classroom in School of Nursing Simulation Lab.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 11:12 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0134 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | (07.28.2020) Waiting on Donia for equipment and project scope. ON HOLD
AA | 6 | AA-1702 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | College of Health and Human Services | CHHS VIRTUAL CADAVER LAB | CHHS - Virtual Cadaver Lab | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0205-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | (07.28.2020) Waiting on information from Donia regarding location, and equipment. ON HOLD
AA | 0 | AA-1540 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | McMillan Greenhouse | GREENHOUSE FOR BIOLOGY FACULTY | Greenhouse for Biology Faculty | 2018-06-29 09:17 | HUNTER, KATHY (kdwhaley) | HUNTER, KATHY (kdwhaley) | 19-0023 | PATEL, NAVINKUMAR (npatel24) | 228650 | 0 | 0 | (06-03-20) - Still on hold for funding. Scope was provided to EHS for funding review.
AA | 6 | AA-1684 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Fretwell | FRETWELL 114 116 118 120 122, 124 ACT. LEARN. CLRM | Fretwell - 114, 116, 118, 120, 122, 124 - Create new Active Learning Classroom and relocate Math Computer labs from other floors in Fretwell.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 2020-01-14 11:10 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0133 | SISCO, ASHLEY (asisco1) | 28634 | 0 | 0 | (7/28/20) Per email from Donia 6/24 this project is on hold due to funding. Will revisit in early fall.
AA | 6 | AA-1693 | Project On Hold Design Services | Informal Projects | English | Fretwell | FRETWELL 275 AND 248C REFRESH | I would like to talk to Ashley Sisco about possible options (seating and mobile wall) for refurbishing the English Department Reception area and lounge.Fretwell 275 and 248C | 2020-02-20 10:55 | WILLIAMS, ANGELA (anwillia) | WILLIAMS, ANGELA (anwillia) | 20-0177 | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 | (7/28/20) Per email from customer this project will be on hold.
AA | 6 | AA-1701 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Fretwell | FRETWELL 314 RENOVATIONS | Fretwell - Suite 314 - Office of Interdisciplinary Studies | 2020-03-16 08:40 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0204-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 | (7/28/20) Per email from Donia on 5/27 this project will be placed on hold. Will revisit in 6 months.
AA | 0 | AA-1692 | Scope & Budget Requested | Informal Projects | Academic Affairs VC | Campus | BAND TOWER FOOTING DESIGN | Band Tower Footing Design - The marching band will be installing a pre-fabricated 24' tall steel tower at the practice field. The tower will need to have a footing designed by an NC licensed engineer. Getting a budget for this project is very urgent | 2020-02-12 10:38 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0174 | SMITH, RYAN (rsmit341) | 0 | 0 | 11731.7 | On Hold till Funding Approved
AA | 6 | AA-1628 | Project On Hold Design Services | Informal Projects | Mech Engineering & Engineering Sci | Motorsports Research | MOTORSPORT WIND/TUN.STRUCT. ANALYSIS & POWER SPLY. | Motorsports Research Room 124 - Can we please have someone come out and approve the location of putting a concrete isolation pad in. Isolation pad will be provided by a 3rd party, we just need load approval for the floor below. | 2019-07-03 15:33 | CANTOR, MARION (mjcantor) | TADLOCK, ERICA (ewalter5) | 20-0023 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | (7/28/2020) Waiting on customer to assemble windtunnel and finalize where the equipment will reside in lab. Once complete, electrical can be run.
AA | 6 | AA-1632 | Project On Hold Design Services | Informal Projects | Biological Sciences | Woodward Hall | WOODWARD 461 EMERGENCY CIRCUIT | Woodward Hall - 461 - Add emergency circuit to lab (461). Almost a mirror project to the recently completed 361 | 2019-08-08 14:59 | GRAY, DAVID (dlgray) | GRAY, DAVID (dlgray) | 20-0044 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | (7/28/2020) Scope and budget provided to customer. Waiting on customer decision. Likely to be cancelled.
AA | 6 | AA-1645 | Project On Hold Design Services | Informal Projects | EPIC | Lot 6 | LOT 6 - EV CHARGING STATION | Lot 6 - EV Charging Station: Provide an estimate for design and construction cost to install an experimental EV charging location. | 2019-09-09 13:42 | BROWN, LORI (lmorri25) | MOOSE, ROBIN (rmoose2) | 20-0059 | SPATARO, EVAMARIE (espataro) | 11000 | 0 | 0 | (7/28/2020) On hold.
AA | 6 | AA-1700 | Project On Hold Design Services | Informal Projects | EPIC | EPIC Building | EPIC HIGHBAY WINCH POWER CONNECTION | Please install three 460V 3phase power connections in the EPIC highbay lab. | 2020-03-16 08:40 | MOOSE, ROBIN (rmoose2) | MOOSE, ROBIN (rmoose2) | 20-0203-I | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | (7/28/2020) Showed rough estimate to customer, customer needs to research funding options
AA | 6 | AA-1629 | Project On Hold Design Services | Informal Projects | Research & Economic Dev. VC | PORTAL | PORTAL INTERIOR GRAPHIC SIGNAGE | We want signage to raise the profile of the Office of Tech Transfer, SBTDC, Ventureprise, 49er Foundry, and the PORTAL Solutions Desk. Signage needs to large enough to be seen from across the lobby, attractive, and professional. All of these offices | 2019-07-15 14:23 | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) | 20-0032 | TERRY, STEPHEN (slterry) | 10800 | 0 | 0 | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1663 | Project On Hold Design Services | Informal Projects | DPT Writing, Rhet, Digital Studies | Cameron Hall | CAMERON WRITING PROGRAM 1ST FLOOR SIGNS | CAMERON WRITING PROGRAM 1ST & 2ND FLOOR SIGNS: Name changes needed to Department of Writing, Rhetoric and Digital Studies. Several signs throughout first and second floors need to reflect our new name. Please contact Denise Sabo 7-1902 | 2019-11-15 13:46 | SABO, DENISE (dsabo1) | MULLIN, JOAN (jmulli40) | 20-0089 | TERRY, STEPHEN (slterry) | 2900 | 0 | 0 | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1706 | Project On Hold Design Services | Informal Projects | College of Liberal Arts & Sciences | Fretwell | FRETWELL 3RD FLOOR ATRIUM NAMING | Fretwell 3rd Floor Atrium Naming. Dr. Robert & Mrs. Tiwana Anderson Atrium Signage and Portrait development and installation | 2020-03-31 17:42 | FRIZZELL, MARY ELLEN (mfrizzel) | STAFFORD, ELEANOR (eastaffo) | 20-0217-I | TERRY, STEPHEN (slterry) | 5400 | 0 | 0 | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1669 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Woodward Hall | WOODWARD 264, 275 KINESIOLOGY MOVE FROM CAMERON | Woodward - 264, 275, 276, 276AMove Kinesiology Research labs from Cameron 2nd floor to Woodward 2nd Floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:25 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0121 | WELLS, ALICIA (awells43) | 0 | 0 | 0 | (7/29/20) Project on hold
AA | 6 | AA-1671 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Colvard | COLVARD 1028 FADO MOVE FROM CAMERON | Colvard - 1028, 1028A, 1028B, 1028C, 1028D, 1028E, 1028F, 1028G, 1028H, 1028I - Relocate FADO from Cameron 2nd Floor to Colvard 1000 level.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 2020-01-14 09:46 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0123 | WELLS, ALICIA (awells43) | 10000 | 10000 | 0 | (7/29/20) Project on hold
AA | 6 | AA-1672 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Cameron Hall | CAMERON 174 MOSAIC MOVE FROM CAMERON | Cameron- Suite 174 - Relocate Mosaic from Cameron 2nd floor to Cameron 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 2020-01-14 09:51 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0124 | WELLS, ALICIA (awells43) | 0 | 0 | 0 | (7/29/20) Project on hold
AA | 6 | AA-1674 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | EPIC Building | EPIC 1231 FURNITURE | EPIC - 1231 - Furniture Project - Exact scope still needs to be determined.Do not contact end users directly. Set up first meeting with Donia Schauble and Alicia Wells only. | 2020-01-14 10:01 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0126 | WELLS, ALICIA (awells43) | 0 | 0 | 0 | (7/29/20) Project on Hold
AA | 1 | AA-1440 | Scope & Budget Requested | Informal Projects | Academic Affairs VC | Duke Centennial Hall | DUKE 349 RENOVATIONS | Convert faculty lounge to office spaceContact Kevin Scott Smith for details 7-8350 | 2017-09-07 12:39 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 18-0049 | BOAL, JOHN (jboal1) | 0 | 0 | 0 | (06-03-20) - Still on hold for funding. Scope and preliminary designs were provided to EHS for review.
AA | 6 | AA-1700 | Project On Hold Design Services | Informal Projects | EPIC | 0072 | EPIC Building | EPIC HIGHBAY WINCH POWER CONNECTION | 2020-03-16 08:40 | MOOSE, ROBIN (rmoose2) | PARK, YOUNGJIN (ypark17) | MOOSE, ROBIN (rmoose2) | SPATARO, EVAMARIE (espataro) | 20-0203-I | 0 | 0 | 06/03/20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1670 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | 0017 | Belk Gymnasium | BELK GYM 024 KINESIOLOGY LAB | 2020-01-14 09:28 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0122 | 0 | 0 | Project will move forward pending the new campus standard LED light fixture approval. Existing standard is no longer being manufactured.
AA | 1 | AA-1683 | Scope & Budget Requested | Informal Projects | Academic Affairs VC | Colvard | COLVARD 1017-1018 ACTIVE LEARNING CLASSROOM | Colvard - Suite 1017 and 1018A - Create new Active Learning Classroom.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 2020-01-14 11:07 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0132 | FRERE, ELIZABETH (efrere) | 0 | 0 | 0 | (7-28-20) Project to remain on hold per Scott Plunkett.
AA | 0 | AA-1732 | Scope & Budget Requested | Informal Projects | FRETWELL SUITE 320 WORKSTATION RECONFIGURE | Academic Affairs VC | Fretwell - Suite 320 - Reconfiguration of existing workstations from 5 stations to 3. | Fretwell | 2020-10-22 14:55 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) |  | HILL, CAROLINE (cmhill2) | STAFFORD, ELEANOR (eastaffo) |  | 0 | Following Up with Customer To Closeout
BA | 6 | BA-1631 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Bioinformatics | FPFM, BIOINFORMATICS 124 CODE ROOM USE SEPARATIONS | FPFM - BIOINFORMATICS 124 CODE REQUIRED ROOM USE SEPARATIONS: Mechanical, storage and wood shop uses need separation by 2-hour fire walls. Construction costs unknown. Outside design is required at $30,000. | 2017-11-02 06:48 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) | 18-0089 | BOAL, JOHN (jboal1) | 0 | 0 | 0 | (7-28-20) Project on Hold
BA | 6 | BA-1696 | Project On Hold Design Services | Informal Projects | Business Services AVC | Union Deck | UNION DECK STORAGE ROOM | UNION DECK Storage Room, provide large storage room on level 1 underneath of the up ramp where area is fenced off. This modification was rejected in the Expansion project due to schedule but we would like to review requirements and price out impleme | 2018-05-07 09:37 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | 18-0232 | CAUDLE, AMANDA (afelock) | 225000 | 0 | 30800 | (05-08-2020) Watson Tate Savory total design contract reduced to $29,920. Partial invoice for $23,222.10 dated 04-23-2020 was approved for payment on 04-27-2020.
BA | 6 | UA-0039 | Project On Hold Design Services | Informal Projects | Alumni Affairs | Hauser Alumni Pavilion | HAUSER ALUMNI PAVILION SECURITY DOORS | Project to add garage door type security between the brick columns . Cleo - use 138062. Contact Scott Plunkett at 7-7792 | 2017-11-14 09:27 | PLUNKETT, SCOTT (ssplunke) | WIDMAIER, CLEO (cswidmai) | 18-0101 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | 7/28/2020: Project not funded.
BA | 6 | BA-1930 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Kennedy | KENNEDY CONTEMPLATIVE SPACE RENOVATION | KENNEDY CONTEMPLATIVE SPACE RENOVATION, DESIGN: Chancellor 2020 Central Funds: $50,000. Design Only. Project Dollar Maximum: $30,800.00. | 2020-03-04 07:20 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) | 20-0184 | FRERE, ELIZABETH (efrere) | 30800 | 30800 | 0 | On Hold Pending Cone Deck Decisions
BA | 6 | BA-1586 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Campus | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT: Congestion Task Force assignment for design only: Central Funds - Project Dollar Maximum: $13,000. | 2017-05-17 07:56 | FAKE, WILLIAM (wmfake) | PAQUETTE, NOELLA (njpaquet) | 17-0225 | KELLY, SHAWN (skelly64) | 13000 | 13000 | 0 | 06-03-20 - Site meeting on hold.
BA | 6 | BA-1676 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Campus | FPFM, CAMPUS ADA PATHWAYS SURVEY DATA REVIEW | FPFM, REVIEW RECENTLY COMPILED CAMPUS ADA PATHWAYS SURVEY DATA TO MAKE RECOMMENDATIONS FOR CHANGES TO CAMPUS MAP: Point of contact: Katie Montie with Disability Services (DS). Facilities Information Systems (FIS) to provide technical assistance. | 2018-03-07 06:37 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) | 18-0178 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 | (7/28/2020) Customer has received estimates. Waiting on decision.
BA | 6 | BA-1762 | Project On Hold Design Services | Informal Projects | Business Services AVC | Lot 7 | LOT 7 & 7A RECONFIGURATION | LOT 7 & 7A Reconfiguration, redesign Lots 7 and 7A to optimize usage and traffic flow (Design only at this point in time). | 2019-01-07 10:46 | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | 19-0106 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 | 02-13-2020 ON HOLD - Discussed project with Cass Ferguson. Project does not have funding at this time. Needs further discussion due to continued water infiltration. Does not appear to be site related.
BA | 6 | BA-1544 | Project On Hold Design Services | Informal Projects | Environmental Health & Safety | Campus | CAMPUS WIDE BUILDING EVACUATION MAPS | Building evacuation interior floor plan maps need to be installed in all buildings. The Office of Environmental Health and Safety would like to request an official scope and budget to install these maps. | 2017-03-07 16:43 | GRIFFIN, DARIUS (dgriffin) | GRIFFIN, DARIUS (dgriffin) | 17-0195 | TERRY, STEPHEN (slterry) | 0 | 0 | 0
BA | 6 | BA-1680 | Project On Hold Design Services | Informal Projects | Environmental Health & Safety | Campus | CAMPUS SERVICE VEHICLE SIGNAGE | Please provide a proposed scope and budget for the project detailed below. Once the scope and budget is received, our office will be able to determine if the project can be completed this fiscal year or in the next.Approximately 15 marker post signs | 2018-04-02 16:44 | GRIFFIN, DARIUS (dgriffin) | BARNETT, DENISE (dbarne33) | 18-0198 | TERRY, STEPHEN (slterry) | 18500 | 0 | 0 | 06/27/20: On Hold Pending Review with Engineering Dept
BA | 6 | BA-1871 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Campus | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING: Need Scope & Budget to allow further review by Jon Varnell to allow assessment of funding options. Please assign to Steve Terry. | 2019-11-18 10:44 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) | 20-0088 | TERRY, STEPHEN (slterry) | 30000 | 30000 | 0 | (7/28/2020) Defining Scope & Timeline with Customer. On hold until priority 1 is complete.
BA | 6 | BA-1959 | Project On Hold Design Services | Informal Projects | Auxiliary Operations | Lot 8 | LOT 8 HOUSING VEHICLES SIGNAGE | Install signs for Housing vehicles in Lot 8 (I would call "Lot 8 signage) | 2020-05-13 11:05 | HOLMES, ROBERT (rholme16) | MULLMANN, JANETTA (jmullman) | 20-0240-I | TERRY, STEPHEN (slterry) | 0 | 0 | 0 | 7/28/2020: Project on hold.
IF | 6 | SA-0444 | Project On Hold Design Services | Informal Projects | Cone Univ Center | Cone University Center | CONE NORTH ROOF REPLACEMENT | Cone North Roof Replacement - Fully remove existing system to replace the Cone North Building Roofing System. | 2019-12-09 13:04 | MERCK, DONNA (dlmerck) | HARRIS, MELODY (mhharris) | 20-0112 | BOAL, JOHN (jboal1) | 0 | 0 | 0 | (7/28/2020) On hold.
IF | 6 | BA-1854 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Barnhardt Student Activity Center | FPFM, SAC FIRE & SMOKE PURGE SYSTEMS INVESTIGATION | FPFM, SAC FIRE & SMOKE PURGE SYSTEMS INVESTIGATION: Investigate smoke management of SAC during fire alarm activation. AHU devices do not shut down; smoke purge system serving the food court does not function. Assign to Don Janus. | 2019-07-23 08:33 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) | 20-0034 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 | Project will move forward pending the new campus standard LED light fixture approval. Existing standard is no longer being manufactured.
IF | 6 | BA-1796 | Project On Hold Design Services | Informal Projects | Business Services AVC | North Deck | NORTH DECK FFA LIGHTING REPLACEMENT | NORTH DECK FFA LIGHTING REPLACEMENT, replace top level light fixtures with LED type units in place of the metal halite. | 2019-02-14 09:30 | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | 19-0161 | LOVE, DAVID (dflove) | 7900 | 0 | 0 | Project on Hold per DA per 6/16/2020 Email
IF | 6 | BA-1797 | Project On Hold Design Services | Informal Projects | Business Services AVC | CRI Deck 1 | CRI DECK FFA LIGHTING REPLACEMENT | CRI DECK FFA LIGHTING REPLACEMENT, replace top level light fixtures with LED type units in place of the metal halite. | 2019-02-14 09:31 | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | 19-0162 | LOVE, DAVID (dflove) | 6800 | 0 | 0 | 07/07/2020 -Project on hold while Customer determines if they have other options.
IF | 6 | BA-1913 | Project On Hold FAM | Informal Projects | Safety and Security | Campus | CAMPUS SIREN UPGRADE "ALERTUS" | Safety & Security - Campus Siren upgrade - "Alertus" | 2020-01-31 11:09 | HILL, MICHELLE (mphilipp) | BARNETT, DENISE (dbarne33) | 20-0162 | LOVE, DAVID (dflove) | 0 | 0 | 0 | (7/28/2020) Sent scope and budget to customer. Customer taking S&B to lobby for funding.
IF | 6 | BA-1944 | Project On Hold Design Services | Informal Projects | Business Services AVC | Campus | STARBUCKS TRUCK PAD AND ELECTRICAL | STARBUCKS TRUCK Pad and Electrical, provide design to provide a prototypical pad off off the sidewalk for Starbucks Truck to pull over and sell during the day. Initial location is intended to be Smith but pad could be used anywhere - need pull off, | 2020-04-10 12:56 | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | 20-0221-I | SMITH, RYAN (rsmit341) | 26000 | 0 | 0 | Restarting project, considering a temporary option + storage instead of the permanent tower. Arranging meeting with band group.
IF | 6 | AA-1655 | Project On Hold Design Services | Informal Projects | Center City Campus | The Dubois Center | CCB OUTDOOR LIGHTING | Additional lighting needs to be added to the back garden area. Please assess the current lighting, make recommendations for additional and adequate lighting and provide an estimate of cost. | 2019-10-10 12:30 | DUPLESSIS, ANN (aduples1) | DUPLESSIS, ANN (aduples1) | 20-0079 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | (7/28/2020) On hold.
IF | 6 | BA-1889 | Project On Hold Design Services | Informal Projects | Safety and Security | Barnhardt Student Activity Center | FIRST PRIORITY CAMERA PROJECT PHASE 2 | Please assign to David Love - Phase 2 includes SAC, West Deck, Belk Gym, Cone, Colvard, Levine Hall, Cato, Prospector, McEniry, Auxiliary Services, Cameron, Bioinformatics, PORTAL, EPIC, Grigg, Duke, Motorsports, South Village Deck. (Approximately 2 | 2020-01-07 10:31 | HILL, MICHELLE (mphilipp) | BARNETT, DENISE (dbarne33) | 20-0115 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | 07/07/2020 -Project on Hold per email from Robbie Bell 02/24/20. Overall price ($9,988) was more then they expected. They will use the space as is for now to determine necessity of project.
IF | 0 |  | Created | Capital Projects | Facilities Management AVC | Campus | NEW CRI ENTRANCE ROAD | Create a new entrance off Hwy 29 | 2019-11-20 05:15 |  | CEALLAIGH, SHERRYL (sceallai) |  | KUGLER, BRIAN (bhkugler) | 1449300 | 1159589.44 | 0 | (7-28-20) Informal budget provided to Morgan Meehan 1-27-20. Pending approval to proceed. Placed on Hold April 27.
IF | 0 |  | Created | Capital Projects | Facilities Management AVC | Lot 5A | LOT 5A EXPANSION | re-alignment of lot 5A | 2019-11-19 14:10 |  | CEALLAIGH, SHERRYL (sceallai) |  | KUGLER, BRIAN (bhkugler) | 702248.85 | 742155 | 0 | 7/27/2020 - Project on hold per Customer request.
SA | 6 | SA-0408 | Project On Hold Design Services | Informal Projects | Cone Univ Center | Cone University Center | CONE SOUTH 3 MODERNIZATION | Cone Center - South 3: Upgrade and modernize South 3 level of Cone Center. Collaborate with Director and Associate Director to establish design options and features. | 2019-01-31 13:53 | MERCK, DONNA (dlmerck) | MERCK, DONNA (dlmerck) | 19-0147 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | (7-28-20) On hold - waiting for Morgan and Donna to provide scope of work
SA | 6 | SA-0450 | Project On Hold Design Services | Informal Projects | Student Union | Popp Martin Student Union | STUDENT UNION M101 ESPORTS LOUNGE | There is a space identified in the Student Union as a potential opportunity for an Esports Lounge. Need to determine if it is feasible in the space given the needs of the group. Need feasibility information by 1/28 and then will proceed further if ne | 2020-01-16 10:59 | MEEHAN, MORGAN (mmeeha11) | DALE, JEREMY (jdale8) | 20-0137 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | (7/28/2020) Project can be FF&E. Will work with customer to schedule. Customer holding for funding.
SA | 6 | SA-0462 | Project On Hold Design Services | Informal Projects | Student Activity Ctr and Venue Mgmt | Barnhardt Student Activity Center | SAC SALONS AND PREFUNCTION CARPET | Project is to gather estimates and designs on replacing the carpet inside and outside of the SAC Salons. | 2020-03-16 08:40 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | 20-0202-I | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 | (7/29/20) Project ready for order placement but on hold until funding received
SA | 6 | SA-0407 | Project On Hold Design Services | Informal Projects | Student Activity Ctr and Venue Mgmt | Halton-Wagner Tennis Complex | HALTON TENNIS COMPLEX LOWER HALL FLOODING | The lower hallways of the Halton Tennis Complex flood when there is heavy rain. Zone 1 has performed some modifications to the weep holes in the brick which has helped but we are still getting some flooding. The water drains towards the building inst | 2019-01-24 16:57 | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | 19-0134 | LANIER, LISA (llanier) | 34000 | 0 | 0 | (07.28.2020) Designer approved, will enter SCOPE AND BUDGET by 07.30.20.
SA | 6 | SA-0439 | Project On Hold Design Services | Informal Projects | Student Activity Ctr and Venue Mgmt | Barnhardt Student Activity Center | SAC 062 FITNESS ROOM RENOVATION | Fitness room renovation two include two spaces; one space is to remain a multipurpose room for events and the other space is to be converted into offices and storage space. Would like to keep as much of original hardwood floor as possible. | 2019-10-09 09:37 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | 20-0070 | LINGER, JOSHUA (jlinger2) | 0 | 0 | 0 | 07/07/2020 - project on hold due to cost considerations
SA | 6 | SA-0441 | Project On Hold Design Services | Informal Projects | University Recreation | Belk Gymnasium | BELK GYM 127 RECONFIGURE | Adding a door and wall to create a designated space to be used after UREC moves from Belk Gym to UREC building. Separating COR10 from 127 | 2019-10-16 13:31 | BELL, ROBERT (rbell16) | BARRETT, LACRISSA (lbarre11) | 20-0074 | LINGER, JOSHUA (jlinger2) | 9987.5 | 0 |  | ON HOLD
SA | 6 | SA-0454 | Project On Hold Design Services | Informal Projects | Housing and Residence Life | Witherspoon | WITHERSPOON CABINET & COUNTERTOP REPLACEMENT | Witherspoon Hall.. We want to replace the countertops and cabinets in the kitchens in similar configuration to what's currently in the apartments. ..per Alan Hinton 757-692-9020 | 2020-02-11 15:47 | FOUST, KATHY (kfoust3) | BUNKER, DEBRA (dbunker) | 20-0173 | LINGER, JOSHUA (jlinger2) | 353194.69 | 0 | 0 | 8/19/2020 : On hold. Project not funded.
SA | 6 | SA-0388 | Project On Hold Design Services | Informal Projects | Student Activity Ctr and Venue Mgmt | Barnhardt Student Activity Center | SAC ARENA BB & CURTAIN - LOW VOLTAGE | Change existing retractable basketball goals and mechanical partition curtain systems in Halton arena from 120v to low voltage. | 2018-07-26 14:21 | MOON, STUART (sgmoon) | BARNES, TRENT (tbarne21) | 19-0038 | SPATARO, EVAMARIE (espataro) | 0 | 0 |  | Commissioning and punch list work continues. Continuing with exterior pool work, Testing & Balancing, commissioning, punch list inspections, and corrective work. T&B approx. 95% - 98% complete. Commissioning is approx. 85% complete as of 6/2/20. GC is focusing on working through JCI’s punch list and items discovered during partial “System Integration” by Platinum (FIS consultant). Beneficial Occupancy was granted December 10, 2019 for interior only. Grand Opening was January 8, 2020. Landscaping punch list inspection occurred January 4, 2020. Designer completed interior punch list inspection 3/6/20. Underground Detention System - designer and university inspection occurred 4/15/20. Designer needs to submit documents to the city to obtain a permit. University will pay for the permit. Indoor pool drained 3-18-20 for punch list work. Work to complete 4/1/20. Inspection occurred 4-7-20. Pool full 4-19-20. Mock-up of outdoor pool deck finish reviewed 4-15-20 (needs redo). Commissioning is finally seeing light at the end of the tunnel, and the goal is to wrap up by the end of May (not achieved). 95% complete as of 6-9-20. T&B is 99.9% complete Complete closeout - targeting end of June. Exterior Punch list review occurred 5-26-20 Punch list inspection for the outdoor pool and pool bldg occurred on 7/10/20. Beneficial Occupancy granted by SCO on 7-23-20 for outdoor pool and pool bldg.
SA | 6 | SA-0424 | Project On Hold Design Services | Informal Projects | Student Union | Popp Martin Student Union | STUDENT UNION LED LIGHTING RETROFIT | Student Union - Entire BuildingStudent Union wants to increase sustainability by reducing energy consumption and decrease annual maintenance cost for replacement fluorescent lights by retrofitting lighting to LED. This project aligns with UNC policy | 2019-06-24 09:37 | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | 20-0022 | SPATARO, EVAMARIE (espataro) | 43000 | 0 |  | (8/18/2020) Showed rough estimate to customer, customer needs to research funding options
SA | 6 | SA-0440 | Project On Hold Design Services | Informal Projects | Student Activity Ctr and Venue Mgmt | Barnhardt Student Activity Center | SAC 334A-E SALONS LIGHTING UPDATE | Replace light fixtures, and update control system to accommodate new lighting. | 2019-10-09 09:42 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | 20-0071 | SPATARO, EVAMARIE (espataro) | 0 | 0 |  | 8/19/2020: Customer has been asked to provide additional scope information but not yet supplied it. Project is not yet funded.
SA | 6 | SA-0455 | Project On Hold Design Services | Informal Projects | Student Union | Popp Martin Student Union | STUDENT UNION 340 POWER UPGRADE | Student Union would like to add additional power to the multi purpose room 340. We are looking at 100A, 3 phase, 5 wire, 120/208V. Requesting Eva Spataro on this project | 2020-02-18 16:03 | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | 20-0186 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | 08-05-20. No change. Budget review. Customer said to hold.
SA | 6 | SA-0442 | Project On Hold Design Services | Informal Projects | Cone Univ Center | Belk Gymnasium | BELK GYM 120 VENTURE MOVE | Venture has been approved to move from Cone to Belk gym. Within this project includes: coordinating a move of the staff, office furnishing needs, space renovations in Belk for storage space. As this project is related to project SA-0441 it could be | 2019-10-24 14:09 | MEEHAN, MORGAN (mmeeha11) | DALE, JEREMY (jdale8) | 20-0080 | WELLS, ALICIA (awells43) | 160000 | 160000 | 170609.26 | 9/30/2020 - Closing out project per Customer request.
SA | 2 | SA-0457 | Req Scope & Budget Review | Informal Projects | Health Services | Student Health Center | SHC OUTDOOR BUILDING SIGNS | Project request for outdoor building signage. | 2020-02-19 08:43 | FLORES, CLAUDIA (cflores3) | BARRETT, LACRISSA (lbarre11) | 20-0218-I | TERRY, STEPHEN (slterry) | 13500 | 0 | 0 | Dependent on two other Colvard projects, no action until those projects move forward and have a clear schedule and plan.
SA | 2 | SA-0372 | Construction | Informal Projects | Cone Univ Center | Cone University Center | CONE 382 RENOVATION FOR OFSL | Review and provide drawing for update to OFSL Suite (382) in Cone Center. Would like to maximize space efficiency. | 2018-03-14 12:00 | MEEHAN, MORGAN (mmeeha11) | HARRIS, MELODY (mhharris) | 18-0184 | HILL, CAROLINE (cmhill2) | 23700 | 172195.35 | 0 | Consultants / Contractors: * Consultant: TBD * Contractors: TBD Milestones: * Project currently on Hold Pending Funding and Approval * 04/01/2020: Designer Selection Meeting Held, Designer Tentative Selected (Currently Awaiting Approval To Award) Notes / Issues / Concerns: * None at this time.
SA | 0 | SA-0470 | Construction | Informal Projects | Health Services | Student Health Center | SHC 293 CRC RELOCATION | Renovating SHC 293 for CRC program in phases. This would be phase one to include: General construction: soundproof between 293 and AVC, Carpet, Paint, power by window, card reader relocated, move services and ITS data drops. | 2020-08-06 08:31 | BARRETT, LACRISSA (lbarre11) | BARRETT, LACRISSA (lbarre11) | 21-0019-I | CAUDLE, AMANDA (afelock) | 20000 | 20000 | 21-0048-I |  | 12/14/2020 - Scope and Budget sent to Customers on 11/30/2020.
| 0 |  | Created | Capital Projects | FM Architectural/Engineering | McColl-Richardson Field | Football Game Field Replacement |  | 2020-06-15 |  | SPEASE, DARIN (dspease) |  | LANIER, LISA (llanier) | 0 | 0 | 0 | PROJECT NOTES UPDATED: * 01/11/21 CONSULTANTS / CONTRACTORS: * Consultant: Dewberry * Contractors: TBD * Project Delivery Method: Single Prime * Tentative Construction Duration: TBD MILESTONES: * Project Currently On Hold pending discussion with Parking and Transportation * COMPLETE_ SCO Approval To Bid of 90% Construction Documents & Specifications * Project currently ready to bid contingent on East Village Infrastructure (EVI) Project moving forward. * Tentative Timeline for Advertising for Bid to Contractor Award - 8 Weeks * Tentative Timeline for Construction Start to Construction Completion - 120 Days NOTES / ISSUES / CONCERNS: * Project construction contingent on (EVI) bidding within budget. * Lot 5A Add Alternates and final project scope contingent on Add Alternates selected as part of (EVI).
| 0 | 12165 | Created | Capital Projects | Academic Affairs VC | Campus | STUDENT HEALTH & WELLNESS | UNC Charlotte currently has a significant shortage of student health and wellness activity space. A recent study by Brailsford and Dunleavy showed the campus has well under half of the facility space dedicated to student health and wellness by other | 2011-06-02 09:46 | RAJA, JAYARAMAN (jraja) | CEALLAIGH, SHERRYL (sceallai) |  | NEILSON, JOHN (jneilson) | 66000000 | 63634047.1 | 2638.6 | (1-12-21) Carpet in hand. Project on hold until March per Beau Dooley.
IF | 0 |  | Created | Capital Projects | Facilities Management AVC | Campus | NEW CRI ENTRANCE ROAD | Create a new entrance off Hwy 29 | 2019-11-20 05:15 |  | CEALLAIGH, SHERRYL (sceallai) |  | KUGLER, BRIAN (bhkugler) | 1449300 | 1159589.44 | 0 | PROJECT NOTES UPDATED: * 01/11/21 CONSULTANTS / CONTRACTORS: * Consultant: TBD * Contractors: TBD * Project Delivery Method: TBD * Tentative Construction Duration: TBD MILESTONES: --- Project currently on Hold Pending Funding and Approval --- Designer Selection Meeting Held, Designer Tentative Selected --- Brian Kugler sending signed letter to designers notifying project will not move forward at this time.
IF | 0 |  | Created | Capital Projects | FM Architectural/Engineering | Campus | CID 2-EAST VILLAGE INFRASTRUCTURE | East Village infrastructure including Martin Village Road re-alignment, Van Landingham bridge, lighting, telelcom, storm, sanitary and the electrical extension to the campus substation. Includes a traffic signal at John Kirk Drive. | 2013-10-08 08:26 | GILBERT, CHRISTOPHER (cgilbert) | CEALLAIGH, SHERRYL (sceallai) |  | KUGLER, BRIAN (bhkugler) | 4135056.7 | 7410172.79 | 0 | 01/11/21 CONSULTANTS / CONTRACTORS: * Consultant: Kimley Horne * Contractors: CM@R Sheil Sexton * Project Delivery Method: CM@Risk * Tentative Construction Duration: TBD MILESTONES: * Project currently placed on hold 01/04/21 by University Administration. *30 Day Outlook: To Be Complete By 02/11/21 --- Final Billing for Design to Kimley Horne --- Negotiate Additional Pre-Construction Services --- Office notice of Project Suspension to NCDOT * 60 Day Outlook: To Be Complete By 03/11/21 --- Final Payment to CM@Risk for Final Construction Services NOTES / ISSUES / CONCERNS: * Review Bid Numbers and Determine Next Steps For Award of EVI and construction execution. * Need to receive documentation of Supplemental Agreement to secure Funding from NCDOT (Pending Contract Language Discussion if Project is approved to move forward $500,000.00 in funding currently unconfirmed from NCDOT.) Project construction contingent on (EVI) bidding within budget in order to move forward. * Lot 5A Add Alternates and final project scope contingent on Add Alternates selected as part of (EVI). Due to renegotiation of PGMP to 10% higher GMP Sheil Sexton GMP may come in higher then originally projected causing UNCC to have to decide to go in another direction and hard bid the project. If Martin Hall Village Connector is not accepted we have agreed with CDOT to put it in our UNCC Capital Improvement Plan. * Police & ITS Duct Bank may be funded and installed concurrently with EVI as a informal project. If approved, coordination will need to be discussed and executed.
IF | 0 |  | Created | Capital Projects | Facilities Management AVC | Lot 5A | LOT 5A | re-alignment of lot 5A | 2019-11-19 14:10 | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | KUGLER, BRIAN (bhkugler) |  |  | PROJECT NOTES UPDATED: * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultant: Dewberry * Contractors: TBD * Project Delivery Method: Single Prime * Tentative Construction Duration: TBD (ON HOLD) MILESTONES: * Project Currently On Hold pending discussion with Parking and Transportation * COMPLETE_ SCO Approval To Bid of 90% Construction Documents & Specifications * Project currently ready to bid contingent on East Village Infrastructure (EVI) Project moving forward. * Tentative Timeline for Advertising for Bid to Contractor Award - 8 Weeks * Tentative Timeline for Construction Start to Construction Completion - 120 Days NOTES / ISSUES / CONCERNS: * Project construction contingent on (EVI) bidding within budget. * Lot 5A Add Alternates and final project scope contingent on Add Alternates selected as part of (EVI).
BA | 0 | BA-1971 | Scope & Budget Requested | Informal Projects | Business Services AVC | Popp Martin Student Union | STUDENT UNION 137-138 STORAGE ROOM MODIFICATIONS | SU Storage Room Modifications, modify 137 and 138 to remove demizing wall. Relocate some metal shelving. Need large item storage and pallet drop area. Provide rolling plastic shelving typical of our dry storage areas to provide more storage within | 2020-07-13 13:57 | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) |  | CAUDLE, AMANDA (afelock) | CAUDLE, AMANDA (afelock) | 21-0012-I |  | (2-1-21) Layouts and budget pricing provided to Drew Averitt on 9/21/20. Pending his approval to proceed.
IF | 0 | BA-1981 | Approved Scope & Budget FAM | Informal Projects | Facilities Informal Projects | Campus | FPFM, FOPS SHELTER & PICNIC TABLES | FPFM, FOPS SHELTER & PICNIC TABLES: Build new covered structure and add picnic tables for outdoor seating and event space at FOPS. Assign to Shawn Kelly. | 2020-09-28 11:46 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) |  | FAKE, WILLIAM (wmfake) | KELLY, SHAWN (skelly64) | 21-0032-I |  | PROJECT NOTES UPDATED: * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultants: TBD * Contractor: TBD * Project Delivery Method: TBD * Tentative Construction Timeline: TBD MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Stakeholder meeting held. --- Currently preparing shelter options for stakeholder review. NOTES / ISSUES / CONCERNS: * Project has no funding at this time.