## INFORMAL & FORMAL PROJECTS
Project Priority List | [8 empty] | 2021-08-09 | [7 empty] | Informal and Formal Projects
Unit | Campus Priority | Control Code | Project Status Block | Project Type | Department Code | Sub Department Name | Bldg Code | Building Name | Project Request Name | Project Description | Date Created | Project Account Manager | Project Customer | Financial Account Manager | Scope & Budget Manager | Project Number | Project Coordinator | Scope & Budget | Approved Project Total | Amount Billed | Estimated Design Complete | Notes
| 0 |  | Created | Capital Projects | 14010 | Facilities Informal Projects | 0004 | Atkins | Atkins G26 - Cafe Study |  | 2021-05-19 |  | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) |  | 21-0163-F |  | 0 | 0 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0102 | Softball Indoor Training Facility | Softball Indoor Training Addition |  | 2021-05-03 |  | FERGUSON, JAMES (jcfergus) | SPEASE, DARIN (dspease) |  | 21-0144-F | CEALLAIGH, SHERRYL (sceallai) | 0 | 0 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 2137 | Belk Plaza | Remembrance Memorial |  | 2021-03-19 |  | FRERE, ELIZABETH (efrere) | WIDMAIER, CLEO (cswidmai) |  | 21-0109-F |  | 0 | 0 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0068 | Bioinformatics | Bioinformatics BSL-3 Lab MEP |  | 2021-03-18 |  | MAYS, LAWRENCE (lemays) | CEALLAIGH, SHERRYL (sceallai) |  | 21-0107-F | CEALLAIGH, SHERRYL (sceallai) | 0 | 0 | 0
| 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0055 | Facilities Management & Police & Public Safety | TESTING THE SYSTEM - SHERRY | looking for errors I get when I enter a project in the CRDM | 2021-01-12 07:18 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | CEALLAIGH, SHERRYL (sceallai) | 0 | 1649501 | 0
| 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0069 | Popp Martin Student Union | STUDENT UNION - CROWN COMMONS RENOVATION | The Student Union was completed in 2009. The 9300 SF "Crown Commons" Dining Facility is a highly trafficked area utilized by thousand of patron daily. By the time this project occurs, the facility will be 10 years old and will need renovations includ | 2016-12-14 11:25 |  |  | PAQUETTE, NOELLA (njpaquet) |  |  |  | 0 | 0 | 0
AA | 0 | AA-1673 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0004 | Atkins | ATKINS 146, 149 CNT. FOR GRAD.LIFE MOVE FROM CONE | Atkins - 146, 148A, 148B, Suite 149 - Move Center for ¦Graduate Life from Cone 2nd floor to Atkins 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 43844.4145 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0125 | SISCO, ASHLEY (asisco1) | 180000 | 180000 | 1902-06-15 23:31 | 44378 | (8/02/21) Met with customer 7/15 to review scope of work, discuss finishes, furniture, and walk space. Working on getting revised quotes and updated finish plans for the space.
AA | 0 | AA-1736 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0004 | Atkins | ATKINS MULTI-FLOOR PAINTING | Provide carpet and paint on portions of the 2nd floor and the 3rd floor to update areas where new furniture will be provided to create socially distanced student study space. | 44217.5161 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 21-0066-I | WELLS, ALICIA (awells43) | 408616 | 79026.64 | 2072-12-15 09:07 | 44316 | (7/26/21) Final painting scope complete. Wtg on Donia to confirm project close out.
AA | 0 | AA-1742 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0004 | Atkins | ATKINS LOADING DOCK CANOPY | To keep books protected during loading and unloading into van that travels to and from remote storage, Atkins loading dock needs to be covered with a canopy. | 44279.555 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 21-0111-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.26.21) Received proposal from Bennett Pless with two options. Met on site with structural engineer. Getting proposals from two canopy manufacturers. Has to be complete 09.15.21
AA | 0 |  | Created | Capital Projects | 15100 | Academic Affairs VC | 0068 | Bioinformatics | BIOINFORMATICS 4TH FLOOR BUILD-OUT | Build-out 4th floor to provide interdisciplinary research space to support UNC Charlotte's need for labs and faculty offices. | 43255.4394 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 10500000 | 9376613.33 | 0 |  | "Consultants Designer - LS3P Lab Planner - RFD CM@R - Balfour Beatty Milestone dates and activities Balfour Beatty selected as CMR, precon contract approved by SCO and sent to Balfour for signature April 30, 2020 Alternates discussed March 16, 2020 CMR submitted SD/DD phase cost estimate on April 8, 2020 SD/DD reconciled cost estimate reviewed on April 16, 2020, within budget and approved to move forward without any revisions Design contract routed for University signatures on April 13, 2020 Project taken off hold, restarted design process after Design contract was executed on 6/11/20. CD Kickoff Meeting completed on July 20, 2020 SCO approved SD/DD phase submittal on May 21, 2020 Issues to be addressed Next CD workshop meeting will be late August 2020 BSL3 valve funding issue still on-going - design and construction to be an informal project, trying to locate funding for total project total +/-$400,000 "
AA | 0 | BA-2085 | Scope & Budget Requested | Informal Projects | 14010 | Facilities Informal Projects | 0068 | Bioinformatics | BIOINFORMATICS 4TH FLOOR FF&E | BIOINFORMATICS 4TH FLOOR FF&E: Project is tied to the Bioinformatics Capital Renovation project and will utilize capital funding. Scope and Budget will be entered once Alicia Wells confirms the furniture scope with the customer. | 44397.3825 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | CEALLAIGH, SHERRYL (sceallai) | WELLS, ALICIA (awells43) | 22-0004-I | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (7/26/21) Initial Furniture budget created based off information provided by Donia. Need to send revised layout information for PMC for furniture layout & customer meeting.
AA | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0042 | Cameron Hall | CAMERON SECOND FLOOR RENOVATION | The second floor of Cameron will be renovated to provide space for chemistry research labs. | 43619.5513 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | FRERE, ELIZABETH (efrere) | 1950000 | 18306959 | 0 |  | Schematic Design Complete ON HOLD pending funding
AA | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | SCIENCE BUILDING | The Science Building will provide important undergraduate class laboratory and interdisciplinary research space for UNC Charlotte. Many of UNC Charlottes buildings were constructed before doctoral instruction and, in some cases, before master leveli | 40696.3957 | RAJA, JAYARAMAN (jraja) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 90000000 | 100222514.93 | 0 |  | Clark Nexsen - Designer Balfour Beatty - CM @ Risk Jenkins Peer - Feature Wall Design Consultant CPL - Lab Equipment and Moves Consultant Milestone Dates and Activities: 11/09/2020: RUP 5 BO received 10/29/2020. 11/10/2020: Data Center BO received 11/10/2020. 06/21/2021: Landscaping review held with LandDesign; many items rejected and to be addressed. Cx underway and 25%complete. Feature wall PO issued; install 2nd week of July. Architect's punch list underway. Owner training underway. Fume hood testing complete. Elevator inspections complete. Electrical inspections complete until final BO walk. EOR supervised complete fire controls and systems testing. FFE, AISLE, OneIT, Academic Affairs purchasing underway. FFE installation and moves schedule updates underway upon vendor confirmations of PO's and lead times; Equipment delivery schedule coordination underway. Issues to be resolved: BO projected first week of July with Cx items ongoing past BO. March 26, 2021 contract completion. Balfour Beatty has been notified that liquidated damages will be assessed. Anticipated weather days April 9, 2021 contract completion. Covid impact days being considered by SCO.
AA | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | ACADEMIC COMPLEX RENOVATION | Facilities conditions improvements and renovation over Garinger, Barnard, Denny, Macy and Winningham. | 41843.4486 | MANDERINO, LAUREL (lmanderi) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 3702000 | 21180353.17 | 0 |  | Milestones: * 10/30/30: Tentative construction completion of Garinger Chiller * Project closeout pending the completion of the Garinger Chiller Installation. January 15th Notes / Issues / Concerns: * Decision on brick color for surrounding Chiller Screen Wall holding up progress on completion of masonry.
AA | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | INFORMATION TECHNOLOGY INFRASTRUCTURE UPGRADES | IT Infrastructure Upgrades in Rowe, Storrs and Reese | 43391.46 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 3800050.24 | 3436934.71 | 0 |  | Consultants / Contractors: Consultants: Optima Engineering Contractors: Shiel Sexton CM@R Milestones: * Project construction is behind scheduled 198 day delivery schedule. Cable test should start week of March 8th. * Final SCO Inspection anticipated March 15th. Notes / Issues / Concerns: SSC hired supplemental cabling contractors to help AJT.
AA | 0 | AA-1719 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | STORRS, ROBINSON & ROWE ARTS QUAD | Quad between Storrs, Robinson, and Rowe - The arts quad project is intended to provide canopied space for outdoor art and architecture teaching. Tented structures will cover areas of the quad and the recessed yard in front of Storrs. Amenities will | 44013.5738 | SCHAUBLE, DONIA (dcooke) | MULLER, BROOK (bmuller7) | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 21-0001-I | FRERE, ELIZABETH (efrere) | 50000 | 49720 | 1917-12-06 | 44196 | Met with the customer to further develop new scope, they will be taking it back to their internal units to review and then get back to us on how they would like to proceed. Watson Tate agreement includes SD/DD phase design, CD phase will not commence until funding can be identified. Revised scope to focus more on overall quad and less on the engineering of a structure with canopy.
AA | 0 | AA-1754 | Req Design Estimate Review | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | GREENHOUSE PHASE 2 | Greenhouse structure kit, redundant cooling and exhaust, plant benches, irrigation, and grow lights. | 44369.1212 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 21-0173-I | PATEL, NAVINKUMAR (npatel24) | 225212 | 129000 | 0 | 44411 | (07.19.21) Contracts approved, GC updating construction schedule. Mobilization tentative 7.29.21. Project closeout is October 1.
AA | 0 | AA-1744 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0048 | Cato Hall | CATO ENROLLMENT MANAGEMENT RENOVATION | Renovations to former Enrollment Management Space on the first floor of Cato to provide ability to share space with Assessment & Accreditation. | 44279.6521 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 21-0114-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.26.21) Momentum providing a proposal for renovation. Donia is reviewing this with Jay for approval. To be completed by 12.01.21.
AA | 0 | AA-1702 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0063 | College of Health and Human Services | CHHS VIRTUAL CADAVER LAB | CHHS - Virtual Cadaver Lab | 43906.3616 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0205-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (07.26.21) Had a kick off meeting for scope of work and working with AISLE and ITS for design of interior space. A coordination meeting is set for 07.26.21. Completion of work Spring 2022.
AA | 1 | AA-1683 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1017-1018 ACTIVE LEARNING CLASSROOM | Colvard - Suite 1017 and 1018A - Create new Active Learning Classroom.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 43844.4633 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 20-0132 | FRERE, ELIZABETH (efrere) | 0 | 0 | 0 |  | Dependent on two other Colvard projects, no action until those projects move forward and have a clear schedule and plan.
AA | 0 | AA-1713 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 4077-4085 FACULTY START UP | Reconfigure former spaces 4077, 4078, 4080, 4081, 4084, and 4085 into 3 spaces needed for Psychology research. This is part of a new faculty start up. | 43995.549 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0249-I | SISCO, ASHLEY (asisco1) | 150000 | 150000 | 2174-12-22 12:43 | 44377 | (8/02/21) Wrapping up final billing.
AA | 1 | AA-1440 | Scope & Budget Requested | Informal Projects | 15100 | Academic Affairs VC | 0057 | Duke Centennial Hall | DUKE 349 RENOVATIONS | Convert faculty lounge to office spaceContact Kevin Scott Smith for details 7-8350 | 42985.5268 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 18-0049 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 7/27/2021: On hold. Project not funded.
AA | 0 | AA-1755 | Construction | Informal Projects | 23700 | Center for Precision Metrology | 0057 | Duke Centennial Hall | DUKE 148A UPGRADE SCHMID LAB | Duke 148A Upgrade Schmid Lab. Quotation & Design plans needed for upgrade of lab space to facilitate the Hydroforming machine install. Electrical, entry door enlarged and potentially air conditioning ductwork upgrade in Dr. Schmid's lab. | 44393.3704 | CHASTAIN, JENNIFER (jchasta4) | SCHMID, STEVEN (sschmi16) | CHASTAIN, JENNIFER (jchasta4) | CAUDLE, AMANDA (afelock) | 21-0176-I | CAUDLE, AMANDA (afelock) | 5000 | 5000 | 0 | 44393 | (8-2-21) Purchase order issued to CMTA 7/19/21 to start design.
AA | 0 | AA-1739 | Construction | Informal Projects | 22150 | EPIC | 0072 | EPIC Building | EPIC 1126 RENOVATION DESIGN | Provide architectural design for up fitting EPIC 1126 into a functional space with personnel space (office environment) and shared work space for various types of projects. | 44235.7253 | MOOSE, ROBIN (rmoose2) | MOOSE, ROBIN (rmoose2) | MOOSE, ROBIN (rmoose2) | PATEL, NAVINKUMAR (npatel24) | 21-0073-I | PATEL, NAVINKUMAR (npatel24) | 195165 | 187889 | 2404-10-27 00:29 | 44323 | (07.26.21) The department has added extra funding to complete the project. Furniture is on order and will be delivered August 12. Project has to be complete 08.18.21.
AA | 0 | AA-1749 | Approved-Design & Estimate FAM | Informal Projects | 15100 | Academic Affairs VC | 0072 | EPIC Building | EPIC 3378 LAB 480V DISCONNECT-FLOOR LOAD | EPIC 3378 Lab 480V Disconnect-Floor Load: Dr. Shen-En Chen lab in EPIC 3378 needs to receive a 480V disconnect to support new equipment needed for his grant research. He also needs confirmation that the floor in his lab can support an equipment load | 44314.8708 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | BROWN, LORI (lmorri25) | BOAL, JOHN (jboal1) | 21-0143-I | BOAL, JOHN (jboal1) | 4600 | 2600 | 0 | 44393 | 7/27/2021: Awaiting confirmation of funding availability from customer.
AA | 1 | AA-1446 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL FIRST FLOOR LOBBY RENOVATION | Plans for renovation of Fretwell first floor (open public space).Contact Shawn Long for details 7-0075 | 42985.6292 | SCHAUBLE, DONIA (dcooke) | LONG, SHAWN (sdlong) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 18-0060D&C | SISCO, ASHLEY (asisco1) | 34000 | 368626 | 1991-08-25 | 43325 | (8/02/21) PO's have been issued for all work. Contractor to start week of 8/2/21. Furniture to be install 8/9.
AA | 0 | BA-2059 | Scope & Budget Requested | Informal Projects | 13930 | FM Architectural/Engineering | 0095 | Gage Undergraduate Admissions Center | GAGE PLAQUE TO INDIGENOUS PEOPLE'S DAY | Shortened version of UNC Charlotte's formal recognition on Monday, Oct. 12, 2020, as Indigenous Peoples' Day at the University. | 44313.6003 | FRERE, ELIZABETH (efrere) | KIRBY, CLAIRE (ckirby) | BASEY, MELODIE (mbasey) | TERRY, STEPHEN (slterry) | 21-0141-I | TERRY, STEPHEN (slterry) | 0 | 0 | 0 |  | 06/23/21 - Waiting on PFranz for updated location and type to create a scope and budget.
AA | 6 | AA-1414 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD BIOLOGY CAMERA REPLACEMENT | Woodward Biology Camera Replacement | 42871.5599 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 18-0010 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Placed on hold 11-21-17.
AA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0001 | Kennedy | KENNEDY 2ND FLOOR RENOVATION | Renovate the 2nd floor of Kennedy | 44215.3969 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | CAUDLE, AMANDA (afelock) | 0 | 431020 | 0 |  | (8-2-21) Consultants: Meeting 7/27 to select designer.
AA | 6 | AA-1690 | Construction | Informal Projects | 24200 | OneIT-CIO | 0001 | Kennedy | KENNEDY 320 RECONFIGURATION | We would like to discuss options for how Kennedy 320 can adjust for growth, specifically using 2 - 4 areas of existing space. Sandra Soriano (78987) is the contact for this request. | 43868.6137 | VITALLO, JUDY (jvitallo) |  | VITALLO, JUDY (jvitallo) | HILL, CAROLINE (cmhill2) | 20-0170 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | Project is 100% completed and can be closed out.
AA | 6 | AA-1531 | Project On Hold Design Services | Informal Projects | 24400 | Research & Economic Dev. VC | 0080 | PORTAL | PORTAL 232 AND 242 ENHANCEMENTS | PORTAL 322: 1) add color, texture, or paneling to the walls 2) move the UNCC sign in the space to different location 3) upgrade the photos and picture frames in the roomPORTAL 242: 1) add wall covering to wall outside of 242 and hang pictures like th | 43242.4457 | MATEEN, ALI (amateen) | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) | HILL, CAROLINE (cmhill2) | 19-0001 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 3/30/2021 - Compiling updated pricing for Customers.
AA | 0 | AA-1746 | Construction | Informal Projects | 17800 | Art & Art History | 0002 | Macy | MACY 107 DIGITAL MEDIA LAB | Macy 107- AAH Digital Media Lab. M107 turned into computer lab. Relocate Illustration to Winningham. Macy: 20 iMac stations + work tables. Exists: 4 IT tables (channels for wire/power). More ports & power for Macy. Existing ports (10 unused), relocat | 44279.7103 | SCHAUBLE, DONIA (dcooke) | KAPERONIS, GEORGE (gkaperon) | SOFSKY, DONNA (dsofsky) | BOAL, JOHN (jboal1) | 21-0116-I | BOAL, JOHN (jboal1) | 40014 | 40014 | 1990-02-12 21:07 | 44358 | 7/27/2021; Connection of tables to IT and power at wall have been completed. Computers have not been installed by the customer. After installation of computers final connection to power and IT will be done.
AA | 6 | AA-1610 | Project On Hold Design Services | Informal Projects | 19400 | College of Business | 0035 | Friday | FRIDAY 391 RENOVATION | We are looking at splitting the room in two similar to 388/393.It may not be an exact half split though.We want one side to be a small PhD classroom and the other side to be a student bullpen area similar to 388/393.Classroom half needs to seat 20 if | 43565.5582 | CARMICHAEL, TIMOTHY (twcarmic) | CARMICHAEL, TIMOTHY (twcarmic) | TWEED, DANA (dtweed1) | HILL, CAROLINE (cmhill2) | 19-0204 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 10/26/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1616 | Project On Hold Design Services | Informal Projects | 19400 | College of Business | 0035 | Friday | FRIDAY 242 CONFERENCE ROOM | I need a cost estimate to convert Friday 242 into a conference room. Move 1 display to the end wall. Remove the remaining 5 displays (Belk College Technology Team will take the 5 that get removed). Patch and paint walls. Core drill to connect lapto | 43577.5661 | CARMICHAEL, TIMOTHY (twcarmic) | CARMICHAEL, TIMOTHY (twcarmic) | SANCHEZ, STEPHANIE (ssanch12) | HILL, CAROLINE (cmhill2) | 19-0211 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 10/26/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1629 | Project On Hold Design Services | Informal Projects | 24400 | Research & Economic Dev. VC | 0080 | PORTAL | PORTAL INTERIOR GRAPHIC SIGNAGE | We want signage to raise the profile of the Office of Tech Transfer, SBTDC, Ventureprise, 49er Foundry, and the PORTAL Solutions Desk. Signage needs to large enough to be seen from across the lobby, attractive, and professional. All of these offices | 43661.5994 | MATEEN, ALI (amateen) |  | KEENE, PATRICIA (pgkeene) | TERRY, STEPHEN (slterry) | 20-0032 | TERRY, STEPHEN (slterry) | 10800 | 0 | 0 |  | 06/23/21. No change. Budget review. Customer said to hold.
AA | 6 | AA-1632 | Project On Hold Design Services | Informal Projects | 17200 | Biological Sciences | 0056 | Woodward Hall | WOODWARD 461 EMERGENCY CIRCUIT | Woodward Hall - 461 - Add emergency circuit to lab (461). Almost a mirror project to the recently completed 361 | 43685.6242 | GRAY, DAVID (dlgray) |  | GRAY, DAVID (dlgray) | CAUDLE, AMANDA (afelock) | 20-0044 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Project on hold.
AA | 6 | AA-1638 | Project On Hold Design Services | Informal Projects | 15175 | The Dubois Center | 0073 | The Dubois Center | CCB 1106 EXPANSION | Explore the possibility of remodeling and expanding 1106 at Center City. Remove wooden side walls and wall between 1106 and the storage areas behind it to make the room larger. | 43696.5704 | DUPLESSIS, ANN (aduples1) |  | DUPLESSIS, ANN (aduples1) | CAUDLE, AMANDA (afelock) | 20-0051 | CAUDLE, AMANDA (afelock) | 13000 | 0 | 0 |  | (8-2-21) Routed scope and budget for design 12-4-19. Pending customer approval to proceed. Placed on hold 6-26-20.
IF | 6 | AA-1655 | Project On Hold Design Services | Informal Projects | 15175 | The Dubois Center | 0073 | The Dubois Center | CCB OUTDOOR LIGHTING | Additional lighting needs to be added to the back garden area. Please assess the current lighting, make recommendations for additional and adequate lighting and provide an estimate of cost. | 43748.5205 | DUPLESSIS, ANN (aduples1) |  | DUPLESSIS, ANN (aduples1) | KELLY, SHAWN (skelly64) | 20-0079 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 9/22/2020: Customer received estimates - NOTES / ISSUES / CONCERNS: * Awaiting decision to move forward. * Project currently on hold.
AA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0020 | McEniry | MCENIRY HVAC UPGRADE | Replace HVAC in McEniry | 43788.6291 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | BOAL, JOHN (jboal1) | 7336875 | 9245352.76 | 0 |  | Consultants: Architect: Jenkins Peer Mechanical Engineer: CMTA, Inc. (formally McCracken and Lopez) CM@Risk: New Atlantic Contracting Bid date for subcontractors was August 19. Project bid well under budget. Floors 2, 3 and 4 are under construction now. Completion of these floors is scheduled for May 15. Construction of the first floor and basement are scheduled to begin May 15 and be completed August 15. Installation of a full building exhaust system has been recently added to the scope of work. Completion of that exhaust system is scheduled for November. Return of occupants to the building is still scheduled for mid August.
AA | 0 | AA-1660 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY 310 HYDROLOGY & BIOCHEMISTRY LAB | Renovation of space on the on the 3rd floor as a hydrology and biochemistry lab and renovation of a classroom space on the 2nd floor. | 43775.5209 | FAKE, WILLIAM (wmfake) |  | PAQUETTE, NOELLA (njpaquet) | BOAL, JOHN (jboal1) | 20-0084 | BOAL, JOHN (jboal1) | 35439 | 318169 | 2018-09-26 | 43980 | 7/27/2021. Construction underway. Completion scheduled for August 13.
AA | 6 | AA-1663 | Project On Hold Design Services | Informal Projects | 18050 | DPT Writing, Rhet, Digital Studies | 0042 | Cameron Hall | CAMERON WRITING PROGRAM 1ST FLOOR SIGNS | CAMERON WRITING PROGRAM 1ST & 2ND FLOOR SIGNS: Name changes needed to Department of Writing, Rhetoric and Digital Studies. Several signs throughout first and second floors need to reflect our new name. Please contact Denise Sabo 7-1902 | 43784.5735 | SABO, DENISE (dsabo1) |  | MULLIN, JOAN (jmulli40) | TERRY, STEPHEN (slterry) | 20-0089 | TERRY, STEPHEN (slterry) | 2900 | 0 | 0 |  | 06/23/21. No change. Budget review. Customer said to hold.
AA | 6 | AA-1668 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0058 | Grigg Hall | GRIGG 386 CLEAN ROOM MOVE FROM CAMERON | Grigg - 386A - Move portions of existing Cameron clean room to Grigg 386A . This will locate all campus clean room functions into Grigg.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 43844.3884 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0120 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (09.14.2020) Working with Wei Gao on scope for equipment moves Will engage designer once scope is detailed. Will follow up with Donia regarding design fee.
AA | 6 | AA-1669 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD 264, 275 KINESIOLOGY MOVE FROM CAMERON | Woodward - 264, 275, 276, 276AMove Kinesiology Research labs from Cameron 2nd floor to Woodward 2nd Floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 43844.3921 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0121 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (7/26/21) Project on hold
AA | 6 | AA-1670 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0017 | Belk Gymnasium | BELK GYM 024 KINESIOLOGY LAB | Belk Gym - 024 - Move human physiology research lab from Cameron 2nd floor to Belk Gym Ground floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 43844.3946 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0122 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 7/27/2021; Customer has been asked to provide additional scope information but not yet supplied it. Project is not yet funded.
AA | 6 | AA-1671 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1028 FADO MOVE FROM CAMERON | Colvard - 1028, 1028A, 1028B, 1028C, 1028D, 1028E, 1028F, 1028G, 1028H, 1028I - Relocate FADO from Cameron 2nd Floor to Colvard 1000 level.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 43844.4071 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0123 | WELLS, ALICIA (awells43) | 10000 | 10000 | 0 | 44012 | (7/26/21) Project on hold
AA | 6 | AA-1672 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0042 | Cameron Hall | CAMERON 174 MOSAIC MOVE FROM CAMERON | Cameron- Suite 174 - Relocate Mosaic from Cameron 2nd floor to Cameron 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 43844.4102 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0124 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (7/26/21) Project on hold
AA | 0 | AA-1661 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY 316 LANDSCAPE ECOLOGY LAB | Renovation of McEniry 316 and 313 for use as landscape ecology lab. | 43775.5218 | FAKE, WILLIAM (wmfake) |  | PAQUETTE, NOELLA (njpaquet) | BOAL, JOHN (jboal1) | 20-0085 | BOAL, JOHN (jboal1) | 35000 | 394033 | 1999-02-04 00:14 | 43981 | 7/27/2021: Construction underway. Completion by August 13.
AA | 6 | AA-1674 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0072 | EPIC Building | EPIC 1231 FURNITURE | EPIC - 1231 - Furniture Project - Exact scope still needs to be determined.Do not contact end users directly. Set up first meeting with Donia Schauble and Alicia Wells only. | 43844.4172 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0126 | WELLS, ALICIA (awells43) | 0 | 0 | 0 |  | (7/26/21) Project on Hold
AA | 6 | AA-1676 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0012 | Smith | SMITH 217/218/220 SYST. ENGIN. MOVE FROM CAMERON | Smith - 205, 206, 211, 212, 213, 214, 216, 308,311,314,317,318,319,320, 320A,325,348,349,351,352 - relocate Systems Engineering from Cameron 2nd floor to Smith and create graduate bull pins for Engineering Technology graduate students who currently o | 43844.4475 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0128 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (09.01.2020) Waiting on design fee from McVeign & Mangum. Will follow up with them this week.
AA | 6 | AA-1677 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0012 | Smith | SMITH 2 & 3 FLOOR CORRIDOR REFRESH | Smith - 245D and 2nd/3rd floor corridors - Provide AV upgrade for conference room 245D for use by Engineering Technology. Replace existing VCT possibly Asbestos containing in 2nd and 3rd floor corridors with LVT to match recently renovated hallways o | 43844.4513 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0129 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | NNP - part of Cameron moves
AA | 1 | AA-1686 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0020 | McEniry | MCENIRY FF&E | McEniry - Furniture Project - Full scope still needs to be determined.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 43844.4744 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 20-0135 | WELLS, ALICIA (awells43) | 13000 | 1000000 | 1934-05-09 08:38 | 44561 | (7/26/21)Majority of furniture orders have been placed. Just waiting on confirmed scope for a few small spaces in order to place final orders.
AA | 6 | AA-1684 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 114 116 118 120 122, 124 ACT. LEARN. CLRM | Fretwell - 114, 116, 118, 120, 122, 124 - Create new Active Learning Classroom and relocate Math Computer labs from other floors in Fretwell.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 43844.4651 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0133 | SISCO, ASHLEY (asisco1) | 28634 | 0 | 0 |  | (8/02/21) Per email from Donia 6/24 this project is on hold due to funding. Will revisit in early fall.
AA | 6 | AA-1685 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0063 | College of Health and Human Services | CHHS 330 NURSING SIMULATION LAB | CHHS - 330, 330A - Convert existing Classroom in School of Nursing Simulation Lab.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 43844.4667 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0134 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 |  | (06.21.21) Waiting on Donia for equipment and project scope. ON HOLD
AA | 0 | BA-2045 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0020 | McEniry | MCENIRY MOVES | McENIRY MOVES: Move occupants from Cedar/Hickory back to McEniry. Project moves and purchases start April 2021 and completes mid-December 2022. Assign to Alicia Wells. Project Dollar Maximum: $40,000. | 44300.6911 | FAKE, WILLIAM (wmfake) | SCHAUBLE, DONIA (dcooke) | CEALLAIGH, SHERRYL (sceallai) | FAKE, WILLIAM (wmfake) | 21-0126-I | WELLS, ALICIA (awells43) | 40000 | 40000 | 1945-02-21 13:12 | 44439 | (7/26/21) Move assistance in August for classrooms and furniture that was placed in storage.
AA | 0 | AA-1540 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0037 | McMillan Greenhouse | GREENHOUSE FOR BIOLOGY FACULTY | Greenhouse for Biology Faculty | 43280.387 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 19-0023 | PATEL, NAVINKUMAR (npatel24) | 228650 | 228650 | 2012-05-20 08:53 | 44064 | (07.26.21) The project has been split into two. One is the site and utility package. The other is the Greenhouse structure and the alternates.
AA | 6 | AA-1692 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | BAND TOWER FOOTING DESIGN | Band Tower Footing Design - The marching band will be installing a pre-fabricated 24' tall steel tower at the practice field. The tower will need to have a footing designed by an NC licensed engineer. Getting a budget for this project is very urgent | 43873.4432 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SMITH, RYAN (rsmit341) | 20-0174 | SMITH, RYAN (rsmit341) | 550 | 550 | 1901-06-03 | 44439 | PROJECT NOTES UPDATED: 07/12/21 MILESTONES: * Project placed on hold 12/14/20 pending funding * Reviewed next actions and proposed design with customer. * Completed conceptual image of tower to present to Administration for approval.
AA | 6 | AA-1693 | Project On Hold Design Services | Informal Projects | 18000 | English | 0045 | Fretwell | FRETWELL 275 AND 248C REFRESH | I would like to talk to Ashley Sisco about possible options (seating and mobile wall) for refurbishing the English Department Reception area and lounge.Fretwell 275 and 248C | 43881.4546 | WILLIAMS, ANGELA (anwillia) |  | WILLIAMS, ANGELA (anwillia) | SISCO, ASHLEY (asisco1) | 20-0177 | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 |  | (8/02/21) Per email from customer this project will be on hold.
AA | 6 | AA-1698 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0080 | PORTAL | PORTAL 129 UPGRADES | Portal - 129 - Upgrades to Active Learning Classroom | 43906.3505 | SCHAUBLE, DONIA (dcooke) | TANKERSLEY, RICHARD (rtankers) | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0199-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 6 | AA-1701 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 314 RENOVATIONS | Fretwell - Suite 314 - Office of Interdisciplinary Studies | 43906.3613 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0204-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 |  | (8/02/21) Per email from Donia on 5/27/20 this project will be placed on hold. Will revisit in 6 months.
AA | 1 | AA-1705 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0075 | Motorsports Research | MOTORSPORTS VIBRATION PAD | Motorsports research needs to have their existing vibration pad permanently floor mounted. Adam Stall has a specific location in mind and needs to find out if the pad can be mounted in that location. Costs for the work must be identified and approv | 43920.7296 | SCHAUBLE, DONIA (dcooke) | STALL, ADAM (astall) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 20-0214-I | PATEL, NAVINKUMAR (npatel24) | 4000 | 34000 | 1939-04-23 01:41 | 44258 | (07.26.21) Equipment has been ordered. A progress meeting is set for 08.03.21. Work is in progress Estimated completion is 08.30.21.
AA | 0 | AA-1753 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0036 | Reese | REESE 528 CREATE CONFERENCE SPACE | Reese 528 Create Conference Space. This would be to create a conference space on the east wall as you enter the room. Currently, there is a thermostat that would need to be moved, power and data at 18" that would need to be raised, and some sort of s | 44363.6333 | HOMESLEY, SHANNON (sthomesl) | HOMESLEY, SHANNON (sthomesl) | HUNTER, KATHY (kdwhaley) | PATEL, NAVINKUMAR (npatel24) | 21-0166-I | PATEL, NAVINKUMAR (npatel24) | 12000 | 12000 | 0 | 44435 | (07.26.21) Renovation to take place August 19, on approval from Joan.
AA | 1 | BA-1923 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0097 | Science Building | SCIENCE FF&E | SCIENCE FF&E: Furniture for the new Science building & Data Center. Capital funded project. Project Dollar Maximum; $1,500,000. Assign to Alicia Wells. | 43880.6496 | FAKE, WILLIAM (wmfake) |  | CEALLAIGH, SHERRYL (sceallai) | WELLS, ALICIA (awells43) | 20-0176 | WELLS, ALICIA (awells43) | 1500000 | 1500000 | 2275-01-14 22:34 | 44439 | (7/26/21) Was able to receive better dates for most furniture delays. Working on added scope furniture items and install dates.
AA | 6 | AA-1706 | Project On Hold Design Services | Informal Projects | 15300 | College of Liberal Arts & Sciences | 0045 | Fretwell | FRETWELL 3RD FLOOR ATRIUM NAMING | Fretwell 3rd Floor Atrium Naming. Dr. Robert & Mrs. Tiwana Anderson Atrium Signage and Portrait development and installation | 43921.7374 | FRIZZELL, MARY ELLEN (mfrizzel) | LEKOSKI-EURICH, JUDY (jlekoski) | STAFFORD, ELEANOR (eastaffo) | TERRY, STEPHEN (slterry) | 20-0217-I | TERRY, STEPHEN (slterry) | 5400 | 0 | 0 |  | 06/23/21. No change. Budget review. Customer said to hold.
AA | 0 | BA-2077 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0097 | Science Building | SCIENCE MOVES | SCIENCE MOVES: All related moves to the new Science Building from across campus. Assign to Alicia Wells. Project Dollar Maximum: $250,000.00. Funding Source: Capital Projects Funding Code: 885853. | 44364.5987 | FAKE, WILLIAM (wmfake) | CEALLAIGH, SHERRYL (sceallai) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0169-I | WELLS, ALICIA (awells43) | 250000 | 250000 | 1979-08-08 12:58 | 44592 | (7/26/21) Moves currently taking place for teaching spaces
AA | 1 | AA-1703 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0041 | Storrs | STORRS 230, 222B, 274, 276 RENOVATIONS | Storrs - Rooms 230, 222B, and 274/276 - Additional work and furniture needed to accommodate space changes that will take place as part of the Capital ITS Infrastructure Replacement work in the Storrs building. | 43906.3619 | SCHAUBLE, DONIA (dcooke) | PAYNE, TODD (tapayne) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0206-I | SISCO, ASHLEY (asisco1) | 77000 | 72000 | 2026-04-21 01:12 | 44081 | (8/02/21) Waiting on quote for door.
AA | 0 | AA-1710 | Scope & Budget Requested | Informal Projects | 25000 | Library | 0041 | Storrs | STORRS 200 ARCHITECTURE LIBARY SHELVING | Secure a certified library mover to replace the existing vista base shelving in the architecture library at Storrs with welded frame shelving from the main library in order to create additional shelf capacity. | 43948.3131 | REYNOLDS, MARK (mdreynol) | REYNOLDS, MARK (mdreynol) | BARTON, JESSICA (jbarto18) | FRERE, ELIZABETH (efrere) | 20-0230-I | FRERE, ELIZABETH (efrere) | 0 | 0 | 0 |  | Project already complete. Mark Reynolds and Todd Payne confirmed. Please cancel.
AA | 0 | AA-1747 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0041 | Storrs | STORRS 148 POWER FOR NEW EQUIPMENT | Storrs 148-148A We would like to relocate an existing CNC router (AXYZ) and its accompanying vacuum system (both currently in Storrs 148A). We will also need to provide power to a smaller recently purchased CNC router (Laguna). The new location for b | 44294.4779 | SCHAUBLE, DONIA (dcooke) | PAYNE, TODD (tapayne) | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 21-0123-I | BOAL, JOHN (jboal1) | 18080 | 15803.05 | 0 | 44358 | 7/27/2021: Design is complete. Pricing is underway. Meeting is scheduled for 8/10 on site for pricing review.
BA | 0 | BA-1994 | Approved Scope & Budget PAM | Informal Projects | 10400 | Business Services AVC | 0039 | Auxiliary Services Building | ASB HALLWAY & RESTROOM IMPROVEMENTS | ASB restroom improvements, mens room to be reviewed and cleaned up, new paint, flooring, partitions, fixtures?, new touchless controls. Womens room new touchless controls. ADA Restoom new touchless controls. Carpet deep clean & remove carpet bubbl | 44126.6241 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | SISCO, ASHLEY (asisco1) | 21-0049-I | SISCO, ASHLEY (asisco1) | 45000 | 0 | 0 |  | (7/26/21) Met with customer 7/13/21. Anticipate scope and budget to customer by end of July.
BA | 0 | BA-2046 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0039 | Auxiliary Services Building | AUXILIARY SERVICES RENOVATION STUDY | Auxiliary Services Building Renovation Study, full renovation of building to provide post-covid office space utilizing the campus standards and showcasing what open, flexible offices can be. This is a study. Before and after floor plan and a couple | 44307.5783 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0127-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) RFQ send to (5) design firms - due July 20. Meeting to select designer July 26. Selected DLR Group.
BA | 0 | BA-2080 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0054 | Bissell House | BISSELL HOUSE CABINET & SHELVING RENO | BISSELL HOUSE CABINET & SHELVING RENO: Improvements to the Bissell House cabinets and shelving throughout the residence. Project Dollar Maximum: $34,000.00 Assign to Alicia Wells. | 44368.5746 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0172-I | WELLS, ALICIA (awells43) | 34000 | 34000 | 1926-06-28 17:46 | 44454 | (7/26/21) Project to be complete by the end of July.
BA | 0 | BA-2093 | Scope & Budget Requested | Informal Projects | 14010 | Facilities Informal Projects | 0054 | Bissell House | BISSELL HOUSE PATIO FURNITURE REFINISH | Refinish the patio furniture at Bissell House | 44403.7051 | CAUDLE, AMANDA (afelock) | GREGG, LAUREN (lgregg1) | WITHERSPOON, MELANIE (mewither) | CAUDLE, AMANDA (afelock) | 22-0013-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Reached out to customer contact 7/27 for scope of work. Will submit scope & budget by 8-2-21.
BA | 2 | BA-1945 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | DINING SEAT CUSHIONS | SEAT CUSHIONS, various locations, need to provide seat cushions for all hard wood seats. Includes Prospector, Student Union, SVC. Project will have to be bid given the number of seats. | 43931.539 | AVERITT, DREW (daveritt) | HOLMES, ROBERT (rholme16) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 20-0222-I | CAUDLE, AMANDA (afelock) | 8000 | 8000 | 0 | 44393 | (8-2-21) PO issued to Step Up to fabricate cushions for Prospector patio seating 7/20.
BA | 0 | BA-2074 | Construction | Informal Projects | 10400 | Business Services AVC | 0005 | Cone University Center | CONE 245 MAINSTREET MARKET KIOSKS | Cone 245 Mainstreet Market Kiosks, provide data and power locations for (3) new kiosks. Kiosks will sit on the 6' counter top near the TV area outside of the food area. Conduits can run under counter then enter the TV closet area and run overhead to | 44363.6284 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0164-I | CAUDLE, AMANDA (afelock) | 4000 | 4000 | 0 | 44410 | (8-2-21) Routed Scope & Budget to customer 8-2-21. Work to complete by 8-13-21.
BA | 0 | BA-2005 | Construction | Informal Projects | 13900 | Facilities Management AVC | 0059 | Facilities Annex One (J-Building) | BUILDING J AUTOMOTIVE RENOVATION | Renovate the office area in Bldg J. Create a lobby and small office that can be shared. Add a canopy and large glass storefront. Clean up the back area outside the bldg. move water fountains to auto bay area if possible per walkthrough on 1/25/21 | 44223.6488 | CEALLAIGH, SHERRYL (sceallai) | CEALLAIGH, SHERRYL (sceallai) | WITHERSPOON, MELANIE (mewither) | CAUDLE, AMANDA (afelock) | 21-0069-I | CAUDLE, AMANDA (afelock) | 200000 | 285000 | 2293-01-07 18:58 | 44263 | (8-2-21) Work in progress. Above ceiling inspection targeting July 13. Work anticipated to complete by early August.
BA | 0 | BA-2082 | In Design | Informal Projects | 14010 | Facilities Informal Projects | 0059 | Facilities Annex One (J-Building) | BUILDING J AUTOMOTIVE MEZZANINE REMOVAL | BUILDING J AUTOMOTIVE MEZZANINE REMOVAL: Remove the mezzanine from Building J Automotive Shop. Scope includes removal of sprinkler system, lights and J boxes from underneath. Project Dollar Maximum: $15,000. Assign to Amanda Caudle. | 44385.2376 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 22-0001-I | CAUDLE, AMANDA (afelock) | 15000 | 0 | 0 |  | (8-2-21) Working with contractor on savings from scrap metal.
BA | 0 | BA-2068 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0055 | Facilities Management & Police & Public Safety | FM AVC SUITE DOORS | FM AVC SUITE DOORS - Install four new red oak veneer doors with new knockdown metal frames. Doors to be pre-finished cinnamon color with vision kits and new hardware sets. Project Dollar Maximum: $24,000. Assign to Ashley Sisco. | 44351.4654 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0157-I | SISCO, ASHLEY (asisco1) | 24000 | 24000 | 1961-03-25 | 44439 | 8/02/21 Wrapping up final billing
BA | 0 | BA-2075 | Scope & Budget Requested | Informal Projects | 15000 | Police and Public Safety | 0055 | Facilities Management & Police & Public Safety | FM/PPS 284 DISPATCH CENTER UPGRADE | FM/PPS 284 Dispatch Center Upgrade. Investigate upgrading the Dispatch Center for PPS to better manage cabling and add needed space. | 44363.6351 | GANT, STANLEY (sgant1) | GANT, STANLEY (sgant1) | BARNETT, DENISE (dbarne33) | CAUDLE, AMANDA (afelock) | 21-0167-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Kickoff meeting scheduled for July 7. Working through test fits to expand the dispatch center.
BA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0045 | Fretwell | FRETWELL CAFE' RENOVATION | Renovate Fretwell Cafe' | 43789.2349 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | SISCO, ASHLEY (asisco1) | 722500 | 777820.77 | 0 |  | (8-2-21) Consultants: Watson Tate Savory - designer Contractor: Heartland Contracting Milestone dates and activities: Construction begins May 10, 2021 and currently scheduled to complete mid-September.
BA | 0 | BA-2057 | Construction | Informal Projects | 10400 | Business Services AVC | 0045 | Fretwell | FRETWELL 109 CAFE FURNITURE FOR RENO | Fretwell 109 Cafe Furniture for Renovation, provide new furniture separate from the renovation project. | 44312.4606 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | SISCO, ASHLEY (asisco1) | 21-0138-I | SISCO, ASHLEY (asisco1) | 86284 | 86284 | 0 | 44439 | (8/02/21) - Furniture is on order. Furniture to arrive in 2 separate shipments.
BA | 0 | BA-2060 | Construction | Informal Projects | 10400 | Business Services AVC | 0045 | Fretwell | FRETWELL 109 CAFE KITCHEN EQUIPMENT | FRETWELL 109 CAFE Kitchen Equipment, provide easy self contained kitchen equipment items not being provided in the Cafe Renovation project. | 44314.5956 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | SISCO, ASHLEY (asisco1) | 21-0142-I | SISCO, ASHLEY (asisco1) | 25720 | 105720 | 1965-09-15 | 44439 | (8/02/21) PO for kitchen equipment has been issued. Equipment is expected to arrive mid August with some arriving in September
BA | 6 | BA-1544 | Project On Hold Design Services | Informal Projects | 13800 | Environmental Health & Safety | 0000 | Campus | CAMPUS WIDE BUILDING EVACUATION MAPS | Building evacuation interior floor plan maps need to be installed in all buildings. The Office of Environmental Health and Safety would like to request an official scope and budget to install these maps. | 42801.6963 | GRIFFIN, DARIUS (dgriffin) |  | GRIFFIN, DARIUS (dgriffin) | TERRY, STEPHEN (slterry) | 17-0195 | TERRY, STEPHEN (slterry) | 0 | 0 | 0 |  | 06/23/21. No change. Still on hold for funding. Scope was provided to EHS for funding review. This may need to be an internally BA funded project.
BA | 6 | BA-1586 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT: Congestion Task Force assignment for design only: Central Funds - Project Dollar Maximum: $13,000. | 42872.3307 | FAKE, WILLIAM (wmfake) |  | PAQUETTE, NOELLA (njpaquet) | KELLY, SHAWN (skelly64) | 17-0225 | KELLY, SHAWN (skelly64) | 13000 | 13000 | 1932-02-12 16:48 | 42884 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * On Hold till construction funding can be secured and further direction provided. - NOTES / ISSUES / CONCERNS: * Consultant: Dewberry * CD's 100% Complete & Ready for Construction * Project was initially undertaken as a Chancellor Dubois Funded Campus Circulation Improvement.
BA | 6 | BA-1631 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0068 | Bioinformatics | FPFM, BIOINFORMATICS 124 CODE ROOM USE SEPARATIONS | FPFM - BIOINFORMATICS 124 CODE REQUIRED ROOM USE SEPARATIONS: Mechanical, storage and wood shop uses need separation by 2-hour fire walls. Construction costs unknown. Outside design is required at $30,000. | 43041.2834 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | BOAL, JOHN (jboal1) | 18-0089 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 7/27/2021: Project not funded.
BA | 6 | BA-1680 | Project On Hold Design Services | Informal Projects | 13800 | Environmental Health & Safety | 0000 | Campus | CAMPUS SERVICE VEHICLE SIGNAGE | Please provide a proposed scope and budget for the project detailed below. Once the scope and budget is received, our office will be able to determine if the project can be completed this fiscal year or in the next.Approximately 15 marker post signs | 43192.6969 | GRIFFIN, DARIUS (dgriffin) | ALSTON, TAMEKA (talsto16) | BARNETT, DENISE (dbarne33) | TERRY, STEPHEN (slterry) | 18-0198 | TERRY, STEPHEN (slterry) | 18500 | 0 | 0 |  | 06/23/21. No change. Budget review. Customer said to hold. Scope and preliminary designs were provided to EHS for review.
BA | 6 | BA-1696 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1007 | Union Deck | UNION DECK STORAGE ROOM | UNION DECK Storage Room, provide large storage room on level 1 underneath of the up ramp where area is fenced off. This modification was rejected in the Expansion project due to schedule but we would like to review requirements and price out impleme | 43227.4005 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | CAUDLE, AMANDA (afelock) | 18-0232 | CAUDLE, AMANDA (afelock) | 225000 | 0 | 0 |  | (8-2-21) Placed on hold 1-23-20.
BA | 0 | BA-2091 | Req Design Estimate Review | Informal Projects | 14010 | Facilities Informal Projects | 0035 | Friday | FRIDAY RM 146C RESTRM ADA DOOR ACTUATORS | FRIDAY ROOM 146C RESTROOM ADA DOOR ACTUATORS: Add ADA door actuators on the exterior and interior of Room 146C. Project Dollar Maximum: $10,000. Fund Source: Informal Projects Fees. Assign to Amanda Caudle. | 44403.6274 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | PAQUETTE, NOELLA (njpaquet) | FAKE, WILLIAM (wmfake) | 22-0010-I | CAUDLE, AMANDA (afelock) | 10000 | 6000 | 0 | 44414 | (8-2-21) Working with the lockshop on scope of work and costs. Anticipate scope & budget by 8-6-21.
IF | 6 | BA-1796 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1008 | North Deck | NORTH DECK FFA LIGHTING REPLACEMENT | NORTH DECK FFA LIGHTING REPLACEMENT, replace top level light fixtures with LED type units in place of the metal halite. | 43510.396 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | LOVE, DAVID (dflove) | 19-0161 | LOVE, DAVID (dflove) | 7900 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * Project placed On Hold till further funding is secured by customer. * Project will move forward pending approval of new campus Standard LED light fixture. - NOTES / ISSUES / CONCERNS: * Existing campus lighting standard is no longer being manufactured.
IF | 6 | BA-1797 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1009 | CRI Deck 1 | CRI DECK FFA LIGHTING REPLACEMENT | CRI DECK FFA LIGHTING REPLACEMENT, replace top level light fixtures with LED type units in place of the metal halite. | 43510.3967 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | LOVE, DAVID (dflove) | 19-0162 | LOVE, DAVID (dflove) | 6800 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * Project placed On Hold till further funding is secured by customer. * Project will move forward pending approval of new campus Standard LED light fixture. - NOTES / ISSUES / CONCERNS: * Existing campus lighting standard is no longer being manufactured.
BA | 2 | BA-1911 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 4012 | Niner University Elementary at Amay James | NINER UNIVERSITY ELEMENTARY FF&E | NINER UNIVERSITY ELEMENTARY FF&E: Provide the following: (1) Furniture for eleven classrooms, reception area, media center, and cafeteria. (2) Classroom technology. (3) Signage. Project Dollar Maximum: $590,000. Assign to Amanda Caudle. | 43854.3428 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | CAUDLE, AMANDA (afelock) | 20-0154 | CAUDLE, AMANDA (afelock) | 590000 | 590000 | 579753.15 | 43857 | (8-2-21) Wrapping up punch list items.
BA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0069 | Popp Martin Student Union | POPP MARTIN STUDENT UNION | renovate Einsteins, New Venue & Crown Commons | 43789.2451 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | CAUDLE, AMANDA (afelock) | 9638114.5 | 8970591 | 0 |  | (8-2-21) Consultants: Moseley Architects - designer Shiel Sexton - CM@R CMTA - commissioning agent Shake Smart bids received April 23, 2021 - Heartland Contracting is low bidder. Construction to begin May 18 and complete by August 6, 2021. Crown Commons renovation is back in design per email April 27, 2021. Kickoff meeting with designer is scheduled for July 13. Summer 2022 construction.
BA | 6 | BA-1871 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING: Need Scope & Budget to allow further review by Jon Varnell to allow assessment of funding options. Please assign to Steve Terry. | 43787.4471 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | TERRY, STEPHEN (slterry) | 20-0088 | TERRY, STEPHEN (slterry) | 30000 | 30000 | 0 | 43994 | 06/23/21. Reviewed by K. Horne and J. Varnell. Funds pending. No change. Said to hold.
IF | 6 | BA-1889 | Project On Hold Design Services | Informal Projects | 13115 | Safety and Security | 0046 | Barnhardt Student Activity Center | FIRST PRIORITY CAMERA PROJECT PHASE 2 | Please assign to David Love - Phase 2 includes SAC, West Deck, Belk Gym, Cone, Colvard, Levine Hall, Cato, Prospector, McEniry, Auxiliary Services, Cameron, Bioinformatics, PORTAL, EPIC, Grigg, Duke, Motorsports, South Village Deck. (Approximately 2 | 43837.4379 | HILL, MICHELLE (mphilipp) |  | BARNETT, DENISE (dbarne33) | KELLY, SHAWN (skelly64) | 20-0115 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * Project Currently on Hold * Awaiting funding and Defined Scope & Timeline with Customer.
BA | 0 | BA-1971 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0069 | Popp Martin Student Union | STUDENT UNION 137-138 STORAGE ROOM MODIFICATIONS | SU Storage Room Modifications, modify 137 and 138 to remove demizing wall. Relocate some metal shelving. Need large item storage and pallet drop area. Provide rolling plastic shelving typical of our dry storage areas to provide more storage within | 44025.5813 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0012-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Layouts and budget pricing provided to Drew Averitt on 9-21-20. Working with Metro Shelving on final layout.
IF | 6 | BA-1913 | Project On Hold FAM | Informal Projects | 13115 | Safety and Security | 0000 | Campus | CAMPUS SIREN UPGRADE "ALERTUS" | Safety & Security - Campus Siren upgrade - "Alertus" | 43861.4644 | HILL, MICHELLE (mphilipp) |  | BARNETT, DENISE (dbarne33) | LOVE, DAVID (dflove) | 20-0162 | LOVE, DAVID (dflove) | 0 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * Project on hold until Police & Public Safety can secure new project funding. - NOTES / ISSUES / CONCERNS: * Consultants: Alertus
BA | 0 | BA-2035 | Construction | Informal Projects | 10400 | Business Services AVC | 0069 | Popp Martin Student Union | STUDENT UNION 151 MARKET ENTRY DOOR | SU Market door lock, review and design a solution to the existing sliding door that currently has to remain unlocked for fire egress before opening to the public. Need a lock/door that can be locked but allows panic out if needed. Public will open th | 44273.6208 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0108-I | CAUDLE, AMANDA (afelock) | 5500 | 23000 | 1906-11-04 | 44307 | (8-2-21) In design with Lambert Architecture. Selected door type and manufacturer - working on construction documents.
BA | 0 | BA-2062 | Construction | Informal Projects | 10400 | Business Services AVC | 0069 | Popp Martin Student Union | STUDENT UNION 112 BOOKSTORE REPLACE SIGN | Popp Martin Student Union 112 Bookstore Replace Front Sign - replace existing front entry sign with the Starbucks type of sign. | 44321.4439 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0146-I | CAUDLE, AMANDA (afelock) | 17000 | 17000 | 0 | 44323 | (8-2-21) Purchase order issued to Momentum Construction 5-10-21. Installation to begin week July 26 and complete by August 6.
BA | 6 | BA-1927 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR DOOR REPLACEMENT | PROSPECTOR Door Replacement, replace the (5) full glass door locations with standard doors. There are (3) exterior pairs of doors (tied into Open Options), (1) interior vestibule pair of doors and (1) interior pair of doors (needs to lock). Pending | 43888.4872 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 20-0190 | CAUDLE, AMANDA (afelock) | 12000 | 12000 | 1923-10-26 | 44158 | (8-2-21) In design with C Design. Drawings submitted to SCO for review March 12. Bids due April 7 by 2pm. Bids still too high for customers budget. Project is on hold as of 5-6-21.
IF | 6 | BA-1929 | Project On Hold Design Services | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | MEMORIAL STRUCTURAL SCULPTURE DESIGN | MEMORIAL STRUCTURAL SCULPTURE DESIGN: Structural design for steel memorial sculpture with foundation in University Gardens to contain large stones with student etched memorials. Pro Bono (no cost) design by SKA Consulting Engineers. Fund: 336487. | 43892.3788 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0182 | FAKE, WILLIAM (wmfake) | 1 | 1 | 0 | 44134 | (11-11-2020) No new updates - Project awaiting Customer approval actions and funding source. (10-27-2020) - Two Construction Cost Estimates: (#1) $21,600 steel frame only (SteelFab). Installation $29,800 (MV Momentum). Contingency $2,600. Net total $55,000. (#2) $21,600 steel frame only (SteelFab). Installation $18,700 (Heartland Contracting). Contingency $2,000. Net total $42,300. Well over $17,000 anticipated by Customer Marek Ranis - Marek acknowledged receipt of estimates on Monday,10-26-2020. (09-29-2020) - Design by SKA (Garrett Overcash) Pro Bono: Design completed and approved by Customer late Tuesday 09-15-2020. Final documents submitted to SCO week of 09-21-2020 using SCO - ID# 20-21851-01. SCO Approved documents on 09-29-2020. (03-03-2020) Original construction start anticipated mid-October with completion anticipated late November - Needs a project request entry by Student Affairs for Construction phase.
BA | 0 | BA-2025 | Construction | Informal Projects | 10500 | Auxiliary Operations | 0034 | Prospector | PROSPECTOR CFA NEW CARPET PROJECT | Bid out new carpet in CFA area. To coincide with existing new booths. | 44251.7755 | HOLMES, ROBERT (rholme16) | HOLMES, ROBERT (rholme16) | MEDINA, CHARISSE (cturne66) | SISCO, ASHLEY (asisco1) | 21-0096-I | SISCO, ASHLEY (asisco1) | 15847 | 15847 | 0 | 44377 | (8/02/21) Customer wanted to get a quote to install carpet in the lower dining area.
IF | 6 | BA-1944 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | STARBUCKS TRUCK PAD AND ELECTRICAL | STARBUCKS TRUCK Pad and Electrical, provide design to provide a prototypical pad off off the sidewalk for Starbucks Truck to pull over and sell during the day. Initial location is intended to be Smith but pad could be used anywhere - need pull off, | 43931.5389 | AVERITT, DREW (daveritt) | THOMPSON, JODY (jthom373) | MEDINA, CHARISSE (cturne66) | SMITH, RYAN (rsmit341) | 20-0221-I | SMITH, RYAN (rsmit341) | 26000 | 0 | 0 |  | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 06/16/20: Project on Hold per Drew Averitt
BA | 0 | BA-2065 | Scope & Budget Requested | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR 102 & 200A STUDY FOR RENO | Prospector 102 1st Floor Study for Renovation - provide study for future renovation plans of the upper level of prospector (102). Include proposed new food venues, new layout and include Gold Room area (200A). | 44340.8351 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0154-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Kick off meeting with Chartwell's BUILT design team 7/22. Awaiting fee proposal.
BA | 0 | BA-2084 | Construction | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR SUSHI WITH GUSTO (AT MONDO) | PROSPECTOR, SUISHI WITH GUSTO (at Mondo's), remove signage and graphics, paint per email, provide (2) 240V outlets per email. Need before Fall Startup. | 44397.3194 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 22-0003-I | CAUDLE, AMANDA (afelock) | 7000 | 7000 | 0 | 44411 | (8-2-21) Routed Scope & Budget to customer 8-2-21. Work to complete by 8-13-21.
BA | 0 | BA-2064 | Construction | Informal Projects | 10300 | Business Affairs VC | 0036 | Reese | REESE 414 & 415 VCBA OFFICE REMODEL | Extend VCBA office in Reese 415 by moving wall between Reese 415 and 414. Move door from 414 and add a door between 415 and 414. | 44340.8349 | FINDLATER, KATHARINA (kfindlat) | FINDLATER, KATHARINA (kfindlat) | LEAMON, MELISSA (mleamon) | CAUDLE, AMANDA (afelock) | 21-0153-I | CAUDLE, AMANDA (afelock) | 32000 | 60000 | 1954-10-03 | 44347 | (8-2-21) Construction to begin June 1. Anticipate completion by end of June. Furniture on order June 16 - currently scheduled to install August 13.
BA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0097 | Science Building | SCIENCE CAFE' | Auntie Ann's Cafe in the new science bldg | 43789.3228 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | NEILSON, JOHN (jneilson) | 1377225 | 735438 | 0 |  | 7-27-21 Consultants: BUILT - Chartwells Consultants for SD Clark Nexsen - Designer for DD, CD, CA GC: Elford, Inc. Milestone Dates and Activities: 07/19/2021 - Contracts executed and NTP issued May 19, 2021; completion September 16, 2021. Elford mobilized and construction underway - aiming for August 20 completion. Work has been underway for 5 weeks. In wall rough-in inspections have passed, including SCO's electrical inspection. Overhead electrical and HVAC work continues. Metal framing is complete, and drywall installation has begun. Finishes will soon begin. Finishes are underway and the only obstacle in the way of completing on time is delivery of the walk in cooler. Mud setting bed and liquid waterproofing have been installed, and installation of floor tile has begun.
BA | 2 | BA-1919 | Construction | Informal Projects | 10500 | Auxiliary Operations | 0082 | South Village Crossing | SVC TERRACE FURNITURE | SVC Terrace Furniture, propose, review and provide exterior furniture and accessories on the upper floor terrace area. Replace and or relocate existing furniture as supports the overall plan fo rthe terrace. | 43871.4719 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 20-0167 | CAUDLE, AMANDA (afelock) | 90000 | 65000 | 0 | 44398 | (8-2-21) Adirondack chairs on order 7/19/21 - install in 12 weeks.
BA | 0 | BA-1968 | Construction | Informal Projects | 10400 | Business Services AVC | 0082 | South Village Crossing | SVC SUN SAILS | SVC Sun Sails, provide sun sails over portions of the terrace area. | 44020.3319 | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0003-I | CAUDLE, AMANDA (afelock) | 60000 | 60000 | 1985-04-06 06:43 | 44054 | (8-2-21) Installation scheduled for the week of August 9.
BA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 1007 | Union Deck | UNION DECK ELEVATOR | Replace elevator | 43997.6095 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | KUGLER, BRIAN (bhkugler) | 0 | 681836.63 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 06/25/21: 100% Owner Sign Off and SCO Approval Received * Project Placed on Hold till October 2021 to perform work in Spring 2022. * 10/06/21: Notice To Bidder Posted * 11/06/21: Bids Received * 12/06/21: Contract Awarded * Tentative Construction Duration (12 Weeks) - NOTES / ISSUES / CONCERNS: * Consultant: WHN * Customer requested elevator construction be held till May 2022 due to equipment procurement timelines and inability to complete by August 6th, 2021.
IF | 0 | AA-1709 | Construction | Informal Projects | 24202 | OneIT-Enterprise Infrastructure | 0004 | Atkins | ATKINS L36 G20 UPS | Atkins UPS for Atkins L-36 and G20ITS would like to start a project to replace the existing UPS at Atkins for our IT rooms. We have been in conversation with Tom MacNab who has worked with a vendor to provide a quote for what he feels is needed bas | 43948.3125 | FRANCUS, KATHLEEN (krfrancu) | FRANCUS, KATHLEEN (krfrancu) | VITALLO, JUDY (jvitallo) | SMITH, RYAN (rsmit341) | 20-0229-I | SMITH, RYAN (rsmit341) | 10000 | 324800 | 2143-08-14 08:24 | 44104 | - PROJECT NOTES UPDATED: 07/12/21 - UPS MILESTONES * 07/01/21:UPS Installation Complete & Fully Operational - G20 PANEL MILESTONES * 07/01/21 - 08/13/21: G20 Work To Be Completed. * 08/16/21: G20 Panel Work Complete & Full Operational
IF | 0 | AA-1735 | Construction | Informal Projects | 24202 | OneIT-Enterprise Infrastructure | 0004 | Atkins | ATKINS G65 HVAC FOR UPS | Atkins G65 New HVAC for the UPS Room.Please proceed with a project for the quote of $28,000.00 from McKim & Creed. This quote is to identify what would be needed for the replacement of the HVAC units and the electrical issues for the UPS Room. We | 44179.397 | FRANCUS, KATHLEEN (krfrancu) | FRANCUS, KATHLEEN (krfrancu) | VITALLO, JUDY (jvitallo) | SMITH, RYAN (rsmit341) | 21-0059-I | SMITH, RYAN (rsmit341) | 30149 | 176533.55 | 1940-07-01 21:22 | 44347 | - PROJECT NOTE UPDATE: 07/12/21 - MILESTONES * 06/23/21: Facilities Management Issue PO to Blackmon through the Informal Construction Project. * 07/01/21 - 12/01/21: Install new HVAC System. * Cause of Installation Delay: 17 Week Lead Time Needed for Mechanical Equipment * 01/03/22: New HVAC System Complete & Fully Operational
IF | 0 | SA-0463 | Construction | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC EAST BOILER REPLACEMENT | BSAC - East Boiler Room, 295A We need options in replacing the boiler in room 295A. We need quotes for a new system with redundancy and quotes on replacing the old system. | 44011.5154 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | KELLY, SHAWN (skelly64) | 20-0257-I | KELLY, SHAWN (skelly64) | 12000 | 12000 | 0 | 44435 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 05/10/21: Project design authorized to move forward. * 07/30/21: Design Completed & Sent to SCO for Approval - NOTES / ISSUES / CONCERNS: * Venue Mgmt. secured funding for design.
IF | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0000 | Campus | NEW CRI ENTRANCE ROAD | Create a new entrance off Hwy 29 | 43789.2191 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 1449300 | 1159589.44 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * Project currently on Hold Pending Funding and Approval * Designer Selection Meeting Held, Designer Tentative Selected * Brian Kugler sending signed letter to designers notifying project will not move forward at this time. - NOTES / ISSUES / CONCERNS: * UNCC Grounds currently working on pricing for topsoil and seeding of site. Funding for site establishment to potentially come from this project per Jon Varnell.
IF | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | RECLAIMED WATER | The University has developed a proposed partnership with Charlotte Water (City of Charlotte) to bring reclaimed water to campus from the Mallard Creek waste water plant. This water will replace potable water currently used in chillers and boilers on | 42719.3281 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 2100000 | 2012020.56 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 06/11/21: Tentative Obtain SCO & Internal 100% CD Approval * 06/22/21: Advertise for Bid for Construction * 07/20/21: Open Bids & Select Contractor * 08/20/21: Award Contractor * 09/06/21 - 01/30/23: Tentative Construction Duration: - NOTES / ISSUES / CONCERNS: * Consultant: AECOM * Charlotte Water Scheduled to Complete on Campus Portion of Reclaimed Waterline by 05/2021 off campus reclaimed connection complete by 12/2021.
IF | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | REGIONAL STORM WATER IMPROVEMENTS MASTER PLAN | Authorization is $850,000 - Capital budget is $750,000. Storm Water Volume Control r-58. #2 priority project in Storm Water Master plan. Required to bring us into compliance with Clean Water Act.The restoration of Toby Creek is proposed as a partners | 41624.69 | FESSLER, JOHN (jafessle) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | FRERE, ELIZABETH (efrere) | 750000 | 402139.45 | 0 |  | University is currently reviewing in Bluebeam, University. Resubmitting existing SCMs that are currently receiving partial or no stormwater credits to the City, Surface is analyzing existing SCMs on campus that were never submitted to the City (UREC, FOPS) or receiving partial credit (EPIC, Lot 27, Phase XII, Phase XIII, South Village Deck). Additional cost proposal from Surface (consultant is Wildlands) to be submitted as soon as they collect all the needed documentation for the above SCMs - anticipated cost +/- $60,000. After our review of the draft report it was decided that taking more time to work with Surface to help us find consensus as to what we want from the final report and provide clarifications that were moving targets when the scope of the designer's work was originally determined. Clarification of FM team roles and responsibilities - Peter will be finalizing the master plan by compiling comments and getting final draft.
IF | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | WEST SUBSTATION | Project adds a second electrical substation to feed electricity from Duke Energy 100 KVA supply on the west side of campus (across W.T. Harris). This is needed to provide redundancy to our electrical source to insure fail safe operation for research | 41555.43 | GILBERT, CHRISTOPHER (cgilbert) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | WALTERS, DOUGLAS (dwalte22) | 6500000 | 2689400.2 | 0 |  | 06/01/2021: McKim & Creed Design Amendment #2 reduction of scope and fees executed. Work to commence on cable testing. David Daignault and Don Janus creating schedule of work, and coordinating with campus partners. Cable testing will require campus electrical shut-downs as indicated below: Schedule to complete testing of 45 remaining cable lengths would be three weeks. Remaining contingency is enough to cover the cost of replacing longest length of cable on campus Engineering has met with FO to discuss this project. Majority of testing can be done without interruption of power to buildings (looped system). Circuit K, Seg 1: Outages would occur in Martin, Hawthorne, SHC, Counseling Center, FM/PPS and Annexes Circuit D, Seg 11: Levine Hall and HRL Circuit D, Seg 7: East Decks, Lots 4, 4A, Lot 6, Cato, Storrs, Band Center Circuit K, Seg 2: Martin Hall
IF | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | CID 2-EAST VILLAGE INFRASTRUCTURE | East Village infrastructure including Martin Village Road re-alignment, Van Landingham bridge, lighting, telelcom, storm, sanitary and the electrical extension to the campus substation. Includes a traffic signal at John Kirk Drive. | 41555.3514 | GILBERT, CHRISTOPHER (cgilbert) |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 4135056.7 | 7441514.79 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * Project currently placed on hold 01/04/21 by University Administration. * Final Billing for Design to Kimley Horne (Awaiting remaining balances for each open PO) * Negotiate Additional Pre-Construction Services (Should have Amendment Request for SCO 2/5/21) * Office notice of Project Suspension to NCDOT * Final Payment to CM@Risk for Final Construction Services - NOTES / ISSUES / CONCERNS: * Consultant: Kimley Horne * Contractors: CM@R Sheil Sexton * Project Delivery Method: CM@Risk * Review Bid Numbers and Determine Next Steps For Award of EVI and construction execution. * Need to receive documentation of Supplemental Agreement to secure Funding from NCDOT (Pending Contract Language Discussion if Project is approved to move forward $500,000.00 in funding currently unconfirmed from NCDOT.) * Project construction contingent on (EVI) bidding within budget in order to move forward. * Lot 5A Add Alternates and final project scope contingent on Add Alternates selected as part of (EVI). * Due to renegotiation of PGMP to 10% higher GMP Sheil Sexton GMP may come in higher then originally projected causing UNCC to have to decide to go in another direction and hard bid the project. * If Martin Hall Village Connector is not accepted we have agreed with CDOT to put it in our UNCC Capital Improvement Plan. * Police & ITS Duct Bank may be funded and installed concurrently with EVI as a informal project. If approved, coordination will need to be discussed and executed.
IF | 6 | BA-2033 | Project On Hold Design Services | Informal Projects | 13902 | Engineering Services | 0000 | Campus | FITNESS TRAIL CULVERT REPAIR | Provide design & repair to failed culvert on fitness path between softball playing fields and EPIC. Please assign to Infrastructure. Greg Cole will be the Engineering contact. | 44271.6111 | KELLY, SHAWN (skelly64) | JANUS III, DONALD (drjanus) | WITHERSPOON, MELANIE (mewither) | KUGLER, BRIAN (bhkugler) | 21-0104-I | KUGLER, BRIAN (bhkugler) | 0 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES * 05/04/22: Project Placed on Hold by Shawn Kelly * Project will move forward pending funding from FM AVC in FY 21-22
IF | 1 | BA-1938 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | CRI BUS PULL OFF DESIGN | CRI BUS PULL OFF DESIGN: Assign to Shawn Kelly. Project Dollar Maximum: $25,000. | 43906.649 | FAKE, WILLIAM (wmfake) | HORNE, KATHRYN (khorne16) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 20-0210-I | KELLY, SHAWN (skelly64) | 25000 | 45305.55 | 2004-04-07 13:55 | 43994 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 05/12/21: Final Design Approval Received * 06/18/21: SCO Approval Received * 06/25/21: Contractor Awarded Assuming Informal Bid Process * 06/28/21: Construction Started * 07/30/21: Construction Completed - NOTES / ISSUES / CONCERNS: * Consultants: Dewberry
IF | 0 | BA-1982 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, LIBRARY LANE VEHICULAR GATE | FPFM, LIBRARY LANE VEHICULAR GATE: Install security gate and infrastructure to control vehicle traffic on to core of campus from Library Lane. Project Dollar Maximum: $150,000.00. Assigned to: Shawn Kelly. | 44111.4672 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0034-I | KELLY, SHAWN (skelly64) | 150000 | 150000 | 1977-12-19 06:29 | 44344 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 06/11/21: Project Construction In Progress * 06/18/21: All Year End PO's Closed
BA | 6 | BA-2037 | Project On Hold Design Services | Informal Projects | 13930 | FM Architectural/Engineering | 1212 | Alumni Way | DUKE EASEMENT WT HARRIS & ALUMNI WAY | Duke Energy easement to access the transformer pole near the intersection of WT Harris and Alumni Way | 44279.7692 | KELLY, SHAWN (skelly64) | LALIBERTE, RICHARD (rlaliber) | WITHERSPOON, MELANIE (mewither) | KUGLER, BRIAN (bhkugler) | 21-0117-I | KUGLER, BRIAN (bhkugler) | 0 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES * 05/04/22: Project Placed on Hold by Shawn Kelly * Project Delayed until 2022 * Project will move off when it is ready to move forward as directed by Richard Liberte
BA | 6 | BA-2038 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1069 | Lot 16 | LOT 16 BIKE ENCLOSURE LAUNDRY UPFIT | Lot 16 Bike & Scooter Enclosure - Laundry Locker Upfit, modify the old bicycle shed (Lot 16/Elm Hall) to accommodate laundry lockers. Need S&B costs to determine project is viable. New storefront on open side. Card swipe entry. Modify lighting. We wi | 44285.3762 | AVERITT, DREW (daveritt) | TORRES, ENRIQUE (etorresj) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0118-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Awaiting design fee proposal from Insight Architecture and RFP selection of laundry lockers to complete design.
IF | 0 | BA-1983 | In Design | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, STORRS SERVICE LANE VEHICULAR GATE | FPFM, STORRS SERVICE LANE VEHICULAR GATE: Install security gate and infrastructure to control vehicle traffic on to the core of campus from Storrs Lane. Project Dollar Maximum: $150,000.00. Assign to: Shawn Kelly. | 44111.567 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0035-I | KELLY, SHAWN (skelly64) | 150000 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 06/11/21: Project Construction In Progress * 06/18/21: All Year End PO's Closed
BA | 6 | BA-2041 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 0069 | Popp Martin Student Union | STUDENT UNION CROWN COMMONS PULPER ROOM | SU Crown Commons pulper room. Find and relocate the pulper from the loading dock area to the 2nd floor in or adjacent to Crown Commons. This will allow us to abandon the pulper lines through the building. | 44288.4179 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | CAUDLE, AMANDA (afelock) | 21-0121-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Kickoff meeting April 5 at 9am. Site visit with Optima Engineering April 13 at 8am. Fee proposal received and sent to Drew for approval. Awaiting customer direction to proceed with project. Project on hold.
IF | 0 | BA-1986 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FY 20-21 CAMPUS HARDSCAPE REPAIR | FPFM, FY 20-21 CAMPUS HARDSCAPE REPAIR: Clean-up and repair existing hardscape: Reduce trip hazards; Improve pedestrian connections; Enhance campus appearance. Project Dollar Maximum: $295,000.00. Estimate to be developed. Assign to Shawn Kelly. | 44112.5147 | KELLY, SHAWN (skelly64) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0038-I | KELLY, SHAWN (skelly64) | 295000 | 151000 | 2242-08-04 23:17 | 44344 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 06/11/21: 100% Construction Complete * 06/18/21: Project Closed
IF | 0 | BA-1987 | In Design | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, COMPLETE ROADWAY STATUS ASSESSMENT | FPFM, COMPLETE ROADWAY CONDITION ASSESSMENT: Perform internal roadway condition assessment per NCDOT guidelines. Establish campus roadway repair priorities. Develop a long-term maintenance plan. Project Dollar Maximum: $25,000. Assign to Ryan Smith. | 44112.5618 | FAKE, WILLIAM (wmfake) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0039-I | SMITH, RYAN (rsmit341) | 25000 | 0 | 0 |  | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 07/30/21: Provide RFQ Outline For Road Study in FY21-22
IF | 0 | BA-1990 | In Design | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, MECKLENBURG: TOBY CREEK RESTORE | FPFM, MECKLENBURG COUNTY: TOBY CREEK RESTORATION: NO COST Project Request: Provide updates on Mecklenburg County Toby Creek Restoration. Brian Kugler serves as FM Liaison for the project. Assign to Brian Kugler. | 44112.6613 | KELLY, SHAWN (skelly64) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0043-I | KUGLER, BRIAN (bhkugler) | 0.01 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES * Tentative Construction Duration: 10/5/20 - 03/29/22 * 06/25/21: Bank Clearing & Construction of Streambank Structures. * Clearing Streambank from Mallard Creek Church Rd. to Championship Lane * Moving to other side of Championship Ln. through end of June. - NOTES / ISSUES / CONCERNS: * Government Entity: Mecklenburg County * Consultants: Kimley Horn * Contractors: Blythe Development
IF | 0 | BA-1991 | Approved Scope & Budget FAM | Informal Projects | 14010 | Facilities Informal Projects | 0000 | Campus | FPFM, CHARLOTTE: SEWER & RECLAIMED WATER | FPFM, CHARLOTTE WATER: SEWER & RECLAIMED WATER LINE: NO COST Project Request: Provide updates on Charlotte Water Sewer & Reclaimed Water Line construction. Brian Kugler serves as FM Liaison for the project. Assign to Brian Kugler. | 44112.6758 | KELLY, SHAWN (skelly64) | VARNELL, JONATHAN (jvarnell) | WITHERSPOON, MELANIE (mewither) | FAKE, WILLIAM (wmfake) | 21-0044-I | KUGLER, BRIAN (bhkugler) | 0.01 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES * Tentative Construction Duration: 10/5/20 - 03/29/22 * 05/28/21: Start Construction near Hammer Throw Site * 08/28/21: Sewer Line Installation complete on inner core of campus. - NOTES / ISSUES / CONCERNS: * Government Entity: Charlotte Water * Consultants: Stantec * Contractors: R.H. Price
IF | 0 | BA-2019 | Construction | Informal Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | CAMPUS WIDE ELEVATOR SHUNT TRIP UPGRADES | Campus wide Elevator shunt trip and solenoid sprinkler valve checks. Across campus many elevator shunt trip systems have never been tested since initial acceptance. Most will need to be upgraded to have elevator recall and time delay programmed for s | 44251.6551 | KELLY, SHAWN (skelly64) | JANUS III, DONALD (drjanus) | WITHERSPOON, MELANIE (mewither) | KELLY, SHAWN (skelly64) | 21-0090-I | KELLY, SHAWN (skelly64) | 7500 | 7500 | 1908-11-24 21:36 | 44365 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 06/11/21: All Equipment Delivered * 06/18/21: All Year End Project PO's Closed
IF | 6 | BA-2050 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1067 | Lot 14 | LOT 14 CRACK SEAL & SEAL COAT | LOT 14 CRACK SEAL & SEAL COAT, provide crack seal and seal coat for summer maintenance. | 44307.5796 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 21-0131-I | SMITH, RYAN (rsmit341) | 3000 | 3000 | 0 | 44439 | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 07/7/21: Project Placed on Hold by Request of Nancy Smith in preparation of potential lot impacts due to the Reclaimed Water Formal Project Construction starting in Fall of 2021.
IF | 6 | BA-2051 | Project On Hold Design Services | Informal Projects | 10400 | Business Services AVC | 1093 | SAC N Lot | SAC NORTH LOT RESTRIPING | SAC NORTH LOT RESTRIPING, provide restriping for summer maintenance. | 44307.5797 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 21-0132-I | SMITH, RYAN (rsmit341) | 2500 | 2500 | 0 | 44439 | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 07/7/21: Project Placed on Hold by Request of Nancy Smith in preparation of potential lot impacts due to the Reclaimed Water Formal Project Construction starting in Fall of 2021.
IF | 0 | BA-2034 | Construction | Informal Projects | 13902 | Engineering Services | 0000 | Campus | STUDENT UNION CULVERT REPAIR | Provide design & repair to failed culvert on path connecting Student Union to Oak. Please assign to Infrastructure. Greg Cole will be the Engineering contact. | 44271.6125 | KELLY, SHAWN (skelly64) | JANUS III, DONALD (drjanus) | WITHERSPOON, MELANIE (mewither) | KELLY, SHAWN (skelly64) | 21-0106-I | KELLY, SHAWN (skelly64) | 15000 | 15000 | 1936-11-05 09:36 | 44365 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 06/11/21: Design Complete * 06/18/21: All Year End PO's Closed
IF | 0 | BA-2078 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | PARKING DECK REPAIR YEAR 3 | PARKING DECK REPAIR YEAR 3, provide recommended list of repairs to all parking decks. | 44364.5996 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 21-0170-I | SMITH, RYAN (rsmit341) | 292000 | 292000 | 1908-03-18 | 44501 | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 08/01/21: Drawings for Year 3 Work Complete for Review * 09/01/21: Drawings Reviewed & PO's Issued * 09/01/21: Construction Start * 12/13/21: Construction Completed * 01/17/22: Project Closeout Complete
IF | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0055 | Facilities Management & Police & Public Safety | JW CLAY & SNYDER RD MODIFICATION | improvement to the JW Clay and Robert Snyder Roads | 44053.4871 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | KUGLER, BRIAN (bhkugler) | 0 | 785883 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * Tentative Construction Duration: 04/30/21 - 09/24/21 * 04/30/21: Construction Start * 09/24/21: Construction Complete * 10/30/21: Project Closeout Complete - NOTES / ISSUES / CONCERNS: * Consultant: EMH&T * Contractors: MV Momentum
IF | 1 | BA-1830 | In Design | Informal Projects | 13115 | Safety and Security | 0055 | Facilities Management & Police & Public Safety | FM & POLICE BLDG - RM 281 - RADIO INFRASTRUCTURE | FM & Police Building - Room 281 - Radio Infrastructure Upgrade | 43593.4322 | HILL, MICHELLE (mphilipp) | BARNES, RICKY (rbarne29) | BARNETT, DENISE (dbarne33) | LOVE, DAVID (dflove) | 19-0219 | LOVE, DAVID (dflove) | 163120 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES * 06/03/21: SCO Approval Received * 06/07/21: Construction Start (6 Weeks) * 07/09/21: Electrical Complete * 08/11/21: Construction Complete * 08/27/21: Closeout Complete - NOTES / ISSUES / CONCERNS: * Consultants: Motorola * Contractors: Motorola
IF | 0 | IA-0038 | Construction | Informal Projects | 30900 | Athletics Admin/Support | 2134 | Hammer Throw Field 5 | HAMMER THROW FIELD 5 RENOVATION | Concrete pad at hammer throw to eliminate water issues. | 44334.5511 | FERGUSON, JAMES (jcfergus) | FERGUSON, JAMES (jcfergus) | SPEASE, DARIN (dspease) | KUGLER, BRIAN (bhkugler) | 21-0149-I | KUGLER, BRIAN (bhkugler) | 43582 | 54082 | 0 | 44407 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 05/31/21: Awaiting Athletics Scope & Budget Approval * Tentative 2 Week Construction Duration - NOTES / ISSUES / CONCERNS: * Consultant: PDC Design - Build
IF | 2 | BA-1865 | Construction | Informal Projects | 10400 | Business Services AVC | 0029 | Housing and Residence Life | HOUSING & RESIDENCE LIFE LOADING DOCK LADDER | HRL, Loading Dock Ladder, add metal ladder at the catering loading dock between the two truck bays with roll over grab bars. This is required as drivers are jumping off dock rather than using nearby stairs. | 43766.5016 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 20-0091 | KELLY, SHAWN (skelly64) | 1500 | 1500 | 1900-07-02 03:22 | 43889 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 06/18/21: Financial & Project Closeout Complete
IF | 0 | BA-1965 | Construction | Informal Projects | 10400 | Business Services AVC | 0029 | Housing and Residence Life | HRL CATERING SCREEN WALL | HRL, Catering Screen Wall, provide fence or green wall in and around the Catering cart/van parking area as students are cutting through area with near misses and some students jumping off the loading dock presenting lots of safety issues. Please ass | 43992.3306 | HOLMES, ROBERT (rholme16) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 20-0247-I | KELLY, SHAWN (skelly64) | 10000 | 10000 | 1927-05-18 | 44253 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES * 06/25/21: 100% Construction Complete * 07/09/21: Project Closeout Complete
IF | 0 | AA-1750 | Scope & Budget Requested | Informal Projects | 24204 | OneIT-Planning & Administration | 0001 | Kennedy | KENNEDY ENVELOPE REPAIR | Kennedy - Building Envelope Structural Repair - Column Footing Crack and Exterior Mortar Falling Out - request for Scope and Budget only. | 44340.5308 | HAJDUK, MICHAEL (mhajduk) | HAJDUK, MICHAEL (mhajduk) | VITALLO, JUDY (jvitallo) | SMITH, RYAN (rsmit341) | 21-0150-I | SMITH, RYAN (rsmit341) | 0 | 0 | 0 |  | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 07/30/21: Submit Scope & Budget for Funding & Approval * TBD: Review Proposal and secure funding to move project forward in FY 21-22.
IF | 2 | BA-1471 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0011 | King | KING EMERGENCY POWER SWITCHES | FPFM: King Building: Add Two Emergency Power Automatic Transfer Switches: Per State Electrical Inspector, King Bldg. occupants are at risk; critical life safety features are missing. Point of Contact: Tom MacNab. Assign to Mac Fake. | 42607.3218 | FAKE, WILLIAM (wmfake) | CEALLAIGH, SHERRYL (sceallai) | CEALLAIGH, SHERRYL (sceallai) | LOVE, DAVID (dflove) | 17-0036 | LOVE, DAVID (dflove) | 54800 | 54800 | 1925-04-27 22:48 | 42853 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 07/05/21: Final DD Design Complete & Reviewed by SCO - NOTES / ISSUES / CONCERNS: * Consultants: McKim & Creed * Upon completion of design the project will be placed On Hold until funding can be secured for construction.
IF | 0 | BA-2048 | Construction | Informal Projects | 10400 | Business Services AVC | 1087 | Lot CRI 1A | LOT CRI 1A CRACK SEAL & SEAL COAT | LOT CRI 1A CRACK SEAL & SEAL COAT, provide crack seal and seal coat for summer maintenance. | 44307.5793 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 21-0129-I | SMITH, RYAN (rsmit341) | 4500 | 4500 | 0 | 44439 | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 08/23/21: Construction Completed * 09/01/21: Financial Closeout Complete
IF | 0 | BA-2049 | Construction | Informal Projects | 10400 | Business Services AVC | 1077 | Lot 23 | LOT 23 CRACK SEAL & SEAL COAT | LOT 23 CRACK SEAL & SEAL COAT, provide crack seal and seal coat for summer maintenance. | 44307.5794 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 21-0130-I | SMITH, RYAN (rsmit341) | 19000 | 19000 | 0 | 44439 | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 08/23/21: Construction Completed * 09/01/21: Financial Closeout Complete
IF | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 1054 | Lot 5A | LOT 5A | re-alignment of lot 5A | 43788.59 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | 702248.85 | 743155 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * Project Currently On Hold pending discussion with Parking and Transportation * COMPLETE_ SCO Approval To Bid of 90% Construction Documents & Specifications * Project currently ready to bid contingent on East Village Infrastructure (EVI) Project moving forward. * Tentative Timeline for Advertising for Bid to Contractor Award - 8 Weeks * Tentative Timeline for Construction Start to Construction Completion - 120 Days - NOTES / ISSUES / CONCERNS: * Consultant: Dewberry * Project construction contingent on (EVI) bidding within budget. * Lot 5A Add Alternates and final project scope contingent on Add Alternates selected as part of (EVI).
IF | 0 | BA-2047 | Construction | Informal Projects | 10400 | Business Services AVC | 1083 | Lot CRI 2 | LOT CRI 2 CRACK SEAL & SEAL COAT | LOT CRI 2 CRACK SEAL & SEAL COAT, provide crack seal and seal coat for summer maintenance. | 44307.5791 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 21-0128-I | SMITH, RYAN (rsmit341) | 12000 | 12000 | 0 | 44439 | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 08/23/21: Construction Completed * 09/01/21: Financial Closeout Complete
IF | 0 | IA-0037 | Construction | Informal Projects | 30900 | Athletics Admin/Support | 2108 | McColl-Richardson Field | JERRY RICHARDSON STADIUM FIELD CONSULT | Consultation for Jerry Richardson Stadium Field replacement. | 44257.687 | FERGUSON, JAMES (jcfergus) | FERGUSON, JAMES (jcfergus) | SPEASE, DARIN (dspease) | KUGLER, BRIAN (bhkugler) | 21-0097-I | KUGLER, BRIAN (bhkugler) | 260000 | 260000 | 236441.15 | 44293 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 05/18/21: Construction Start * 06/25/21: Construction Complete * 07/30/21: Project Closeout Complete - NOTES / ISSUES / CONCERNS: * Consultant: Fit Fields * Contractor: AstroTurf
IF | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0020 | McEniry | MCENIRY CHILLER | replace chiller | 44203.5919 |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | KELLY, SHAWN (skelly64) | 0 | 1057404.3 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 05/19/21: Project Kick-Off Meeting Scheduled * 05/30/21: 50% Completed for Internal Review * 06/11/21: Page Turn Onsite Walk Through Completed * 06/25/21: 90% CD's Completed and Sent for SCO Review - NOTES / ISSUES / CONCERNS: * Consultant: CMTA * Tentative Construction Duration: 11/01/21 - 06/01/22
IF | 0 |  | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0020 | McEniry | McEniry Roof Repl | repl roof on McEniry | 44082 |  | HORNE, KATHRYN (khorne16) | CEALLAIGH, SHERRYL (sceallai) |  | 21-0026-F | CEALLAIGH, SHERRYL (sceallai) | 0 | 0 | 0 |  | Consultants / Contractors: * Consultant: SKA * Contractors: TBD Milestones: * SKA submitted report on of review spec's and wall flash details provided by Tremco. Site visit held on Feb 9th. SKA recommended extensive revisions to Tremco details.
IF | 0 | BA-2024 | Construction | Informal Projects | 30400 | University Development AVC | 0020 | McEniry | MCENIRY GLOBE SCULPTURE | Globe sculpture purchase and site modifications to accommodate the use/viewing of it. To be located adjacent to the Geography and Earth Sciences Department housed in McEniry. | 44251.7571 | SHEHEE, AMY (ashehee) | SHEHEE, AMY (ashehee) | VERRET, GREGORY (gverret) | KUGLER, BRIAN (bhkugler) | 21-0095-I | KUGLER, BRIAN (bhkugler) | 37600 | 37600 | 1910-07-19 12:29 | 44408 | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * Artist and Structural Engineer finalizing design for construction * Globe Installation Scheduled for Mid September
IF | 0 | BA-2039 | Req Scope & Budget Review | Informal Projects | 13950 | FM Maintenance Operations | 0019 | Rowe | ROWE 132, 252, 2ND FL WATER INTRUSION | 1) Standing water in main gallery room 132 each time it rains. Joints in ceramic tile are cracking and then coming loose. Roof drain scupper is likely source of water. Proposed solution: relocate roof scupper to side of building with an exterior down | 44285.5772 | KELLY, SHAWN (skelly64) | ROGERS, MICHAEL (mroger59) | WITHERSPOON, MELANIE (mewither) | SMITH, RYAN (rsmit341) | 21-0119-I | SMITH, RYAN (rsmit341) | 6000 | 0 | 0 |  | "- PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 06/28/21: Receive REI Engineering Proposal for Assessment * 07/12/21: Scope & Budget Submitted for FBO Funding Approval * TBD: Review Proposal and secure funding to move project forward in FY 21-22.
IF | 0 | SA-0469 | Construction | Informal Projects | 30000 | Health Services | 0065 | Student Health Center | STUDENT HEALTH CENTER AIR HANDLER | Repair an Air Handler Unit at the Student Health Center | 44033.5929 | BARRETT, LACRISSA (lbarre11) | FLORES, CLAUDIA (cflores3) | BARRETT, LACRISSA (lbarre11) | SMITH, RYAN (rsmit341) | 21-0016-I | SMITH, RYAN (rsmit341) | 13490 | 296347 | 295688.18 | 44317 | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 07/30/21: Commissioning Complete * 08/27/21: Construction Complete * 09/24/21: Project Closeout Complete
IF | 2 | BA-1747 | Req Scope & Budget Review | Informal Projects | 10400 | Business Services AVC | 1007 | Union Deck | UNION DECK BLUE LIGHT PHONES | UNION DECK Blue Light Phones, add additional blue light phones.Per 10/17/18 email from Troy Russell - the two dead emg phones on the 6th level of the existing deck have been removed until project replaces them along with the existing stairwell #2.Als | 43390.65 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | LOVE, DAVID (dflove) | 19-0095 | LOVE, DAVID (dflove) | 37400 | 0 | 0 |  | - PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * 05/04/21: Scope & Budget to Customer - NOTES / ISSUES / CONCERNS: * Tentative Installation period pending PPS & IT approvals and funding. * Review with One IT to establish path and cost for connection to E-phone network for additional locations identified by PPS. * Work will need to be during holiday break between Thanksgiving and Christmas due to location of emergency phone locations.
SA | 6 | SA-0388 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC ARENA BB & CURTAIN - LOW VOLTAGE | Change existing retractable basketball goals and mechanical partition curtain systems in Halton arena from 120v to low voltage. | 43307.5982 | MOON, STUART (sgmoon) |  | BARNES, TRENT (tbarne21) | LANIER, LISA (llanier) | 19-0038 | LOVE, DAVID (dflove) | 0 | 0 | 0 |  | 05/24/2021: Funding does not exist for this project, Cynthia requested it to remain on hold.
IF | 6 | SA-0397 | Project On Hold Design Services | Informal Projects | 29700 | Housing and Residence Life | 0503 | Scott Hall | SCOTT HALL TO SOVI BRIDGE | request for FM Projects to evaluate and design a new (replacement) path from Scott Hall Bridge to SOVI (Dining Hall) lower level. | 43403.6248 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | KELLY, SHAWN (skelly64) | 19-0072 | KELLY, SHAWN (skelly64) | 10000 | 10000 | 1908-05-24 04:48 | 43728 | PROJECT NOTES UPDATED: 05/31/21 - MILESTONES: * Project on hold till receive further direction and funding from HRL & FM AVC. - NOTES / ISSUES / CONCERNS: * Consultant: McAdams * Project original proposed to be split funded between FM & HRL prior to Pandemic. * Survey and SD Design currently completed.
SA | 2 | SA-0461 | Construction | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC SALONS A/V DESIGN & CONSTRUCTION | Project is to replace and upgrade Salon A/V. Project would include replacement of projectors and screens, additional projectors and screens, increased capability of streaming and conferencing, integration of cable TV, and necessary upgrades to audio | 43906.3607 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | SPATARO, EVAMARIE (espataro) | 20-0201-I | CAUDLE, AMANDA (afelock) | 25000 | 170000 | 1976-04-28 11:17 | 44074 | (8-2-21) Work to begin 8-23 and complete by 9-17.
SA | 0 | SA-0465 | Construction | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC OFFICE LEAK ROOM 303 | BSAC - Room 303. There is a substantial leak in office 303 but upon prior inspections the leak does not seem to come from the roof but perhaps issues with the gutter system or the window panes. We need a contractor to evaluate the source of the probl | 44011.6123 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | NEILSON, JOHN (jneilson) | 20-0261-I | NEILSON, JOHN (jneilson) | 5000 | 18600 | 1932-06-05 | 44316 | 07/27/2021 - Will receive informal bids by email on 07/22 by 2:00pm. The lowest of 2 bidders was IL Long at $154,800, which was approx. $95,000 lower than the other bidder.
SA | 0 | SA-0472 | Construction | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC SALONS A/V FFE | Split for the A/V project for Electrical and HVACProject should be forwarded to Eva Spataro who is working on the existing A/V project. | 44153.6323 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | CAUDLE, AMANDA (afelock) | 21-0056-I | CAUDLE, AMANDA (afelock) | 265000 | 265000 | 0 | 44370 | (8-2-21) Work to begin 8-23 and complete by 9-17.
SA | 6 | SA-0424 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION LED LIGHTING RETROFIT | Student Union - Entire BuildingStudent Union wants to increase sustainability by reducing energy consumption and decrease annual maintenance cost for replacement fluorescent lights by retrofitting lighting to LED. This project aligns with UNC policy | 43640.4007 | BROWN, JOSHUA (jbrow450) | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | LANIER, LISA (llanier) | 20-0022 | LOVE, DAVID (dflove) | 43000 | 0 | 0 |  | 9/22/2020: On hold.
SA | 6 | SA-0439 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC 062 FITNESS ROOM RENOVATION | Fitness room renovation two include two spaces; one space is to remain a multipurpose room for events and the other space is to be converted into offices and storage space. Would like to keep as much of original hardwood floor as possible. | 43747.4006 | STONE, CYNTHIA (cstone26) |  | STONE, CYNTHIA (cstone26) | NEILSON, JOHN (jneilson) | 20-0070 | NEILSON, JOHN (jneilson) | 0 | 0 | 0 |  | 07/07/2020 -Project on hold while Customer determines if they have other options.
SA | 6 | SA-0440 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC 334A-E SALONS LIGHTING UPDATE | Replace light fixtures, and update control system to accommodate new lighting. | 43747.404 | STONE, CYNTHIA (cstone26) |  | STONE, CYNTHIA (cstone26) | LANIER, LISA (llanier) | 20-0071 | LOVE, DAVID (dflove) | 0 | 0 | 0 |  | 05/24/2021: Eva's update 09/22/2020 - Project can be FF&E. Customer holding for funding.
SA | 6 | SA-0441 | Project On Hold Design Services | Informal Projects | 28900 | University Recreation | 0017 | Belk Gymnasium | BELK GYM 127 RECONFIGURE | Adding a door and wall to create a designated space to be used after UREC moves from Belk Gym to UREC building. Separating COR10 from 127 | 43754.5629 | BELL, ROBERT (rbell16) |  | BARRETT, LACRISSA (lbarre11) | NEILSON, JOHN (jneilson) | 20-0074 | NEILSON, JOHN (jneilson) | 9987.5 | 0 | 0 |  | 07/07/2020 -Project on Hold per email from Robbie Bell 02/24/20. Overall price ($9,988) was more then they expected. They will use the space as is for now to determine necessity of project.
SA | 0 | SA-0442 | Construction | Informal Projects | 29000 | Cone Univ Center | 0017 | Belk Gymnasium | BELK GYM 120 VENTURE MOVE | Venture has been approved to move from Cone to Belk gym. Within this project includes: coordinating a move of the staff, office furnishing needs, space renovations in Belk for storage space. As this project is related to project SA-0441 it could be | 43762.5896 | MEEHAN, MORGAN (mmeeha11) | MEEHAN, MORGAN (mmeeha11) | DALE, JEREMY (jdale8) | WELLS, ALICIA (awells43) | 20-0080 | SISCO, ASHLEY (asisco1) | 160000 | 160000 | 2068-09-14 23:46 | 44043 | (8/02/21) Move of office area to take place August 3rd. Working on quotes for signage, millwork for 009 space. Waiting on product for 009 space to arrive which will be late August.
IF | 6 | SA-0444 | Project On Hold Design Services | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE NORTH ROOF REPLACEMENT | Cone North Roof Replacement - Fully remove existing system to replace the Cone North Building Roofing System. | 43808.5443 | MERCK, DONNA (dlmerck) |  | HARRIS, MELODY (mhharris) | BOAL, JOHN (jboal1) | 20-0112 | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 7/27/2021: Project on hold.
SA | 6 | SA-0450 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION M101 ESPORTS LOUNGE | There is a space identified in the Student Union as a potential opportunity for an Esports Lounge. Need to determine if it is feasible in the space given the needs of the group. Need feasibility information by 1/28 and then will proceed further if ne | 43846.4574 | MEEHAN, MORGAN (mmeeha11) |  | DALE, JEREMY (jdale8) | CAUDLE, AMANDA (afelock) | 20-0137 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Informal budget provided to Morgan Meehan 1-27-20. Pending approval to proceed. Placed on Hold April 27.
SA | 6 | SA-0454 | Project On Hold Design Services | Informal Projects | 29700 | Housing and Residence Life | 0544 | Witherspoon | WITHERSPOON CABINET & COUNTERTOP REPLACEMENT | Witherspoon Hall.. We want to replace the countertops and cabinets in the kitchens in similar configuration to what's currently in the apartments. ..per Alan Hinton 757-692-9020 | 43872.6577 | FOUST, KATHY (kfoust3) |  | BUNKER, DEBRA (dbunker) | NEILSON, JOHN (jneilson) | 20-0173 | NEILSON, JOHN (jneilson) | 353194.69 | 0 | 0 |  | 07/07/2020 - project on hold due to cost considerations
SA | 6 | SA-0455 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 340 POWER UPGRADE | Student Union would like to add additional power to the multi purpose room 340. We are looking at 100A, 3 phase, 5 wire, 120/208V. Requesting Eva Spataro on this project | 43879.6685 | BROWN, JOSHUA (jbrow450) |  | MEEHAN, MORGAN (mmeeha11) | LANIER, LISA (llanier) | 20-0186 | LOVE, DAVID (dflove) | 0 | 0 | 0 |  | 05/24/2021: Eva's update 09/22/2020- Sent scope and budget to customer. Customer taking S&B to lobby for funding.
SA | 0 | SA-0408 | Scope & Budget Requested | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE SOUTH 3 MODERNIZATION | Cone Center - South 3: Upgrade and modernize South 3 level of Cone Center. Collaborate with Director and Associate Director to establish design options and features. | 43496.5781 | MERCK, DONNA (dlmerck) |  | MERCK, DONNA (dlmerck) | CAUDLE, AMANDA (afelock) | 19-0147 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Placed on hold 7-2-20. Project removed from hold status and kickoff meeting scheduled for June 29. Selecting design firm off of open end.
SA | 0 | SA-0475 | Scope & Budget Requested | Informal Projects | 29000 | Cone Univ Center | 0005 | Cone University Center | CONE SOUTH 2 AUTOMATIC DOOR REPLACEMENT | Room 206 - Replace the South 2 ADA doors per the approved quote 001303 from DH Pace. This door is the only ADA route from the Cone Visitor Deck. John Boal is familiar with this project and has the drawings and full scope of work. | 44239.5552 | MERCK, DONNA (dlmerck) | MERCK, DONNA (dlmerck) | MEEHAN, MORGAN (mmeeha11) | BOAL, JOHN (jboal1) | 21-0080-I | BOAL, JOHN (jboal1) | 0 | 0 | 0 |  | 7/27/2021: Repair package has arrived and installation is scheduled for today.
SA | 0 | SA-0477 | Construction | Informal Projects | 29300 | Student Union | 0005 | Cone University Center | CONE 348-349 RENOVATIONS | Cone Center- 348-349 - This project will encompass the work that is the responsibility of Cone Center administration during renovations. This includes carpet, vision kits in office doors, 348C furniture | 44243.7202 | MEEHAN, MORGAN (mmeeha11) | MEEHAN, MORGAN (mmeeha11) | MERCK, DONNA (dlmerck) | LANIER, LISA (llanier) | 21-0082-I | CAUDLE, AMANDA (afelock) | 26000 | 26000 | 1965-10-25 16:05 | 44347 | (8-2-21) Project complete; waiting to close out for added scope considerations. Customer would like to add Inpro wall protection and chair rail to conference room. Additional matching chair rail needed at lobby wall at seating area. Also considering quote received from Lockshop for adding ADA actuator at lobby door.
SA | 6 | SA-0462 | Project On Hold Design Services | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0046 | Barnhardt Student Activity Center | SAC SALONS AND PREFUNCTION CARPET | Project is to gather estimates and designs on replacing the carpet inside and outside of the SAC Salons. | 43906.3608 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | HILL, CAROLINE (cmhill2) | 20-0202-I | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 10/26/2020 - Reached out to Customer and project funding is under evaluation. Project will still need to be on hold for now.
SA | 0 | SA-0407 | Req Scope & Budget Review | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0077 | Halton-Wagner Tennis Complex | HALTON TENNIS COMPLEX LOWER HALL FLOODING | The lower hallways of the Halton Tennis Complex flood when there is heavy rain. Zone 1 has performed some modifications to the weep holes in the brick which has helped but we are still getting some flooding. The water drains towards the building inst | 43489.7061 | BARNES, TRENT (tbarne21) | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | LANIER, LISA (llanier) | 19-0134 | NEILSON, JOHN (jneilson) | 34000 | 0 | 0 |  | 07/16/2021 Received Design Fee proposal for addressing water infiltration by C Design. Reviewed with customer. Waiting for OK to proceed and funding. Athletics advised waiting to re-visit in the Winter after other project priorities are complete.
SA | 0 | SA-0473 | Scope & Budget Requested | Informal Projects | 29500 | Student Activity Ctr and Venue Mgmt | 0078 | Judy W. Rose Football Center | JUDY ROSE ADDITIONAL CAMERAS LOCKER ROOM | This is a project request to create a quote to add 2 additional cameras in the Judy Rose Football Center. These cameras would oversee the 2 entrances/exits to the football home locker room (008). I have already spoke with Lisa Lanier and David Love a | 44211.6692 | RICE, JARRETT (jrice39) | RICE, JARRETT (jrice39) | STONE, CYNTHIA (cstone26) | LANIER, LISA (llanier) | 21-0064-I | LOVE, DAVID (dflove) | 0 | 0 | 0 |  | 07/12/2021: Cameras on order through PPS.
SA | 0 | SA-0474 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0564 | Martin Hall | MARTIN HALL SHOWER REPLACEMENT FY21 | We need to replace the remaining showers in Martin Hall with the same shower units we have used the last two years. | 44229.3586 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | CAUDLE, AMANDA (afelock) | 21-0070-I | CAUDLE, AMANDA (afelock) | 142000 | 142000 | 2272-12-10 07:41 | 44256 | (8-2-21) Met with customer on site 2-1-21. Provided budget pricing to customer 2-19-21. Purchase orders issued 3-4-21. Work scheduled to begin 5-17-21. On schedule to complete the first week of August.
SA | 0 |  | Created | Capital Projects | 13900 | Facilities Management AVC | 0069 | Popp Martin Student Union | STUDENT GOVERNMENT OFFICE RENOVATIONS | Student Government Office Complex (2nd floor) renovation to allow students to see activities going on in the space from outside the suite and better use of space. | 43143.4117 |  |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | CAUDLE, AMANDA (afelock) | 1210502.76 | 1102723.5 | 0 |  | (8-2-21) Consultants: Little - designer Received email from Karen Shaffer on April 14, 2021 that project is being funded and ready for re-start. Kickoff meeting scheduled for April 27 at 10am. Working with Little on fee proposal to complete design and bid project. Anticipate construction to start early December 2021.
SA | 6 | SA-0470 | Project On Hold Design Services | Informal Projects | 30000 | Health Services | 0065 | Student Health Center | SHC 293 CRC RELOCATION | Renovating SHC 293 for CRC program in phases. This would be phase one to include: General construction: soundproof between 293 and AVC, Carpet, Paint, power by window, card reader relocated, move services and ITS data drops. | 44049.3546 | BARRETT, LACRISSA (lbarre11) |  | BARRETT, LACRISSA (lbarre11) | CAUDLE, AMANDA (afelock) | 21-0019-I | CAUDLE, AMANDA (afelock) | 20000 | 20000 | 1907-03-22 14:24 | 44137 | (8-2-21) Carpet in hand. Project on hold per Beau Dooley.
IF | 6 | SA-0471 | Project On Hold Design Services | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION ROOF LEAKS | PMSU has two active leaks in Stairwell 001 and 377. We have worked with renovations shop in the past with no real resolution about fix. We are requesting a Project Manager assist to investigate and provide a permanent repair. | 44099.5178 | BROWN, JOSHUA (jbrow450) | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | SMITH, RYAN (rsmit341) | 21-0031-I | SMITH, RYAN (rsmit341) | 3600 | 3600 | 1909-07-31 | 44378 | - PROJECT NOTES UPDATED: 07/12/21 - MILESTONES: * 03/01/21: Awaiting customer funding approval to move forward. * 02/23/21: Delivered Site Assessment Report to Customer * 07/12/21: Project Placed on Hold by Shawn Kelly Pending Customer Funding & Approval * If approved and funded, move forward on completing CD's for bidding and repair work.
SA | 2 | SA-0409 | Scope & Budget Requested | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 200 UPGRADES | Student Union - 200 - Aesthetic and other upgrades to room 200 to reflect new naming of space as James M. Hoppa Room. | 43508.55 | MEEHAN, MORGAN (mmeeha11) | BROWN, JOSHUA (jbrow450) | MARTIN, KAREN (kmart126) | HILL, CAROLINE (cmhill2) | 19-0156 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/2/2021 - Customers are revisiting funding to see if we can move forward with project.
SA | 0 | SA-0411 | Construction | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 150 NORMS UPGRADES | Student Union - 150 - Upgrades to furniture, gaming equipment, technology in Norms space in the Student Union | 43509.6485 | MEEHAN, MORGAN (mmeeha11) | BROWN, JOSHUA (jbrow450) | DALE, JEREMY (jdale8) | HILL, CAROLINE (cmhill2) | 19-0160 | HILL, CAROLINE (cmhill2) | 2800 | 90800 | 1906-06-17 12:00 | 44012 | 6/2/2021 - Funding has been approved and we are moving forward with project. Purchase Orders have been submitted. Project will be completed by September 2021.
SA | 0 | SA-0467 | Scope & Budget Requested | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION PLUMBING DRAIN LINES STUDY | A project to fully investigate these apparent systemic issues and provide recommendations to bring the system into reliable operating conditions. Can original construction team involvement for repair/remediation/cost recovery? We would like the fee | 44020.336 | BROWN, JOSHUA (jbrow450) | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | LANIER, LISA (llanier) | 21-0005-I | NEILSON, JOHN (jneilson) | 0 | 0 | 0 |  | 07/16/2021 - Met with customer and MO on 04/14. Called McKim & Creed for further background info. Customer received Aux. Services drain maintenance protocols. Reconvene with further info prior to proceeding with investigation work. Need to determine fund responsibility for repairs. 7/15/21 - JN contacted the piping manuf., Charlote Pipe and Foundry, who will help determine the cause. SU staff will assemble information needed by Charlotte Pipe.
SA | 0 | SA-0479 | Scope & Budget Requested | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION FABRIC WALL REPLACEMENT | The Student Union has fabric whisper walls system that were installed in 2010. We want to explore replacing fabric. A scope and budget is requested based per floor. | 44279.573 | BROWN, JOSHUA (jbrow450) | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | LANIER, LISA (llanier) | 21-0112-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 |  | (8/02/21) Meeting with Morgan 8/11/21
SA | 0 | SA-0483 | Scope & Budget Requested | Informal Projects | 29300 | Student Union | 0069 | Popp Martin Student Union | STUDENT UNION 280 SUITE RENOVATION | Student Union 280 Suite Renovation to add offices and relocate the reception area. | 44403.7021 | MEEHAN, MORGAN (mmeeha11) | MEEHAN, MORGAN (mmeeha11) | DALE, JEREMY (jdale8) | CAUDLE, AMANDA (afelock) | 22-0011-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Reaching out to customer to review scope of work. Will submit scope & budget by 8-6-21.
SA | 2 | SA-0457 | Req Scope & Budget Review | Informal Projects | 30000 | Health Services | 0065 | Student Health Center | SHC OUTDOOR BUILDING SIGNS | Project request for outdoor building signage. | 43880.3633 | FLORES, CLAUDIA (cflores3) | SIMPSON, BRANDI (BrandiSimpson) | BARRETT, LACRISSA (lbarre11) | TERRY, STEPHEN (slterry) | 20-0218-I | TERRY, STEPHEN (slterry) | 13500 | 0 | 0 |  | 06/23/21. No change. Budget review. Customer said to hold.
SA | 0 | SA-0476 | Scope & Budget Requested | Informal Projects | 29200 | Student Fee Commission | 2101 | Van Landingham Glen | BOTANICAL GARDENS APRIL 30TH MEMORIAL | Design and installation of a permanent public sculpture to contain and display remembrance stones created by faculty, staff and students. Sculpture will be placed in the Botanical Gardens. | 44243.3861 | HURST, CASEY (cphurst) | HILL, CAROLINE (cmhill2) | HARRIS, MELODY (mhharris) | HILL, CAROLINE (cmhill2) | 21-0081-I | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 |  | 6/2/2021 - Working on coordinating with Customers. Reviewing drawings and will meet with Contractor's soon. Anticipated completion date, TBD.
SA | 2 | SA-0459 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0544 | Witherspoon | WITHERSPOON FALLING KEYSTONES | Please put in an Archibus request for Design Services. We have some failing keystones underneath a few balconies at Witherspoon Hall and need some help determining the proper fix.Thanks,Donny | 43887.6382 | FOUST, KATHY (kfoust3) |  | BUNKER, DEBRA (dbunker) | LINGER, JOSHUA (jlinger2) | 20-0189 | NEILSON, JOHN (jneilson) | 15537.5 | 275287.5 | 2214-03-31 00:43 | 44071 | 07/27/2021 - Heartland low bid. Issued PO; Construction to begin July 20th for demo. Awaiting split-face block (material delay) for full construction schedule and completion date. Demolition began on 7/23/21. Demo and build back of 17 locations will occur in groups of 4.
BA | 6 | UA-0039 | Project On Hold Design Services | Informal Projects | 30300 | Alumni Affairs | 0088 | Hauser Alumni Pavilion | HAUSER ALUMNI PAVILION SECURITY DOORS | Project to add garage door type security between the brick columns . Cleo - use 138062. Contact Scott Plunkett at 7-7792 | 43053.3936 | PLUNKETT, SCOTT (ssplunke) |  | WIDMAIER, CLEO (cswidmai) | CAUDLE, AMANDA (afelock) | 18-0101 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 |  | (8-2-21) Placed on hold 2-17-20.

## PROJECTS in CLOSEOUT
Projects in Closeout
Unit | Campus Priority | Control Code | Project Status Block | Project Type |  | Sub Department Name |  | Building Name | Project Request Name | Project Description | Date Created |  |  | Project Account Manager | Financial Account Manager | Project Number | Project Coordinator | Scope & Budget | Approved Project Total | Amount Billed |  | Notes
AA | 1 | AA-1556 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0537 | Sycamore | SYCAMORE FF&E | Sycamore FFEThe units that are moving are:Urban Institute_Contact: Jeff MichaelMetropolitan studies_ Contact: Curt WaltonInstitutional research_Contct: Steve Coppola | 2018-10-05 15:11 | HUNTER, KATHY (kdwhaley) |  | MCMANNEN, TONYA (tmcmanne) | WELLS, ALICIA (awells43) | 19-0067F | WELLS, ALICIA (awells43) | 315000 | 419880 | 401514.27 | 2019-02-19 | (6/23/20) Move complete. Finalize punch list items
AA | 0 | AA-1718 | Scope & Budget Requested | Informal Projects |  | Research & Economic Dev. VC |  | Grigg Hall | GRIGG 330 SAFETY SHOWER | Grigg Hall - 330 - We would like a quote to purchase and install a lab safety shower. Is the current plumbing sufficient and can it be tied into the tempered water line? Need an idea of the timeline. | 2020-06-29 14:26 | 20-0258-I | PATEL, NAVINKUMAR (npatel24) | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) |  |  | 0 | 0 | 0 | 2020-04-24 | (7/14/20) Project complete. Working on final invoicing
AA | 1 | AA-1634 | Construction | Informal Projects |  | Academic Affairs VC |  | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | 20-0048 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) |  |  | 27589 | 80000 | 62292.54 | 2020-03-06 | (06-03-20) - Current work Complete. Nancy to provide other sign needs to use remaining balance. Project to remain open.
AA | 0 | AA-1714 | Construction | Informal Projects |  | AISLE |  | Burson | BURSON, CAMERON, COED, CHHS SIMULCAST CLASSROOMS | Burson 115, Cameron 101, COED 065, CHHS 281 we will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | 20-0252-I | PATEL, NAVINKUMAR (npatel24) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) |  |  | 9000 | 9000 | 0 | 2020-02-28 | 06/01/20: Construction Completed 06/26/20: Projected Project Closeout
AA | 0 | AA-1715 | Construction | Informal Projects |  | AISLE |  | Fretwell | FRET, FRIDAY, MCENIRY, DENNY SIMULCAST CLASSROOMS | Fretwll 128, Friday 137, McEniry 117 Denny220. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | 20-0253-I | PATEL, NAVINKUMAR (npatel24) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) |  |  | 9000 | 9000 | 0 | 2019-08-16 | 07/31/20: Construction Complete 08/07/20: Projected Project Closeout Note: Awaiting Special Order Brick to complete Year 1 Masonry Repairs.
AA | 0 | AA-1716 | Construction | Informal Projects |  | AISLE |  | Belk Gymnasium | BELK GYM, DUKE, EPIC SIMULCAST CLASSROOMS | Belk Gym 201, Duke 345, Epic 2222. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | 20-0254-I | PATEL, NAVINKUMAR (npatel24) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) |  |  | 9000 | 9000 | 0 | 2020-02-28 | 07/31/20: Projected Construction Completion 08/14/20: Projected Project Closeout Note: Project delayed due to equipment manufacture production delays caused by Covid-19
AA | 0 | AA-1717 | Construction | Informal Projects |  | AISLE |  | Rowe | ROWE, SMITH, STORRS, WOODWARD SIMULCAST CLASSROOMS | Rowe 161, Smith 202, Storrs 290, Woodward 155. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:13 | 20-0255-I | PATEL, NAVINKUMAR (npatel24) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) |  |  | 9000 | 9000 | 0 | 2020-04-03 | 100% complete Close out Project
AA | 0 | AA-1724 | Construction | Informal Projects |  | Academic Affairs VC |  | Cameron Hall | CAMERON 217 COVID19 TESTING LAB | Prepare exiting lab area in Cameron Lab Suite 271 to be ready for use as COVID 19 Testing Lab per description provide by Angelica Martins | 2020-07-16 11:39 | 21-0015-I | PATEL, NAVINKUMAR (npatel24) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) |  |  | 5100 | 5100 | 0 | 2020-08-30 | 100% complete project closeout phaset
AA | 1 | AA-1704 | Construction | Informal Projects |  | Academic Affairs VC |  | Cafeteria Activities Building | CAB KITCHEN EQUIPMENT DEMO | CAB-Kitchen Equipment Demolition | 2020-03-16 08:41 | 20-0207-I | BOAL, JOHN (jboal1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 53382 | 60882
AA | 0 | AA-1636 | Construction | Informal Projects |  | Academic Affairs VC |  | Fretwell | FRETWELL 407 SOCIOLOGY LAB | Convert existing small classroom in Fretwell 407 into a Sociology lab. | 2019-08-15 12:57 | 20-0050 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 17171 | 17171 |  | This project is closed out.
AA | 1 | AA-1634 | Construction | Informal Projects |  | Academic Affairs VC |  | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | 20-0048 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) |  | 27589 | 80000
AA | 1 | AA-1707 | Construction | Informal Projects |  | Academic Affairs VC |  | College of Education | COED 002-009 ACTIVE LEARNING CLASSROOM | COED Building - Rooms 002, 003, 005, 007, 009 - This project is meant to combine rooms 002, 005, and 007 into a large active learning classroom for 128 students. Room 009 would be converted into a graduate bull pin and room 003 would become a semina | 2020-04-09 11:12 | 20-0219-I | CAUDLE, AMANDA (afelock) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) |  | 265000 | 265000 |  | (9.1.20) Work complete
AA | 1 | AA-1635 | Construction | Informal Projects |  | Academic Affairs VC |  | Woodward Hall | WOODWARD VIVARIUM AUTOCLAVE REPLACEMENT | Replace current vivarium autoclave with larger-capacity, internal-boiler autoclave. | 2019-08-15 11:48 | 20-0049 | CAUDLE, AMANDA (afelock) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 200000 | 209000 |  | (8/31/20) Project complete. Waiting on final billing.
AA | 1 | AA-1697 | Construction | Informal Projects |  | Academic Affairs VC |  | Robinson Hall | ROBINSON BELK THEATER ORCHESTRA PIT LIFT | Replacement of Orchestra Lift | 2020-03-16 08:25 | 20-0198-I | CAUDLE, AMANDA (afelock) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 268293.64 | 268293.64 |  | (9-1-20) Work complete - wrapping up punch list items.
AA | 1 | AA-1641 | Construction | Informal Projects |  | Performing Arts Services (PAS) |  | Robinson Hall | ROBINSON 220 FACULTY OFFICE | Need to create a new faculty office from the alcove part of Robinson 220 that is adjacent to 221 and create a separate entrance into the hallway. This project should be similar to the one recently done for Robinson 124. | 2019-08-27 17:32 | 20-0075 | HILL, CAROLINE (cmhill2) | LUEKE, BEVERLY (bblueke) |  | RUCKER, BETH (aefird) |  |  | 8200 | 17400 |  | (9/2/20) project complete
AA | 0 | AA-1636 | Construction | Informal Projects |  | Academic Affairs VC |  | Fretwell | FRETWELL 407 SOCIOLOGY LAB | Convert existing small classroom in Fretwell 407 into a Sociology lab. | 2019-08-15 12:57 | 20-0050 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 17171 | 17171 |  | (09.01.2020) Work Complete
AA | 1 | AA-1634 | Construction | Informal Projects |  | Academic Affairs VC |  | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | 20-0048 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  |  | 27589 | 80000 |  | (09.01.2020) Work Complete
AA | 1 | AA-1623 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 1040 ACTIVE LEARNING CLASSROOM | Colvard Classroom Active Learning | 2019-06-07 13:22 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0008 | CAUDLE, AMANDA (afelock) | 298000 | 298000 | 120458.21 |  | (09.01.2020) Work Complete
AA | 1 | AA-1694 | Construction | Informal Projects | 23700 | Prec Metrology & Intellignt Mfg Ctr | 0057 | Duke Centennial Hall | DUKE 138 350FG MOORE MACHINE RELOC | Duke Centennial Hall - Rooms 132 & 151The following is requested :1. CSA Certified2. 208 3 Phase 30 AMP Breaker /40 AMP Fuses3. (3) 208 1 PHASE 10 AMP Each4. High Pressure Air from BoosterThis is needed to prepare the lab for Moore 350FG machine | 2020-02-25 15:30 | CHASTAIN, JENNIFER (jchasta4) | DUTTERER, BRIAN (bsdutter) | CHASTAIN, JENNIFER (jchasta4) | SPATARO, EVAMARIE (espataro) | 20-0181 | CAUDLE, AMANDA (afelock) | 11000 | 7000 | 5629.57 |  | (09.01.2020) Work Complete
AA | 1 | AA-1707 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0052 | College of Education | COED 002-009 ACTIVE LEARNING CLASSROOM | COED Building - Rooms 002, 003, 005, 007, 009 - This project is meant to combine rooms 002, 005, and 007 into a large active learning classroom for 128 students. Room 009 would be converted into a graduate bull pin and room 003 would become a semina | 2020-04-09 11:12 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | CAUDLE, AMANDA (afelock) | 20-0219-I | CAUDLE, AMANDA (afelock) | 265000 | 265000 | 93125.93 |  | (09.21.20) Waiting on walk off matts, all punch list items complete All interior work is complete and Lab is functional.
AA | 0 | AA-1725 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0000 | Campus | CLASSROOM SOCIAL DISTANCING DIAGRAMS | Generate and provide social distancing diagrams for all campus classrooms showing student seating layout to be achieved for social distancing in light of COVID 19 spread prevention. | 2020-07-22 15:29 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 21-0017-I | FRERE, ELIZABETH (efrere) | 25000 | 24490.1 | 0 |  | (9-22-20) Consultants: Biloba Architecture Contractor: MV Momentum LLC Milestone dates and activities: Construction and punch list complete. Working through final change order paperwork and close out documents.
AA | 0 | AA-1714 | Construction | Informal Projects | 28350 | AISLE | 0038 | Burson | BURSON, CAMERON, COED, CHHS SIMULCAST CLASSROOMS | Burson 115, Cameron 101, COED 065, CHHS 281 we will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0252-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 0 | (9-28-20) Consultants: Biloba Architecture Contractor: MV Momentum LLC Milestone dates and activities: Construction complete. Working through close out documents.
AA | 0 | AA-1715 | Construction | Informal Projects | 28350 | AISLE | 0045 | Fretwell | FRET, FRIDAY, MCENIRY, DENNY SIMULCAST CLASSROOMS | Fretwll 128, Friday 137, McEniry 117 Denny220. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0253-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 7757.63 | 9/21/2020: This project is complete at this time. Awaiting final billing.
AA | 0 | AA-1716 | Construction | Informal Projects | 28350 | AISLE | 0017 | Belk Gymnasium | BELK GYM, DUKE, EPIC SIMULCAST CLASSROOMS | Belk Gym 201, Duke 345, Epic 2222. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:12 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0254-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 15554.3 | (9/29/20) Construction complete. Project to be closed out.
AA | 0 | AA-1717 | Construction | Informal Projects | 28350 | AISLE | 0019 | Rowe | ROWE, SMITH, STORRS, WOODWARD SIMULCAST CLASSROOMS | Rowe 161, Smith 202, Storrs 290, Woodward 155. We will be upgrading equipment for the recording and streaming of classes. We will be using HD Network Solutions | 2020-06-25 09:13 | STRILKA, SCOTT (sstrilka) | STRILKA, SCOTT (sstrilka) | FRANKLIN, JENNY (jfrank36) | PATEL, NAVINKUMAR (npatel24) | 20-0255-I | PATEL, NAVINKUMAR (npatel24) | 9000 | 9000 | 0 | 35455.64 | Consultants/Contractors: *Contractors: MV Momentum Milestones: *09/28/2020 - Project complete. Final billing received.
AA | 1 | AA-1634 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0032 | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0048 | SISCO, ASHLEY (asisco1) | 27589 | 80000 | 77068.84 | 106913.39 | Consultant/Contractors: *Contractor: Heartland Construction Milestones: *09/29/2020 - Project punch list walk held 08/28. Project complete. Final billing issued.
AA | 0 | AA-1636 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 407 SOCIOLOGY LAB | Convert existing small classroom in Fretwell 407 into a Sociology lab. | 2019-08-15 12:57 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0050 | SISCO, ASHLEY (asisco1) | 17171 | 17171 | 15554.3 | 77068.84 | (9/29/20) Project complete. Need to reorder two lamps that came in with missing parts.
AA | 6 | AA-1684 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 114 116 118 120 122, 124 ACT. LEARN. CLRM | Fretwell - 114, 116, 118, 120, 122, 124 - Create new Active Learning Classroom and relocate Math Computer labs from other floors in Fretwell.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 2020-01-14 11:10 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0133 | SISCO, ASHLEY (asisco1) | 28634 | 0 | 0 | 93125.93 | (9-28-20) Construction complete - wrapping up final billing.
AA | 6 | AA-1693 | Project On Hold Design Services | Informal Projects | 18000 | English | 0045 | Fretwell | FRETWELL 275 AND 248C REFRESH | I would like to talk to Ashley Sisco about possible options (seating and mobile wall) for refurbishing the English Department Reception area and lounge.Fretwell 275 and 248C | 2020-02-20 10:55 | WILLIAMS, ANGELA (anwillia) |  | WILLIAMS, ANGELA (anwillia) | SISCO, ASHLEY (asisco1) | 20-0177 | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 | 78988.3 | (10-5-20) Equipment start up complete. Continue monitoring BAS trends. With funds remaining, looking into floor refinish.
AA | 6 | AA-1701 | Project On Hold Design Services | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 314 RENOVATIONS | Fretwell - Suite 314 - Office of Interdisciplinary Studies | 2020-03-16 08:40 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0204-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 | 218096.9 | (10-5-20) Installation complete. Wrapping up final billing.
AA | 1 | AA-1703 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0041 | Storrs | STORRS 230, 222B, 274, 276 RENOVATIONS | Storrs - Rooms 230, 222B, and 274/276 - Additional work and furniture needed to accommodate space changes that will take place as part of the Capital ITS Infrastructure Replacement work in the Storrs building. | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | PAYNE, TODD (tapayne) | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0206-I | SISCO, ASHLEY (asisco1) | 77000 | 77000 | 3869.8 | 0 | Project already complete. Mark Reynolds and Todd Payne confirmed. Please cancel.
AA | 0 | AA-1724 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0042 | Cameron Hall | CAMERON 217 COVID19 TESTING LAB | Prepare exiting lab area in Cameron Lab Suite 271 to be ready for use as COVID 19 Testing Lab per description provide by Angelica Martins | 2020-07-16 11:39 | SCHAUBLE, DONIA (dcooke) | KEENE, PATRICIA (pgkeene) | MCMANNEN, TONYA (tmcmanne) | PATEL, NAVINKUMAR (npatel24) | 21-0015-I | PATEL, NAVINKUMAR (npatel24) | 5100 | 5100 | 0 | 14201.98 | 9/30/2020 - Will finalize invoices and close out project per Customer requests.
AA | 0 | AA-1718 | Scope & Budget Requested | Informal Projects | 24400 | Research & Economic Dev. VC | 0058 | Grigg Hall | GRIGG 330 SAFETY SHOWER | Grigg Hall - 330 - We would like a quote to purchase and install a lab safety shower. Is the current plumbing sufficient and can it be tied into the tempered water line? Need an idea of the timeline. | 2020-06-29 14:26 | MATEEN, ALI (amateen) | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) | PATEL, NAVINKUMAR (npatel24) | 20-0258-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | 117877.71 | 9/30/2020 - Following up with Customers to see how they would like to use their contingency.
AA | 1 | AA-1635 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0056 | Woodward Hall | WOODWARD VIVARIUM AUTOCLAVE REPLACEMENT | Replace current vivarium autoclave with larger-capacity, internal-boiler autoclave. | 2019-08-15 11:48 | SCHAUBLE, DONIA (dcooke) | WILLIAMS, CHANDRA (cwill297) | MCMANNEN, TONYA (tmcmanne) | SPATARO, EVAMARIE (espataro) | 20-0049 | CAUDLE, AMANDA (afelock) | 200000 | 209000 | 87436.12 | 0 | Dependent on two other Colvard projects, no action until those projects move forward and have a clear schedule and plan.
AA | 0 | AA-1636 | Punch List | Informal Projects | 15100 | Academic Affairs VC | 0045 | Fretwell | FRETWELL 407 SOCIOLOGY LAB | Convert existing small classroom in Fretwell 407 into a Sociology lab. | 2019-08-15 12:57 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | SISCO, ASHLEY (asisco1) | 20-0050 | SISCO, ASHLEY (asisco1) | 17171 | 17171 | 15554.3 | 35455.64 | Consultants/Contractors: *Contractors: MV Momentum Milestones: *10/06/2020 - Project complete. Final billing received.
AA | 1 | AA-1697 | Construction | Informal Projects |  | Academic Affairs VC |  | Robinson Hall | ROBINSON BELK THEATER ORCHESTRA PIT LIFT | Replacement of Orchestra Lift | 2020-03-16 08:25 | 20-0198-I | CAUDLE, AMANDA (afelock) |  | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | 268293.64 | 268293.64 | 218096.9 | 15554.3 | (10/05/20) Construction complete. Project to be closed out.
AA | 1 | AA-1641 | Construction | Informal Projects |  | Performing Arts Services (PAS) |  | Robinson Hall | ROBINSON 220 FACULTY OFFICE | Need to create a new faculty office from the alcove part of Robinson 220 that is adjacent to 221 and create a separate entrance into the hallway. This project should be similar to the one recently done for Robinson 124. | 2019-08-27 17:32 | 20-0075 | HILL, CAROLINE (cmhill2) |  | LUEKE, BEVERLY (bblueke) |  | RUCKER, BETH (aefird) | 8200 | 17400 | 14201.98 | 77068.84 | (10/05/20) Project complete. Waiting on two lamps to be delivered. Final billing.
AA | 1 | AA-1634 | Construction | Informal Projects |  | Academic Affairs VC |  | Colvard | COLVARD 4087-4090 OBSERVATION ROOMS | Provide new paint and carpet in Colvard 4087,4088,4089,4090 to fit out as observation rooms. Provide new paint and carpet in Colvard 4082 and move door to fit out as control room. Work with AISLE to provide cameras, microphones, and technology. S | 2019-08-14 16:18 | 20-0048 | SISCO, ASHLEY (asisco1) | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) |  | 27589 | 80000 | 77139.32 | 44040 | (10-5-20) Final SCO inspection scheduled for 9/29/20.
AA | 0 | AA-1711 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0041 | Storrs | STORRS 1ST FL STUDIO KNEE WALL REMOVAL | SoA would like to remove the knee wall in the 1st year studio area on the 1st floor. Once the wall is removed VCT in the area will need to be patched. | 2020-04-27 07:32 | SCHAUBLE, DONIA (dcooke) | PAYNE, TODD (tapayne) | MCMANNEN, TONYA (tmcmanne) | FRERE, ELIZABETH (efrere) | 20-0234-I | FRERE, ELIZABETH (efrere) | 10000 | 9991.6 | 5858.6 | 44025 | (10-5-20) MET Labs re-inspection complete 9/24/20. Final SCO inspection 9/29/20.
AA | 1 | AA-1704 | Construction | Informal Projects | 15100 | Academic Affairs VC | 0031 | Cafeteria Activities Building | CAB KITCHEN EQUIPMENT DEMO | CAB-Kitchen Equipment Demolition | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0207-I | BOAL, JOHN (jboal1) | 53382 | 71182 | 7757.63 | 44046 | (10-5-20) Construction complete - wrapping up final billing.
BA | 1 | BA-1920 | Construction | Informal Projects | 14010 | Facilities Informal Projects | 0092 | Facilities Ops and Parking (FOPS) | MOVE FIS TO FOPS FACILITIES OPERATIONS | FPFM, MOVE FIS TO FOPS, FACILITIES OPERATIONS & PARKING SERVICES BUILDING: Moves Management: | 2020-02-11 05:24 | FAKE, WILLIAM (wmfake) |  | WITHERSPOON, MELANIE (mewither) | CLARK, VALERIE (vclark9) | 20-0168 | SISCO, ASHLEY (asisco1) | 5000 | 80040.46 | 79724.1 | 44104 | Designer completed their work. Currently invoicing - requested backup information and more detailed breakdown of invoicing charges.
BA | 2 | BA-1894 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | 2020 CAMPUS PARKING MISC. SIGNS #1 | 2020 CAMPUS PARKING MISC. SIGNS #1, various signs as needed as done in years past. First 2 items are: 1) Replace damaged HC sign in Lot 7 with flex post. 2) Install 2 new spaces in Lot 16 for Geography and Earth Sciences vehicles. | 2020-01-23 08:54 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | TERRY, STEPHEN (slterry) | 20-0139 | TERRY, STEPHEN (slterry) | 7000 | 7000 | 2250 | 44012 | (10.05.20) Work Complete
BA | 0 | BA-1969 | Construction | Informal Projects |  | Business Services AVC |  | Prospector | PROSPECTOR COVID DINING MODIFICATIONS | PROSPECTOR Covid Modifications, modify Prospector as follows:1. All wall in Servery 200, patch and paint wall in 200 common with 200C. Remove and store door (at CAB) between 200/202.2 Remove portion of 4th cashier stand (end wall where cash regist | 2020-07-13 13:57 | 21-0010-I | CAUDLE, AMANDA (afelock) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) |  |  | 7000 | 7000 | 6358 | 44012 | (10.05.20) Work Complete
BA | 0 | BA-1970 | Construction | Informal Projects |  | Business Services AVC |  | Popp Martin Student Union | STUDENT UNION COVID DINING MODIFICATIONS | SU Covid Modifications1. at Bojangles, remove low wall and counter across from Bojangles BOH door and cashiers. Remove counter only at low wally near Bojangles pick up area. Need to determine how to treat top of wall - looks like we can cut stone | 2020-07-13 13:57 | 21-0011-I | CAUDLE, AMANDA (afelock) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) |  |  | 6500 | 6500 | 5893.32 | 44012 | (10.05.20) Work Complete
BA | 0 | BA-1956 | Construction | Informal Projects |  | Facilities Informal Projects |  | Bissell House | CHANCELLOR LOT EXTERIOR UPGRADES | CHANCELLOR LOT EXTERIOR UPGRADES: Project Dollar Maximum: $100,000.00 using Chancellor's Central Funds. Includes excavation design & construction, waterproofing, plants & bushes replanting, and soil compaction. Assign to Alicia Wells. | 2020-05-11 12:19 | 20-0237-BA | WELLS, ALICIA (awells43) | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) |  |  | 100000 | 300000 | 292826.55 | 44012 | (10.05.20) Work Complete
BA | 0 |  | Created | Capital Projects |  | Facilities Management AVC |  | Popp Martin Student Union | STARBUCKS RENOVATION | Renovate the Starbucks at Student Union | 2020-01-06 07:18 |  | CAUDLE, AMANDA (afelock) |  | CEALLAIGH, SHERRYL (sceallai) |  |  | 428309.49 | 316213.68 | 0 | 43782 | (10/05/20) Project complete. Waiting on two lamps to be delivered. Final billing.
BA | 0 |  | Created | Capital Projects |  | Facilities Management AVC |  | Popp Martin Student Union | STARBUCKS RENOVATION | Renovate the Starbucks at Student Union | 2020-01-06 07:18 |  | CAUDLE, AMANDA (afelock) |  |  | CEALLAIGH, SHERRYL (sceallai) |  |  | 428309.49 | 316213.68 | 44074 | (10/05/20) Construction complete. Project to be closed out.
IF | 2 | BA-1865 | Construction | Informal Projects | 10400 | Business Services AVC | 0029 | Housing and Residence Life | HOUSING & RESIDENCE LIFE LOADING DOCK LADDER | HRL, Loading Dock Ladder, add metal ladder at the catering loading dock between the two truck bays with roll over grab bars. This is required as drivers are jumping off dock rather than using nearby stairs. | 2019-10-28 12:02 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | KELLY, SHAWN (skelly64) | 20-0091 | KELLY, SHAWN (skelly64) | 1500 | 1500 | 184.14 |  | (10/05/20) Per email from Donia 6/24 this project is on hold due to funding. Will revisit in early fall.
IF | 2 | BA-1853 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | CAMPUS WIDE PARKING DECK REPAIRS PHASE 1 | CAMPUS WIDE PARKING DECK REPAIRS, provide recommended repairs for year 1 work as outlined by THP Limited, Inc. in various decks as outlined in previous reports and meetings. Please assign to Shawn Kelly. Thanks. | 2019-07-15 15:25 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | KELLY, SHAWN (skelly64) | 20-0033 | KELLY, SHAWN (skelly64) | 275000 | 275000 | 225585.16 |  | (10/05/20) Per email from customer this project will be on hold.
IF | 2 | SA-0451 | Construction | Informal Projects | 29700 | Housing and Residence Life | 0545 | Wallis Hall | WALLIS HALL AIR COOLED CHILLER | For Design Services:The Wallis Hall air cooled chiller is at its end of life. Last summer it actually failed and we had to bring in a temporary chiller to cool the building for a few weeks to the cost of about $40,000. So we'd like to go ahead and | 2020-01-31 07:51 | FOUST, KATHY (kfoust3) | EDWARDS, DONALD (dedwar55) | BUNKER, DEBRA (dbunker) | KELLY, SHAWN (skelly64) | 20-0161 | KELLY, SHAWN (skelly64) | 200000 | 202500 | 0 |  | (10/05/20) Per email from Donia on 5/27/20 this project will be placed on hold. Will revisit in 6 months.
IF | 2 | BA-1903 | Construction | Informal Projects | 10400 | Business Services AVC | 1096 | Chancellor's Lot | CHANCELLOR'S LOT CRACK SEAL & SEAL COAT | CHANCELLOR'S LOT CRACK SEAL & SEAL COAT, utilize JSS's existing contract to provide crack seal and seal coat maintenance this summer | 2020-01-23 09:17 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0146 | SMITH, RYAN (rsmit341) | 8600 | 8600 | 8470 | 44081 | (10/05/20) Entering PO's. Product is coming in and being stored in Storrs. Todd Payne is handling all the install of the product once the capital project is complete.
IF | 0 | BA-1960 | Construction | Informal Projects | 10500 | Auxiliary Operations | 1005 | West Deck | WEST DECK ARROWS | West Deck - repaint arrows Call West deck arrows) | 2020-05-13 11:06 | HOLMES, ROBERT (rholme16) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0241-I | SMITH, RYAN (rsmit341) | 4020 | 4020 | 4020 | 44104 | (10.05.20) All punch list items complete All interior work is complete and Lab is functional.
IF | 2 | BA-1756 | Construction | Informal Projects |  | Business Services AVC |  | CRI Deck 1 | CRI DECK ELECTRICAL REPAIRS | CRI DECK, Electrical Repairs, the bulk of the raceways in the main electrical closet exit the panelboards on the top, with the exception of the genset battery charger / jacket heater circuit. This circuit is in the slab of the electrical room, and c | 2018-12-13 11:34 | 19-0097 | SPATARO, EVAMARIE (espataro) | HOLMES, ROBERT (rholme16) | MULLMANN, JANETTA (jmullman) |  |  | 35000 | 3000 | 2600 |  | (10.05.20) Work complete
IF | 2 | BA-1860 | Construction | Informal Projects |  | Business Services AVC |  | Prospector | PROSPECTOR DUMPSTER BOLLARDS | PROSPECTOR, provide dumpster bollards. The 2 dumpsters (trash and recycling - 10CY) have a tendency to migrate out into the drive lanes until we reset them. Trucks are forced to have to maneuver around them to access the loading dock. We need to d | 2019-09-23 10:28 | 20-0066 | KELLY, SHAWN (skelly64) | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) |  | 9500 | 9500 | 0 | 43951 | (10-13-20) Equipment start up complete. Continue monitoring BAS trends. With funds remaining, looking into floor refinish.
IF | 2 | BA-1865 | Construction | Informal Projects |  | Business Services AVC |  | Housing and Residence Life | HOUSING & RESIDENCE LIFE LOADING DOCK LADDER | HRL, Loading Dock Ladder, add metal ladder at the catering loading dock between the two truck bays with roll over grab bars. This is required as drivers are jumping off dock rather than using nearby stairs. | 2019-10-28 12:02 | 20-0091 | KELLY, SHAWN (skelly64) | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) |  | 1500 | 1500 | 184.14 | 44074 | (10/12/20) Project to be closed out.
IF | 2 | BA-1853 | Construction | Informal Projects |  | Business Services AVC |  | Campus | CAMPUS WIDE PARKING DECK REPAIRS PHASE 1 | CAMPUS WIDE PARKING DECK REPAIRS, provide recommended repairs for year 1 work as outlined by THP Limited, Inc. in various decks as outlined in previous reports and meetings. Please assign to Shawn Kelly. Thanks. | 2019-07-15 15:25 | 20-0033 | KELLY, SHAWN (skelly64) | AVERITT, DREW (daveritt) |  | MULLMANN, JANETTA (jmullman) |  | 275000 | 275000 | 225585.16 |  | (10-20-20) Installation complete. Wrapping up final billing.
IF | 0 | BA-1967 | Construction | Informal Projects |  | FM Architectural/Engineering |  | Campus | CRAVEN CROFT RENOVATION | Renovation of several Craven Croft Houses to prepare to be rented Estimate prepared by Renovations team | 2020-06-25 15:24 | 20-0256-I | KELLY, SHAWN (skelly64) | FAKE, WILLIAM (wmfake) |  | HARRIS, ELLEN (elharris) |  | 60000 | 60000 | 33017.12 |  | 10/8/2020 - Will finalize invoices and close out project per Customer requests.
IF | 2 | BA-1864 | Construction | Informal Projects | Business Services AVC |  |  | Prospector | PROSPECTOR REROOF UPPER LEVEL | PROSPECTOR Reroof Upper Prospector - remove and replace the Upper Prospector roof which is only area that is still rubber and rock ballast with EPDM roof to match newer areas. | 2019-10-28 11:59 | 20-0090 | SMITH, RYAN (rsmit341) | AVERITT, DREW (daveritt) |  | MEDINA, CHARISSE (cturne66) |  | 26502 | 251002 | 21840 |  | Consultants / Contractors: * Consultants: None * Contractors: Heartland General Contracting Milestones: * Construction Completed * 10/09/20: Project Closeout Completed Notes / Issues / Concerns: * None
IF | 2 | BA-1848 | Construction | Informal Projects | Business Services AVC |  |  | South Village Deck | SOUTH VILLAGE DECK WEST ELEVATOR TOWER VENTILATION | SOUTH VILLAGE DECK, provide heating and ventilation in the west elevator tower as per Heapy Engineering recommendations received during the deck reviews (under a Shawn Kelly project). Thanks. | 2019-06-28 11:15 | 20-0028 | SMITH, RYAN (rsmit341) | AVERITT, DREW (daveritt) |  | MULLMANN, JANETTA (jmullman) |  | 17105 | 188105 | 169190.13 |  | (10/19/20) Project complete. Working on final billing
IF | 0 | BA-1951 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | PARKING DECK REPAIR YEAR 2; FACADE | PARKING DECK REPAIR Year 2; Facade, Joint & Concrete RepairYear 2 regular maintenance as specified by 5 year parking deck maintenance plan for repair of concrete flooring, exterior masonry, expansion joints, crack sealant, and facade repair. | 2020-04-27 07:31 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0231-I | SMITH, RYAN (rsmit341) | 150000 | 150000 | 120759.42 |  | Consultants / Contractors: * Consultants: None * Contractors: Lockelane Construction Milestones: * Construction Completed * 10/9/20: Project Closeout Completed Notes / Issues / Concerns: * None
IF | 0 | BA-1951 | Construction | Informal Projects | 10400 | Business Services AVC | 0000 | Campus | PARKING DECK REPAIR YEAR 2; FACADE | PARKING DECK REPAIR Year 2; Facade, Joint & Concrete RepairYear 2 regular maintenance as specified by 5 year parking deck maintenance plan for repair of concrete flooring, exterior masonry, expansion joints, crack sealant, and facade repair. | 2020-04-27 07:31 | AVERITT, DREW (daveritt) | SMITH, NANCY (nmsmith) | MULLMANN, JANETTA (jmullman) | SMITH, RYAN (rsmit341) | 20-0231-I | SMITH, RYAN (rsmit341) | 150000 | 150000 | 120759.42 |  | Consultants / Contractors: * Consultants: THP * Contractors: Carolina Restoration & Waterproofing Milestones: * 8/10/20 - 09/25/20: Completing masonry and additional structural improvements with remaining project contingency as authorized by customer. *10/05/20 - 10/09/20: Estimated Projector Closeout Complete Notes / Issues / Concerns: * None
IF | 0 | BA-1955 | Construction | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR REPLACE AHU-3 | PROSPECTOR REPLACE AHU-3. Replace AHU-3 which recently had the motor go down. Unit is 32 years old and probably best to make a full replacement rather than just the motor. Don Janus has been involved in discussions. | 2020-05-06 07:35 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | SMITH, RYAN (rsmit341) | 20-0236-I | SMITH, RYAN (rsmit341) | 240500 | 240500 | 17914.56 |  | Consultants / Contractors: * Contractors: - FM Renovations-Paint & Repair - FM BES-Cleaning, FM Zone 6-HVAC - Stratos Solutions-Flooring Milestones: * 7/20/20 - 8/14/20: Cleaning, Painting, & HVAC Repairs * 8/17/20 - 8/21/20: Carpet Installation * 8/24/20 - 8/28/20: Final Punch List & Completion of Properties 601 & 605 * 8/31/20 - 9/28/20: Final Punch List & Completion of Properties 625, 9902, & 9903. * 10/09/20: Projected 100% Project Closeout Notes / Issues / Concerns: * Project Delayed due to complications with wall paper removal and drywall repair as well as completing additional work requests as requested by Richard in Real Estate. * Minimal budget to repair any major structural or mechanical issues that may be found during cosmetic improvements.
IF | 0 | BA-1955 | Construction | Informal Projects | 10400 | Business Services AVC | 0034 | Prospector | PROSPECTOR REPLACE AHU-3 | PROSPECTOR REPLACE AHU-3. Replace AHU-3 which recently had the motor go down. Unit is 32 years old and probably best to make a full replacement rather than just the motor. Don Janus has been involved in discussions. | 2020-05-06 07:35 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | SMITH, RYAN (rsmit341) | 20-0236-I | SMITH, RYAN (rsmit341) | 240500 | 240500 | 17914.56 |  | Consultants / Contractors: * Consultant: REI Engineers * Contractor: Rike Roofing Milestones: * 08/17/20: Begin Construction * 10/09/20: Projected Construction Completion * 10/30/20: Projected Project Closeout Notes / Issues / Concerns: * Roof repair will still be under construction during the first four weeks of school. However, customer is aware and impacts to operations at Prospector loading dock will be minimal.
SA | 0 |  | Created | Capital Projects |  | FM Architectural/Engineering |  | Wells Fargo Fieldhouse | WELLS FARGO SOFTBALL INDOOR TRAINING FACILITY | A new Softball Indoor Training facility will be constructed in order to improve and extend practice schedules to remain competitive with other collegiate women's softball programs, including Conference USA peers. Further, the project will result in c | 2017-05-25 08:46 |  |  | CEALLAIGH, SHERRYL (sceallai) |  | NEILSON, JOHN (jneilson) |  |  | 650000 | 1174971.62 |  | Consultants / Contractors: * Consultant: Heapy Engineering * Contractors: Heartland General Contracting Milestones: * 08/05/20: Pre-Construction Meeting Held * 09/14/20 - 10/02/20: Construction Scheduled * 10/05/20 - 10/09/20: Final Punch List & SCO Inspections * 10/12/20 - 10/30/20: Project Construction & Financial Closeout Notes / Issues / Concerns: * None
SA | 0 | 11494 | Created | Capital Projects |  | FM Architectural/Engineering |  | Campus | EAST VILLAGE UTILITIES |  |  | This project is closed out. |  |  |  |  | KUGLER, BRIAN (bhkugler) |  | 2100000 | 1279159.45 | 44074 | 100% Complete Project Closeout
SA | 2 | SA-0447 | Construction | Informal Projects |  | Housing and Residence Life |  | Resident Managers House | GREEK HOUSE 14 CAMERA | Can you please create a design service project for pulling wiring and adding in an electrical outlet at Greek House 14 (Resident Manager's House) for the camera project?Thanks,Donny | 2019-12-12 12:10 | 20-0109 | LANIER, LISA (llanier) | FOUST, KATHY (kfoust3) |  | BUNKER, DEBRA (dbunker) | LANIER, LISA (llanier) |  | 8000 | 38500 | 44104 | Knee wall removal complete, basic electrical work complete, working with customer and Tom MacNab to find a solution for replacement of floor outlets that stick up out of the slab.
SA | 1 | IA-0035 | Construction | Informal Projects |  | Athletics Admin/Support |  | Barnhardt Student Activity Center | SAC 066 ATHLETIC WEIGHT ROOM RENOVATION | Building Name - Barnhardt Student Activity CenterRoom Number - 066Will need to add three offices to weight room in the SAC when Recreation vacates the area in November. Cannot do project until UREC has vacated the area after 11/1. | 2019-06-05 16:33 | 20-0053 | LANIER, LISA (llanier) | FERGUSON, JAMES (jcfergus) |  | SPEASE, DARIN (dspease) | LANIER, LISA (llanier) |  | 28500 | 114500 | 44022 | 11/11/2020: All work has been completed. Walked the space with the customer 11/6/2020 and received final approval. Getting invoices submitted now.
SA | 2 | SA-0365 | Construction | Informal Projects |  | Student Union |  | Popp Martin Student Union | STUDENT UNION 2ND FLOOR CARPET REPLACEMENT | Replace the carpet in 2nd floor common areas of the student union. Well worn areas include by the stairwell and Crown Commons | 2018-02-14 12:47 | 18-0146 | HILL, CAROLINE (cmhill2) | MEEHAN, MORGAN (mmeeha11) |  | HARRIS, MELODY (mhharris) |  |  | 135100 | 135100 | 44074 | 100% Complete Project Closeout
SA | 2 | SA-0447 | Construction | Informal Projects |  | Housing and Residence Life |  | Resident Managers House | GREEK HOUSE 14 CAMERA | Can you please create a design service project for pulling wiring and adding in an electrical outlet at Greek House 14 (Resident Manager's House) for the camera project?Thanks,Donny | 2019-12-12 12:10 | 20-0109 | LANIER, LISA (llanier) | FOUST, KATHY (kfoust3) |  | BUNKER, DEBRA (dbunker) |  |  | 8000 | 38500 | 44105 | Consultants / Contractors: * Consultant: McVeigh & Mangum/McCracken & Lopez * Contractor: Trane Milestones: * 10/16/20: Install new unit * 10/25/20: Startup, Testing, & Commissioning * 11/15/20: Projected Project Closeout Notes / Issues / Concerns: * None at this time.
SA | 0 | IA-0036 | Construction | Informal Projects |  | Athletics Admin/Support |  | Judy W. Rose Football Center | FOOTBALL LOCKER REPLACEMENT | Judy Rose Fieldhouse - Home Football Locker RoomTo replace lockers in home football locker room. Athletics has secured the lockers they want to purchase but need project # so that SCO can approve any electrical needs. Have discussed with Lisa Lanier. | 2020-05-18 11:38 | 20-0246-I | LANIER, LISA (llanier) | FERGUSON, JAMES (jcfergus) | SPEASE, DARIN (dspease) |  |  | 38300 | 38300 | 32008.49 | 44105 | Consultants / Contractors: * Consultant: McVeigh & Mangum/McCracken & Lopez * Contractor: Trane Milestones: * 10/16/20: Install new unit * 10/25/20: Startup, Testing, & Commissioning * 11/15/20: Projected Project Closeout Notes / Issues / Concerns: * None at this time.
| 0 | 11494 | Created | Capital Projects | 13930 | FM Architectural/Engineering | 0000 | Campus | EAST VILLAGE UTILITIES | The project is for the construction of utility infrastructure to support improvements to the East Village sector of campus to include water, telecom, and high voltage electrical service. | 2015-03-12 09:37 |  | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) |  |  | 2100000 | 1279159.45 |  | Consultants/Contractors: *Consultants: Engineering Services *Contractors: FO Milestones: *01/11/2021 - New lockers installed. Perimeter lockers are final and passed electrical inspection. Center lockers awaiting final electrical inspection. Project to be closed out.
AA | 0 | AA-1728 | Construction | Informal Projects |  | Greenhouse |  | McMillan Greenhouse | POLLY'S GARDEN | This is phase II of Polly's Garden in the VanLandingham Glen. The new work is an extension of previously installed work installed by Ponders, Inc. This project involves a combination of highly detailed specialty stonework that must be identical toex | 2020-08-27 13:56 | HILL, CAROLINE (cmhill2) | 21-0023-I | RAMOS, AMPARO (agil2) | GILLMAN, JEFFREY (jgillman) | HILL, CAROLINE (cmhill2) | [5 empty] | 2/1/2021 - Project completed. Will process invoice and close out project this week.
IF | 0 |  |  | Capital Projects |  | FM Architectural/Engineering |  | Campus | CID 2 - EAST VILLAGE UTILITIES | The project is for the construction of utility infrastructure to support improvements to the East Village sector of campus to include water, telecom, and high voltage electrical service. | 2015-03-12 09:37 | PAQUETTE, NOELLA (njpaquet) |  | CEALLAIGH, SHERRYL (sceallai) |  | KUGLER, BRIAN (bhkugler) | [5 empty] | * Consultant: McGill * Contractors: Two Brothers Utilities --- Final Project Closeout to be Complete * Project continues to remain open until FM Engineering is satisfied with model calculations. Final project closeout completely contingent on FM Engineering final approvals. * 05/18/20: Project Construction Completed * McGill currently providing model updates to water use calculations per Greg Cole of FM Engineering's direction. * Projected completion of model updates and review and approval by FM Engineering estimated to take 6 Months to complete. * Project currently being managed by Greg Cole of FM Engineering to determine and approve final model revisions and project completion.
AA | 1 | AA-1704 | Construction | Informal Projects |  | Academic Affairs VC |  | Cafeteria Activities Building | CAB KITCHEN EQUIPMENT DEMO | CAB-Kitchen Equipment Demolition | 2020-03-16 08:41 | BOAL, JOHN (jboal1) | 20-0207-I | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | [5 empty] | 3/1/2021: All work has been completed. All invoices are paid as of late last week. Project should be put in Punch.
AA | 0 |  | Created | Capital Projects |  | FM Architectural/Engineering |  | Campus | INFORMATION TECHNOLOGY INFRASTRUCTURE UPGRADES | IT Infrastructure Upgrades in Rowe, Storrs and Reese | 2018-10-18 11:02 | PAQUETTE, NOELLA (njpaquet) |  | CEALLAIGH, SHERRYL (sceallai) |  | WALTERS, DOUGLAS (dwalte22) | [5 empty] | Consultants / Contractors: Consultants: Optima Engineering Contractors: Shiel Sexton CM@R Milestones: * Project construction is behind scheduled 198 day delivery schedule. Cable test should start week of March 8th. * Final SCO Inspection anticipated March 15th. Notes / Issues / Concerns: SSC hired supplemental cabling contractors to help AJT.

## PROJECTS - ON HOLD
Projects on Hold
Unit | Campus Priority | Control Code | Project Status Block | Project Type | Sub Department Name | Building Name | Project Request Name | Project Description | Date Created | Project Account Manager | Financial Account Manager | Project Number | Project Coordinator | Scope & Budget | Approved Project Total | Amount Billed | Notes
AA | 6 | AA-1440 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Duke Centennial Hall | DUKE 349 RENOVATIONS | Convert faculty lounge to office spaceContact Kevin Scott Smith for details 7-8350 | 2017-09-07 12:39 | HUNTER, KATHY (kdwhaley) | HUNTER, KATHY (kdwhaley) | 18-0049 | BOAL, JOHN (jboal1) | 0 | 0 | 0 | 7/28/2020 : On hold. Project not funded.
AA | 6 | AA-1660 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | McEniry | MCENIRY 310 HYDROLOGY & BIOCHEMISTRY LAB | Renovation of space on the on the 3rd floor as a hydrology and biochemistry lab and renovation of a classroom space on the 2nd floor. | 2019-11-06 12:30 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0084 | BOAL, JOHN (jboal1) | 35439 | 37439 | 24653.05 | 7/28/2020: Scope of work has been significantly reduced. Change order to increase design fee has been issued. FY 21 funding from AA.
AA | 6 | AA-1661 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | McEniry | MCENIRY 316 LANDSCAPE ECOLOGY LAB | Renovation of McEniry 316 and 313 for use as landscape ecology lab. | 2019-11-06 12:31 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0085 | BOAL, JOHN (jboal1) | 35000 | 38000 | 24346.63 | 7/28/2020: Scope of work has been significantly reduced. Redesign fee was submitted 5-11. Change order to design purchase order has been issued. FY 21 funding from AA.
AA | 6 | AA-1670 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Belk Gymnasium | BELK GYM 024 KINESIOLOGY LAB | Belk Gym - 024 - Move human physiology research lab from Cameron 2nd floor to Belk Gym Ground floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:28 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0122 | BOAL, JOHN (jboal1) | 0 | 0 | 0 | 7/28/2020: Customer has been asked to provide additional scope information but not yet supplied it. Project is not yet funded.
AA | 6 | AA-1414 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Woodward Hall | WOODWARD BIOLOGY CAMERA REPLACEMENT | Woodward Biology Camera Replacement | 2017-05-16 13:26 | HUNTER, KATHY (kdwhaley) | HUNTER, KATHY (kdwhaley) | 18-0010 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | (7-28-20) Project on hold per Academic Affairs.
AA | 6 | AA-1638 | Project On Hold Design Services | Informal Projects | Center City Campus | The Dubois Center | CCB 1106 EXPANSION | Explore the possibility of remodeling and expanding 1106 at Center City. Remove wooden side walls and wall between 1106 and the storage areas behind it to make the room larger. | 2019-08-19 13:41 | DUPLESSIS, ANN (aduples1) | DUPLESSIS, ANN (aduples1) | 20-0051 | CAUDLE, AMANDA (afelock) | 13000 | 0 | 0 | (7-28-20) Routed scope and budget for design 12/4/19. Pending customer approval to proceed. Placed on hold 6-26-20.
AA | 6 | AA-1673 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Atkins | ATKINS 146, 149 CNT. FOR GRAD.LIFE MOVE FROM CONE | Atkins - 146, 148A, 148B, Suite 149 - Move Center for ¦Graduate Life from Cone 2nd floor to Atkins 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:57 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0125 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | (7-28-20) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 6 | AA-1698 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | PORTAL | PORTAL 129 UPGRADES | Portal - 129 - Upgrades to Active Learning Classroom | 2020-03-16 08:25 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0199-I | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | (7-28-20) On Hold per Academic Affairs 7-1-20 weekly meeting.
AA | 6 | AA-1531 | Project On Hold Design Services | Informal Projects | Research & Economic Dev. VC | PORTAL | PORTAL 232 AND 242 ENHANCEMENTS | PORTAL 322: 1) add color, texture, or paneling to the walls 2) move the UNCC sign in the space to different location 3) upgrade the photos and picture frames in the roomPORTAL 242: 1) add wall covering to wall outside of 242 and hang pictures like th | 2018-05-22 10:42 | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) | 19-0001 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 | 7/27/2020 - Customer has requested that this project should be place on hold until further notice.
AA | 6 | AA-1610 | Project On Hold Design Services | Informal Projects | College of Business | Friday | FRIDAY 391 RENOVATION | We are looking at splitting the room in two similar to 388/393.It may not be an exact half split though.We want one side to be a small PhD classroom and the other side to be a student bullpen area similar to 388/393.Classroom half needs to seat 20 if | 2019-04-10 13:24 | CARMICHAEL, TIMOTHY (twcarmic) | TWEED, DANA (dtweed1) | 19-0204 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 | 7/27/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1616 | Project On Hold Design Services | Informal Projects | College of Business | Friday | FRIDAY 242 CONFERENCE ROOM | I need a cost estimate to convert Friday 242 into a conference room. Move 1 display to the end wall. Remove the remaining 5 displays (Belk College Technology Team will take the 5 that get removed). Patch and paint walls. Core drill to connect lapto | 2019-04-22 13:35 | CARMICHAEL, TIMOTHY (twcarmic) | SANCHEZ, STEPHANIE (ssanch12) | 19-0211 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 | 7/27/2020 - Project on hold per customer request and lack of funding.
AA | 6 | AA-1690 | Project On Hold Design Services | Informal Projects | OneIT-CIO | Kennedy | KENNEDY 320 RECONFIGURATION | We would like to discuss options for how Kennedy 320 can adjust for growth, specifically using 2 - 4 areas of existing space. Sandra Soriano (78987) is the contact for this request. | 2020-02-07 14:44 | VITALLO, JUDY (jvitallo) | VITALLO, JUDY (jvitallo) | 20-0170 | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 | 7/27/2020 - Project on hold per customer request.
AA | 6 | AA-1668 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Grigg Hall | GRIGG 386 CLEAN ROOM MOVE FROM CAMERON | Grigg - 386A - Move portions of existing Cameron clean room to Grigg 386A . This will locate all campus clean room functions into Grigg.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:19 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0120 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | (07.28.2020) Working with Wei Gao on scope for equipment moves Will engage designer once scope is detailed. Will follow up with Donia regarding design fee.
AA | 6 | AA-1676 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Smith | SMITH 217/218/220 SYST. ENGIN. MOVE FROM CAMERON | Smith - 205, 206, 211, 212, 213, 214, 216, 308,311,314,317,318,319,320, 320A,325,348,349,351,352 - relocate Systems Engineering from Cameron 2nd floor to Smith and create graduate bull pins for Engineering Technology graduate students who currently o | 2020-01-14 10:44 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0128 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | (07.28.2020) Waiting on design fee from McVeign & Mangum. Will follow up with them this week.
AA | 6 | AA-1677 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Smith | SMITH 2 & 3 FLOOR CORRIDOR REFRESH | Smith - 245D and 2nd/3rd floor corridors - Provide AV upgrade for conference room 245D for use by Engineering Technology. Replace existing VCT possibly Asbestos containing in 2nd and 3rd floor corridors with LVT to match recently renovated hallways o | 2020-01-14 10:50 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0129 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | NNP - part of Cameron moves
AA | 6 | AA-1685 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | College of Health and Human Services | CHHS 330 NURSING SIMULATION LAB | CHHS - 330, 330A - Convert existing Classroom in School of Nursing Simulation Lab.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 11:12 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0134 | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | (07.28.2020) Waiting on Donia for equipment and project scope. ON HOLD
AA | 6 | AA-1702 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | College of Health and Human Services | CHHS VIRTUAL CADAVER LAB | CHHS - Virtual Cadaver Lab | 2020-03-16 08:41 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0205-I | PATEL, NAVINKUMAR (npatel24) | 0 | 0 | 0 | (07.28.2020) Waiting on information from Donia regarding location, and equipment. ON HOLD
AA | 0 | AA-1540 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | McMillan Greenhouse | GREENHOUSE FOR BIOLOGY FACULTY | Greenhouse for Biology Faculty | 2018-06-29 09:17 | HUNTER, KATHY (kdwhaley) | HUNTER, KATHY (kdwhaley) | 19-0023 | PATEL, NAVINKUMAR (npatel24) | 228650 | 0 | 0 | (06-03-20) - Still on hold for funding. Scope was provided to EHS for funding review.
AA | 6 | AA-1684 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Fretwell | FRETWELL 114 116 118 120 122, 124 ACT. LEARN. CLRM | Fretwell - 114, 116, 118, 120, 122, 124 - Create new Active Learning Classroom and relocate Math Computer labs from other floors in Fretwell.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 2020-01-14 11:10 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0133 | SISCO, ASHLEY (asisco1) | 28634 | 0 | 0 | (7/28/20) Per email from Donia 6/24 this project is on hold due to funding. Will revisit in early fall.
AA | 6 | AA-1693 | Project On Hold Design Services | Informal Projects | English | Fretwell | FRETWELL 275 AND 248C REFRESH | I would like to talk to Ashley Sisco about possible options (seating and mobile wall) for refurbishing the English Department Reception area and lounge.Fretwell 275 and 248C | 2020-02-20 10:55 | WILLIAMS, ANGELA (anwillia) | WILLIAMS, ANGELA (anwillia) | 20-0177 | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 | (7/28/20) Per email from customer this project will be on hold.
AA | 6 | AA-1701 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Fretwell | FRETWELL 314 RENOVATIONS | Fretwell - Suite 314 - Office of Interdisciplinary Studies | 2020-03-16 08:40 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0204-I | SISCO, ASHLEY (asisco1) | 0 | 0 | 0 | (7/28/20) Per email from Donia on 5/27 this project will be placed on hold. Will revisit in 6 months.
AA | 0 | AA-1692 | Scope & Budget Requested | Informal Projects | Academic Affairs VC | Campus | BAND TOWER FOOTING DESIGN | Band Tower Footing Design - The marching band will be installing a pre-fabricated 24' tall steel tower at the practice field. The tower will need to have a footing designed by an NC licensed engineer. Getting a budget for this project is very urgent | 2020-02-12 10:38 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0174 | SMITH, RYAN (rsmit341) | 0 | 0 | 11731.7 | On Hold till Funding Approved
AA | 6 | AA-1628 | Project On Hold Design Services | Informal Projects | Mech Engineering & Engineering Sci | Motorsports Research | MOTORSPORT WIND/TUN.STRUCT. ANALYSIS & POWER SPLY. | Motorsports Research Room 124 - Can we please have someone come out and approve the location of putting a concrete isolation pad in. Isolation pad will be provided by a 3rd party, we just need load approval for the floor below. | 2019-07-03 15:33 | CANTOR, MARION (mjcantor) | TADLOCK, ERICA (ewalter5) | 20-0023 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | (7/28/2020) Waiting on customer to assemble windtunnel and finalize where the equipment will reside in lab. Once complete, electrical can be run.
AA | 6 | AA-1632 | Project On Hold Design Services | Informal Projects | Biological Sciences | Woodward Hall | WOODWARD 461 EMERGENCY CIRCUIT | Woodward Hall - 461 - Add emergency circuit to lab (461). Almost a mirror project to the recently completed 361 | 2019-08-08 14:59 | GRAY, DAVID (dlgray) | GRAY, DAVID (dlgray) | 20-0044 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | (7/28/2020) Scope and budget provided to customer. Waiting on customer decision. Likely to be cancelled.
AA | 6 | AA-1645 | Project On Hold Design Services | Informal Projects | EPIC | Lot 6 | LOT 6 - EV CHARGING STATION | Lot 6 - EV Charging Station: Provide an estimate for design and construction cost to install an experimental EV charging location. | 2019-09-09 13:42 | BROWN, LORI (lmorri25) | MOOSE, ROBIN (rmoose2) | 20-0059 | SPATARO, EVAMARIE (espataro) | 11000 | 0 | 0 | (7/28/2020) On hold.
AA | 6 | AA-1700 | Project On Hold Design Services | Informal Projects | EPIC | EPIC Building | EPIC HIGHBAY WINCH POWER CONNECTION | Please install three 460V 3phase power connections in the EPIC highbay lab. | 2020-03-16 08:40 | MOOSE, ROBIN (rmoose2) | MOOSE, ROBIN (rmoose2) | 20-0203-I | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | (7/28/2020) Showed rough estimate to customer, customer needs to research funding options
AA | 6 | AA-1629 | Project On Hold Design Services | Informal Projects | Research & Economic Dev. VC | PORTAL | PORTAL INTERIOR GRAPHIC SIGNAGE | We want signage to raise the profile of the Office of Tech Transfer, SBTDC, Ventureprise, 49er Foundry, and the PORTAL Solutions Desk. Signage needs to large enough to be seen from across the lobby, attractive, and professional. All of these offices | 2019-07-15 14:23 | MATEEN, ALI (amateen) | KEENE, PATRICIA (pgkeene) | 20-0032 | TERRY, STEPHEN (slterry) | 10800 | 0 | 0 | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1663 | Project On Hold Design Services | Informal Projects | DPT Writing, Rhet, Digital Studies | Cameron Hall | CAMERON WRITING PROGRAM 1ST FLOOR SIGNS | CAMERON WRITING PROGRAM 1ST & 2ND FLOOR SIGNS: Name changes needed to Department of Writing, Rhetoric and Digital Studies. Several signs throughout first and second floors need to reflect our new name. Please contact Denise Sabo 7-1902 | 2019-11-15 13:46 | SABO, DENISE (dsabo1) | MULLIN, JOAN (jmulli40) | 20-0089 | TERRY, STEPHEN (slterry) | 2900 | 0 | 0 | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1706 | Project On Hold Design Services | Informal Projects | College of Liberal Arts & Sciences | Fretwell | FRETWELL 3RD FLOOR ATRIUM NAMING | Fretwell 3rd Floor Atrium Naming. Dr. Robert & Mrs. Tiwana Anderson Atrium Signage and Portrait development and installation | 2020-03-31 17:42 | FRIZZELL, MARY ELLEN (mfrizzel) | STAFFORD, ELEANOR (eastaffo) | 20-0217-I | TERRY, STEPHEN (slterry) | 5400 | 0 | 0 | 06-03-20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1669 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Woodward Hall | WOODWARD 264, 275 KINESIOLOGY MOVE FROM CAMERON | Woodward - 264, 275, 276, 276AMove Kinesiology Research labs from Cameron 2nd floor to Woodward 2nd Floor.Do not contact end users directly. Set up first meeting with Donia Schauble only. | 2020-01-14 09:25 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0121 | WELLS, ALICIA (awells43) | 0 | 0 | 0 | (7/29/20) Project on hold
AA | 6 | AA-1671 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Colvard | COLVARD 1028 FADO MOVE FROM CAMERON | Colvard - 1028, 1028A, 1028B, 1028C, 1028D, 1028E, 1028F, 1028G, 1028H, 1028I - Relocate FADO from Cameron 2nd Floor to Colvard 1000 level.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 2020-01-14 09:46 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0123 | WELLS, ALICIA (awells43) | 10000 | 10000 | 0 | (7/29/20) Project on hold
AA | 6 | AA-1672 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | Cameron Hall | CAMERON 174 MOSAIC MOVE FROM CAMERON | Cameron- Suite 174 - Relocate Mosaic from Cameron 2nd floor to Cameron 1st floor.Do not contact end users directly. Set up first meeting with Donia Schauble and Nick Patel only. | 2020-01-14 09:51 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0124 | WELLS, ALICIA (awells43) | 0 | 0 | 0 | (7/29/20) Project on hold
AA | 6 | AA-1674 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | EPIC Building | EPIC 1231 FURNITURE | EPIC - 1231 - Furniture Project - Exact scope still needs to be determined.Do not contact end users directly. Set up first meeting with Donia Schauble and Alicia Wells only. | 2020-01-14 10:01 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0126 | WELLS, ALICIA (awells43) | 0 | 0 | 0 | (7/29/20) Project on Hold
AA | 1 | AA-1440 | Scope & Budget Requested | Informal Projects | Academic Affairs VC | Duke Centennial Hall | DUKE 349 RENOVATIONS | Convert faculty lounge to office spaceContact Kevin Scott Smith for details 7-8350 | 2017-09-07 12:39 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 18-0049 | BOAL, JOHN (jboal1) | 0 | 0 | 0 | (06-03-20) - Still on hold for funding. Scope and preliminary designs were provided to EHS for review.
AA | 6 | AA-1700 | Project On Hold Design Services | Informal Projects | EPIC | 0072 | EPIC Building | EPIC HIGHBAY WINCH POWER CONNECTION | 2020-03-16 08:40 | MOOSE, ROBIN (rmoose2) | PARK, YOUNGJIN (ypark17) | MOOSE, ROBIN (rmoose2) | SPATARO, EVAMARIE (espataro) | 20-0203-I | 0 | 0 | 06/03/20. No change. Budget review. Customer said to hold.
AA | 6 | AA-1670 | Project On Hold Design Services | Informal Projects | Academic Affairs VC | 0017 | Belk Gymnasium | BELK GYM 024 KINESIOLOGY LAB | 2020-01-14 09:28 | SCHAUBLE, DONIA (dcooke) |  | MCMANNEN, TONYA (tmcmanne) | BOAL, JOHN (jboal1) | 20-0122 | 0 | 0 | Project will move forward pending the new campus standard LED light fixture approval. Existing standard is no longer being manufactured.
AA | 1 | AA-1683 | Scope & Budget Requested | Informal Projects | Academic Affairs VC | Colvard | COLVARD 1017-1018 ACTIVE LEARNING CLASSROOM | Colvard - Suite 1017 and 1018A - Create new Active Learning Classroom.Do not contact end users directly. Set up first meeting with Donia Schauble and AISLE Group only. | 2020-01-14 11:07 | SCHAUBLE, DONIA (dcooke) | MCMANNEN, TONYA (tmcmanne) | 20-0132 | FRERE, ELIZABETH (efrere) | 0 | 0 | 0 | (7-28-20) Project to remain on hold per Scott Plunkett.
AA | 0 | AA-1732 | Scope & Budget Requested | Informal Projects | FRETWELL SUITE 320 WORKSTATION RECONFIGURE | Academic Affairs VC | Fretwell - Suite 320 - Reconfiguration of existing workstations from 5 stations to 3. | Fretwell | 2020-10-22 14:55 | SCHAUBLE, DONIA (dcooke) | SCHAUBLE, DONIA (dcooke) |  | HILL, CAROLINE (cmhill2) | STAFFORD, ELEANOR (eastaffo) |  | 0 | Following Up with Customer To Closeout
BA | 6 | BA-1631 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Bioinformatics | FPFM, BIOINFORMATICS 124 CODE ROOM USE SEPARATIONS | FPFM - BIOINFORMATICS 124 CODE REQUIRED ROOM USE SEPARATIONS: Mechanical, storage and wood shop uses need separation by 2-hour fire walls. Construction costs unknown. Outside design is required at $30,000. | 2017-11-02 06:48 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) | 18-0089 | BOAL, JOHN (jboal1) | 0 | 0 | 0 | (7-28-20) Project on Hold
BA | 6 | BA-1696 | Project On Hold Design Services | Informal Projects | Business Services AVC | Union Deck | UNION DECK STORAGE ROOM | UNION DECK Storage Room, provide large storage room on level 1 underneath of the up ramp where area is fenced off. This modification was rejected in the Expansion project due to schedule but we would like to review requirements and price out impleme | 2018-05-07 09:37 | AVERITT, DREW (daveritt) | AVERITT, DREW (daveritt) | 18-0232 | CAUDLE, AMANDA (afelock) | 225000 | 0 | 30800 | (05-08-2020) Watson Tate Savory total design contract reduced to $29,920. Partial invoice for $23,222.10 dated 04-23-2020 was approved for payment on 04-27-2020.
BA | 6 | UA-0039 | Project On Hold Design Services | Informal Projects | Alumni Affairs | Hauser Alumni Pavilion | HAUSER ALUMNI PAVILION SECURITY DOORS | Project to add garage door type security between the brick columns . Cleo - use 138062. Contact Scott Plunkett at 7-7792 | 2017-11-14 09:27 | PLUNKETT, SCOTT (ssplunke) | WIDMAIER, CLEO (cswidmai) | 18-0101 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | 7/28/2020: Project not funded.
BA | 6 | BA-1930 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Kennedy | KENNEDY CONTEMPLATIVE SPACE RENOVATION | KENNEDY CONTEMPLATIVE SPACE RENOVATION, DESIGN: Chancellor 2020 Central Funds: $50,000. Design Only. Project Dollar Maximum: $30,800.00. | 2020-03-04 07:20 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) | 20-0184 | FRERE, ELIZABETH (efrere) | 30800 | 30800 | 0 | On Hold Pending Cone Deck Decisions
BA | 6 | BA-1586 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Campus | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT | EAST DECK 2 ENTRANCE DRIVE IMPROVEMENT: Congestion Task Force assignment for design only: Central Funds - Project Dollar Maximum: $13,000. | 2017-05-17 07:56 | FAKE, WILLIAM (wmfake) | PAQUETTE, NOELLA (njpaquet) | 17-0225 | KELLY, SHAWN (skelly64) | 13000 | 13000 | 0 | 06-03-20 - Site meeting on hold.
BA | 6 | BA-1676 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Campus | FPFM, CAMPUS ADA PATHWAYS SURVEY DATA REVIEW | FPFM, REVIEW RECENTLY COMPILED CAMPUS ADA PATHWAYS SURVEY DATA TO MAKE RECOMMENDATIONS FOR CHANGES TO CAMPUS MAP: Point of contact: Katie Montie with Disability Services (DS). Facilities Information Systems (FIS) to provide technical assistance. | 2018-03-07 06:37 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) | 18-0178 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 | (7/28/2020) Customer has received estimates. Waiting on decision.
BA | 6 | BA-1762 | Project On Hold Design Services | Informal Projects | Business Services AVC | Lot 7 | LOT 7 & 7A RECONFIGURATION | LOT 7 & 7A Reconfiguration, redesign Lots 7 and 7A to optimize usage and traffic flow (Design only at this point in time). | 2019-01-07 10:46 | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | 19-0106 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 | 02-13-2020 ON HOLD - Discussed project with Cass Ferguson. Project does not have funding at this time. Needs further discussion due to continued water infiltration. Does not appear to be site related.
BA | 6 | BA-1544 | Project On Hold Design Services | Informal Projects | Environmental Health & Safety | Campus | CAMPUS WIDE BUILDING EVACUATION MAPS | Building evacuation interior floor plan maps need to be installed in all buildings. The Office of Environmental Health and Safety would like to request an official scope and budget to install these maps. | 2017-03-07 16:43 | GRIFFIN, DARIUS (dgriffin) | GRIFFIN, DARIUS (dgriffin) | 17-0195 | TERRY, STEPHEN (slterry) | 0 | 0 | 0
BA | 6 | BA-1680 | Project On Hold Design Services | Informal Projects | Environmental Health & Safety | Campus | CAMPUS SERVICE VEHICLE SIGNAGE | Please provide a proposed scope and budget for the project detailed below. Once the scope and budget is received, our office will be able to determine if the project can be completed this fiscal year or in the next.Approximately 15 marker post signs | 2018-04-02 16:44 | GRIFFIN, DARIUS (dgriffin) | BARNETT, DENISE (dbarne33) | 18-0198 | TERRY, STEPHEN (slterry) | 18500 | 0 | 0 | 06/27/20: On Hold Pending Review with Engineering Dept
BA | 6 | BA-1871 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Campus | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING | FPFM, BUILDING AND PROPERTY SIGNAGE ADDRESSING: Need Scope & Budget to allow further review by Jon Varnell to allow assessment of funding options. Please assign to Steve Terry. | 2019-11-18 10:44 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) | 20-0088 | TERRY, STEPHEN (slterry) | 30000 | 30000 | 0 | (7/28/2020) Defining Scope & Timeline with Customer. On hold until priority 1 is complete.
BA | 6 | BA-1959 | Project On Hold Design Services | Informal Projects | Auxiliary Operations | Lot 8 | LOT 8 HOUSING VEHICLES SIGNAGE | Install signs for Housing vehicles in Lot 8 (I would call "Lot 8 signage) | 2020-05-13 11:05 | HOLMES, ROBERT (rholme16) | MULLMANN, JANETTA (jmullman) | 20-0240-I | TERRY, STEPHEN (slterry) | 0 | 0 | 0 | 7/28/2020: Project on hold.
IF | 6 | SA-0444 | Project On Hold Design Services | Informal Projects | Cone Univ Center | Cone University Center | CONE NORTH ROOF REPLACEMENT | Cone North Roof Replacement - Fully remove existing system to replace the Cone North Building Roofing System. | 2019-12-09 13:04 | MERCK, DONNA (dlmerck) | HARRIS, MELODY (mhharris) | 20-0112 | BOAL, JOHN (jboal1) | 0 | 0 | 0 | (7/28/2020) On hold.
IF | 6 | BA-1854 | Project On Hold Design Services | Informal Projects | Facilities Informal Projects | Barnhardt Student Activity Center | FPFM, SAC FIRE & SMOKE PURGE SYSTEMS INVESTIGATION | FPFM, SAC FIRE & SMOKE PURGE SYSTEMS INVESTIGATION: Investigate smoke management of SAC during fire alarm activation. AHU devices do not shut down; smoke purge system serving the food court does not function. Assign to Don Janus. | 2019-07-23 08:33 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) | 20-0034 | KELLY, SHAWN (skelly64) | 0 | 0 | 0 | Project will move forward pending the new campus standard LED light fixture approval. Existing standard is no longer being manufactured.
IF | 6 | BA-1796 | Project On Hold Design Services | Informal Projects | Business Services AVC | North Deck | NORTH DECK FFA LIGHTING REPLACEMENT | NORTH DECK FFA LIGHTING REPLACEMENT, replace top level light fixtures with LED type units in place of the metal halite. | 2019-02-14 09:30 | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | 19-0161 | LOVE, DAVID (dflove) | 7900 | 0 | 0 | Project on Hold per DA per 6/16/2020 Email
IF | 6 | BA-1797 | Project On Hold Design Services | Informal Projects | Business Services AVC | CRI Deck 1 | CRI DECK FFA LIGHTING REPLACEMENT | CRI DECK FFA LIGHTING REPLACEMENT, replace top level light fixtures with LED type units in place of the metal halite. | 2019-02-14 09:31 | AVERITT, DREW (daveritt) | MULLMANN, JANETTA (jmullman) | 19-0162 | LOVE, DAVID (dflove) | 6800 | 0 | 0 | 07/07/2020 -Project on hold while Customer determines if they have other options.
IF | 6 | BA-1913 | Project On Hold FAM | Informal Projects | Safety and Security | Campus | CAMPUS SIREN UPGRADE "ALERTUS" | Safety & Security - Campus Siren upgrade - "Alertus" | 2020-01-31 11:09 | HILL, MICHELLE (mphilipp) | BARNETT, DENISE (dbarne33) | 20-0162 | LOVE, DAVID (dflove) | 0 | 0 | 0 | (7/28/2020) Sent scope and budget to customer. Customer taking S&B to lobby for funding.
IF | 6 | BA-1944 | Project On Hold Design Services | Informal Projects | Business Services AVC | Campus | STARBUCKS TRUCK PAD AND ELECTRICAL | STARBUCKS TRUCK Pad and Electrical, provide design to provide a prototypical pad off off the sidewalk for Starbucks Truck to pull over and sell during the day. Initial location is intended to be Smith but pad could be used anywhere - need pull off, | 2020-04-10 12:56 | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) | 20-0221-I | SMITH, RYAN (rsmit341) | 26000 | 0 | 0 | Restarting project, considering a temporary option + storage instead of the permanent tower. Arranging meeting with band group.
IF | 6 | AA-1655 | Project On Hold Design Services | Informal Projects | Center City Campus | The Dubois Center | CCB OUTDOOR LIGHTING | Additional lighting needs to be added to the back garden area. Please assess the current lighting, make recommendations for additional and adequate lighting and provide an estimate of cost. | 2019-10-10 12:30 | DUPLESSIS, ANN (aduples1) | DUPLESSIS, ANN (aduples1) | 20-0079 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | (7/28/2020) On hold.
IF | 6 | BA-1889 | Project On Hold Design Services | Informal Projects | Safety and Security | Barnhardt Student Activity Center | FIRST PRIORITY CAMERA PROJECT PHASE 2 | Please assign to David Love - Phase 2 includes SAC, West Deck, Belk Gym, Cone, Colvard, Levine Hall, Cato, Prospector, McEniry, Auxiliary Services, Cameron, Bioinformatics, PORTAL, EPIC, Grigg, Duke, Motorsports, South Village Deck. (Approximately 2 | 2020-01-07 10:31 | HILL, MICHELLE (mphilipp) | BARNETT, DENISE (dbarne33) | 20-0115 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | 07/07/2020 -Project on Hold per email from Robbie Bell 02/24/20. Overall price ($9,988) was more then they expected. They will use the space as is for now to determine necessity of project.
IF | 0 |  | Created | Capital Projects | Facilities Management AVC | Campus | NEW CRI ENTRANCE ROAD | Create a new entrance off Hwy 29 | 2019-11-20 05:15 |  | CEALLAIGH, SHERRYL (sceallai) |  | KUGLER, BRIAN (bhkugler) | 1449300 | 1159589.44 | 0 | (7-28-20) Informal budget provided to Morgan Meehan 1-27-20. Pending approval to proceed. Placed on Hold April 27.
IF | 0 |  | Created | Capital Projects | Facilities Management AVC | Lot 5A | LOT 5A EXPANSION | re-alignment of lot 5A | 2019-11-19 14:10 |  | CEALLAIGH, SHERRYL (sceallai) |  | KUGLER, BRIAN (bhkugler) | 702248.85 | 742155 | 0 | 7/27/2020 - Project on hold per Customer request.
SA | 6 | SA-0408 | Project On Hold Design Services | Informal Projects | Cone Univ Center | Cone University Center | CONE SOUTH 3 MODERNIZATION | Cone Center - South 3: Upgrade and modernize South 3 level of Cone Center. Collaborate with Director and Associate Director to establish design options and features. | 2019-01-31 13:53 | MERCK, DONNA (dlmerck) | MERCK, DONNA (dlmerck) | 19-0147 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | (7-28-20) On hold - waiting for Morgan and Donna to provide scope of work
SA | 6 | SA-0450 | Project On Hold Design Services | Informal Projects | Student Union | Popp Martin Student Union | STUDENT UNION M101 ESPORTS LOUNGE | There is a space identified in the Student Union as a potential opportunity for an Esports Lounge. Need to determine if it is feasible in the space given the needs of the group. Need feasibility information by 1/28 and then will proceed further if ne | 2020-01-16 10:59 | MEEHAN, MORGAN (mmeeha11) | DALE, JEREMY (jdale8) | 20-0137 | CAUDLE, AMANDA (afelock) | 0 | 0 | 0 | (7/28/2020) Project can be FF&E. Will work with customer to schedule. Customer holding for funding.
SA | 6 | SA-0462 | Project On Hold Design Services | Informal Projects | Student Activity Ctr and Venue Mgmt | Barnhardt Student Activity Center | SAC SALONS AND PREFUNCTION CARPET | Project is to gather estimates and designs on replacing the carpet inside and outside of the SAC Salons. | 2020-03-16 08:40 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | 20-0202-I | HILL, CAROLINE (cmhill2) | 0 | 0 | 0 | (7/29/20) Project ready for order placement but on hold until funding received
SA | 6 | SA-0407 | Project On Hold Design Services | Informal Projects | Student Activity Ctr and Venue Mgmt | Halton-Wagner Tennis Complex | HALTON TENNIS COMPLEX LOWER HALL FLOODING | The lower hallways of the Halton Tennis Complex flood when there is heavy rain. Zone 1 has performed some modifications to the weep holes in the brick which has helped but we are still getting some flooding. The water drains towards the building inst | 2019-01-24 16:57 | BARNES, TRENT (tbarne21) | STONE, CYNTHIA (cstone26) | 19-0134 | LANIER, LISA (llanier) | 34000 | 0 | 0 | (07.28.2020) Designer approved, will enter SCOPE AND BUDGET by 07.30.20.
SA | 6 | SA-0439 | Project On Hold Design Services | Informal Projects | Student Activity Ctr and Venue Mgmt | Barnhardt Student Activity Center | SAC 062 FITNESS ROOM RENOVATION | Fitness room renovation two include two spaces; one space is to remain a multipurpose room for events and the other space is to be converted into offices and storage space. Would like to keep as much of original hardwood floor as possible. | 2019-10-09 09:37 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | 20-0070 | LINGER, JOSHUA (jlinger2) | 0 | 0 | 0 | 07/07/2020 - project on hold due to cost considerations
SA | 6 | SA-0441 | Project On Hold Design Services | Informal Projects | University Recreation | Belk Gymnasium | BELK GYM 127 RECONFIGURE | Adding a door and wall to create a designated space to be used after UREC moves from Belk Gym to UREC building. Separating COR10 from 127 | 2019-10-16 13:31 | BELL, ROBERT (rbell16) | BARRETT, LACRISSA (lbarre11) | 20-0074 | LINGER, JOSHUA (jlinger2) | 9987.5 | 0 |  | ON HOLD
SA | 6 | SA-0454 | Project On Hold Design Services | Informal Projects | Housing and Residence Life | Witherspoon | WITHERSPOON CABINET & COUNTERTOP REPLACEMENT | Witherspoon Hall.. We want to replace the countertops and cabinets in the kitchens in similar configuration to what's currently in the apartments. ..per Alan Hinton 757-692-9020 | 2020-02-11 15:47 | FOUST, KATHY (kfoust3) | BUNKER, DEBRA (dbunker) | 20-0173 | LINGER, JOSHUA (jlinger2) | 353194.69 | 0 | 0 | 8/19/2020 : On hold. Project not funded.
SA | 6 | SA-0388 | Project On Hold Design Services | Informal Projects | Student Activity Ctr and Venue Mgmt | Barnhardt Student Activity Center | SAC ARENA BB & CURTAIN - LOW VOLTAGE | Change existing retractable basketball goals and mechanical partition curtain systems in Halton arena from 120v to low voltage. | 2018-07-26 14:21 | MOON, STUART (sgmoon) | BARNES, TRENT (tbarne21) | 19-0038 | SPATARO, EVAMARIE (espataro) | 0 | 0 |  | Commissioning and punch list work continues. Continuing with exterior pool work, Testing & Balancing, commissioning, punch list inspections, and corrective work. T&B approx. 95% - 98% complete. Commissioning is approx. 85% complete as of 6/2/20. GC is focusing on working through JCI’s punch list and items discovered during partial “System Integration” by Platinum (FIS consultant). Beneficial Occupancy was granted December 10, 2019 for interior only. Grand Opening was January 8, 2020. Landscaping punch list inspection occurred January 4, 2020. Designer completed interior punch list inspection 3/6/20. Underground Detention System - designer and university inspection occurred 4/15/20. Designer needs to submit documents to the city to obtain a permit. University will pay for the permit. Indoor pool drained 3-18-20 for punch list work. Work to complete 4/1/20. Inspection occurred 4-7-20. Pool full 4-19-20. Mock-up of outdoor pool deck finish reviewed 4-15-20 (needs redo). Commissioning is finally seeing light at the end of the tunnel, and the goal is to wrap up by the end of May (not achieved). 95% complete as of 6-9-20. T&B is 99.9% complete Complete closeout - targeting end of June. Exterior Punch list review occurred 5-26-20 Punch list inspection for the outdoor pool and pool bldg occurred on 7/10/20. Beneficial Occupancy granted by SCO on 7-23-20 for outdoor pool and pool bldg.
SA | 6 | SA-0424 | Project On Hold Design Services | Informal Projects | Student Union | Popp Martin Student Union | STUDENT UNION LED LIGHTING RETROFIT | Student Union - Entire BuildingStudent Union wants to increase sustainability by reducing energy consumption and decrease annual maintenance cost for replacement fluorescent lights by retrofitting lighting to LED. This project aligns with UNC policy | 2019-06-24 09:37 | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | 20-0022 | SPATARO, EVAMARIE (espataro) | 43000 | 0 |  | (8/18/2020) Showed rough estimate to customer, customer needs to research funding options
SA | 6 | SA-0440 | Project On Hold Design Services | Informal Projects | Student Activity Ctr and Venue Mgmt | Barnhardt Student Activity Center | SAC 334A-E SALONS LIGHTING UPDATE | Replace light fixtures, and update control system to accommodate new lighting. | 2019-10-09 09:42 | STONE, CYNTHIA (cstone26) | STONE, CYNTHIA (cstone26) | 20-0071 | SPATARO, EVAMARIE (espataro) | 0 | 0 |  | 8/19/2020: Customer has been asked to provide additional scope information but not yet supplied it. Project is not yet funded.
SA | 6 | SA-0455 | Project On Hold Design Services | Informal Projects | Student Union | Popp Martin Student Union | STUDENT UNION 340 POWER UPGRADE | Student Union would like to add additional power to the multi purpose room 340. We are looking at 100A, 3 phase, 5 wire, 120/208V. Requesting Eva Spataro on this project | 2020-02-18 16:03 | BROWN, JOSHUA (jbrow450) | MEEHAN, MORGAN (mmeeha11) | 20-0186 | SPATARO, EVAMARIE (espataro) | 0 | 0 | 0 | 08-05-20. No change. Budget review. Customer said to hold.
SA | 6 | SA-0442 | Project On Hold Design Services | Informal Projects | Cone Univ Center | Belk Gymnasium | BELK GYM 120 VENTURE MOVE | Venture has been approved to move from Cone to Belk gym. Within this project includes: coordinating a move of the staff, office furnishing needs, space renovations in Belk for storage space. As this project is related to project SA-0441 it could be | 2019-10-24 14:09 | MEEHAN, MORGAN (mmeeha11) | DALE, JEREMY (jdale8) | 20-0080 | WELLS, ALICIA (awells43) | 160000 | 160000 | 170609.26 | 9/30/2020 - Closing out project per Customer request.
SA | 2 | SA-0457 | Req Scope & Budget Review | Informal Projects | Health Services | Student Health Center | SHC OUTDOOR BUILDING SIGNS | Project request for outdoor building signage. | 2020-02-19 08:43 | FLORES, CLAUDIA (cflores3) | BARRETT, LACRISSA (lbarre11) | 20-0218-I | TERRY, STEPHEN (slterry) | 13500 | 0 | 0 | Dependent on two other Colvard projects, no action until those projects move forward and have a clear schedule and plan.
SA | 2 | SA-0372 | Construction | Informal Projects | Cone Univ Center | Cone University Center | CONE 382 RENOVATION FOR OFSL | Review and provide drawing for update to OFSL Suite (382) in Cone Center. Would like to maximize space efficiency. | 2018-03-14 12:00 | MEEHAN, MORGAN (mmeeha11) | HARRIS, MELODY (mhharris) | 18-0184 | HILL, CAROLINE (cmhill2) | 23700 | 172195.35 | 0 | Consultants / Contractors: * Consultant: TBD * Contractors: TBD Milestones: * Project currently on Hold Pending Funding and Approval * 04/01/2020: Designer Selection Meeting Held, Designer Tentative Selected (Currently Awaiting Approval To Award) Notes / Issues / Concerns: * None at this time.
SA | 0 | SA-0470 | Construction | Informal Projects | Health Services | Student Health Center | SHC 293 CRC RELOCATION | Renovating SHC 293 for CRC program in phases. This would be phase one to include: General construction: soundproof between 293 and AVC, Carpet, Paint, power by window, card reader relocated, move services and ITS data drops. | 2020-08-06 08:31 | BARRETT, LACRISSA (lbarre11) | BARRETT, LACRISSA (lbarre11) | 21-0019-I | CAUDLE, AMANDA (afelock) | 20000 | 20000 | 21-0048-I |  | 12/14/2020 - Scope and Budget sent to Customers on 11/30/2020.
| 0 |  | Created | Capital Projects | FM Architectural/Engineering | McColl-Richardson Field | Football Game Field Replacement |  | 2020-06-15 |  | SPEASE, DARIN (dspease) |  | LANIER, LISA (llanier) | 0 | 0 | 0 | PROJECT NOTES UPDATED: * 01/11/21 CONSULTANTS / CONTRACTORS: * Consultant: Dewberry * Contractors: TBD * Project Delivery Method: Single Prime * Tentative Construction Duration: TBD MILESTONES: * Project Currently On Hold pending discussion with Parking and Transportation * COMPLETE_ SCO Approval To Bid of 90% Construction Documents & Specifications * Project currently ready to bid contingent on East Village Infrastructure (EVI) Project moving forward. * Tentative Timeline for Advertising for Bid to Contractor Award - 8 Weeks * Tentative Timeline for Construction Start to Construction Completion - 120 Days NOTES / ISSUES / CONCERNS: * Project construction contingent on (EVI) bidding within budget. * Lot 5A Add Alternates and final project scope contingent on Add Alternates selected as part of (EVI).
| 0 | 12165 | Created | Capital Projects | Academic Affairs VC | Campus | STUDENT HEALTH & WELLNESS | UNC Charlotte currently has a significant shortage of student health and wellness activity space. A recent study by Brailsford and Dunleavy showed the campus has well under half of the facility space dedicated to student health and wellness by other | 2011-06-02 09:46 | RAJA, JAYARAMAN (jraja) | CEALLAIGH, SHERRYL (sceallai) |  | NEILSON, JOHN (jneilson) | 66000000 | 63634047.1 | 2638.6 | (1-12-21) Carpet in hand. Project on hold until March per Beau Dooley.
IF | 0 |  | Created | Capital Projects | Facilities Management AVC | Campus | NEW CRI ENTRANCE ROAD | Create a new entrance off Hwy 29 | 2019-11-20 05:15 |  | CEALLAIGH, SHERRYL (sceallai) |  | KUGLER, BRIAN (bhkugler) | 1449300 | 1159589.44 | 0 | PROJECT NOTES UPDATED: * 01/11/21 CONSULTANTS / CONTRACTORS: * Consultant: TBD * Contractors: TBD * Project Delivery Method: TBD * Tentative Construction Duration: TBD MILESTONES: --- Project currently on Hold Pending Funding and Approval --- Designer Selection Meeting Held, Designer Tentative Selected --- Brian Kugler sending signed letter to designers notifying project will not move forward at this time.
IF | 0 |  | Created | Capital Projects | FM Architectural/Engineering | Campus | CID 2-EAST VILLAGE INFRASTRUCTURE | East Village infrastructure including Martin Village Road re-alignment, Van Landingham bridge, lighting, telelcom, storm, sanitary and the electrical extension to the campus substation. Includes a traffic signal at John Kirk Drive. | 2013-10-08 08:26 | GILBERT, CHRISTOPHER (cgilbert) | CEALLAIGH, SHERRYL (sceallai) |  | KUGLER, BRIAN (bhkugler) | 4135056.7 | 7410172.79 | 0 | 01/11/21 CONSULTANTS / CONTRACTORS: * Consultant: Kimley Horne * Contractors: CM@R Sheil Sexton * Project Delivery Method: CM@Risk * Tentative Construction Duration: TBD MILESTONES: * Project currently placed on hold 01/04/21 by University Administration. *30 Day Outlook: To Be Complete By 02/11/21 --- Final Billing for Design to Kimley Horne --- Negotiate Additional Pre-Construction Services --- Office notice of Project Suspension to NCDOT * 60 Day Outlook: To Be Complete By 03/11/21 --- Final Payment to CM@Risk for Final Construction Services NOTES / ISSUES / CONCERNS: * Review Bid Numbers and Determine Next Steps For Award of EVI and construction execution. * Need to receive documentation of Supplemental Agreement to secure Funding from NCDOT (Pending Contract Language Discussion if Project is approved to move forward $500,000.00 in funding currently unconfirmed from NCDOT.) Project construction contingent on (EVI) bidding within budget in order to move forward. * Lot 5A Add Alternates and final project scope contingent on Add Alternates selected as part of (EVI). Due to renegotiation of PGMP to 10% higher GMP Sheil Sexton GMP may come in higher then originally projected causing UNCC to have to decide to go in another direction and hard bid the project. If Martin Hall Village Connector is not accepted we have agreed with CDOT to put it in our UNCC Capital Improvement Plan. * Police & ITS Duct Bank may be funded and installed concurrently with EVI as a informal project. If approved, coordination will need to be discussed and executed.
IF | 0 |  | Created | Capital Projects | Facilities Management AVC | Lot 5A | LOT 5A | re-alignment of lot 5A | 2019-11-19 14:10 | CEALLAIGH, SHERRYL (sceallai) | PAQUETTE, NOELLA (njpaquet) |  | KUGLER, BRIAN (bhkugler) | KUGLER, BRIAN (bhkugler) |  |  | PROJECT NOTES UPDATED: * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultant: Dewberry * Contractors: TBD * Project Delivery Method: Single Prime * Tentative Construction Duration: TBD (ON HOLD) MILESTONES: * Project Currently On Hold pending discussion with Parking and Transportation * COMPLETE_ SCO Approval To Bid of 90% Construction Documents & Specifications * Project currently ready to bid contingent on East Village Infrastructure (EVI) Project moving forward. * Tentative Timeline for Advertising for Bid to Contractor Award - 8 Weeks * Tentative Timeline for Construction Start to Construction Completion - 120 Days NOTES / ISSUES / CONCERNS: * Project construction contingent on (EVI) bidding within budget. * Lot 5A Add Alternates and final project scope contingent on Add Alternates selected as part of (EVI).
BA | 0 | BA-1971 | Scope & Budget Requested | Informal Projects | Business Services AVC | Popp Martin Student Union | STUDENT UNION 137-138 STORAGE ROOM MODIFICATIONS | SU Storage Room Modifications, modify 137 and 138 to remove demizing wall. Relocate some metal shelving. Need large item storage and pallet drop area. Provide rolling plastic shelving typical of our dry storage areas to provide more storage within | 2020-07-13 13:57 | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) |  | CAUDLE, AMANDA (afelock) | CAUDLE, AMANDA (afelock) | 21-0012-I |  | (2-1-21) Layouts and budget pricing provided to Drew Averitt on 9/21/20. Pending his approval to proceed.
IF | 0 | BA-1981 | Approved Scope & Budget FAM | Informal Projects | Facilities Informal Projects | Campus | FPFM, FOPS SHELTER & PICNIC TABLES | FPFM, FOPS SHELTER & PICNIC TABLES: Build new covered structure and add picnic tables for outdoor seating and event space at FOPS. Assign to Shawn Kelly. | 2020-09-28 11:46 | FAKE, WILLIAM (wmfake) | WITHERSPOON, MELANIE (mewither) |  | FAKE, WILLIAM (wmfake) | KELLY, SHAWN (skelly64) | 21-0032-I |  | PROJECT NOTES UPDATED: * 02/01/21 CONSULTANTS / CONTRACTORS: * Consultants: TBD * Contractor: TBD * Project Delivery Method: TBD * Tentative Construction Timeline: TBD MILESTONES: * 30 Day Outlook: Completed by 03/01/21 --- Stakeholder meeting held. --- Currently preparing shelter options for stakeholder review. NOTES / ISSUES / CONCERNS: * Project has no funding at this time.
BA | 2 | BA-1919 | Scope & Budget Requested | Informal Projects | Auxiliary Operations | South Village Crossing | SVC TERRACE FURNITURE | SVC Terrace Furniture, propose, review and provide exterior furniture and accessories on the upper floor terrace area. Replace and or relocate existing furniture as supports the overall plan fo rthe terrace. | 2020-02-10 11:20 | AVERITT, DREW (daveritt) | MEDINA, CHARISSE (cturne66) |  | CAUDLE, AMANDA (afelock) | CAUDLE, AMANDA (afelock) | 20-0167 |  | (2-15-21) Working with vendors to get sample pieces in for trial period.